## Planner
LGBT 50 Comms Plan
Aims: - To maximise brand awareness around our "presenting partner" status. - To myth bust internally, promote equal opportnuties and reinforce the Sewell behaviours. - To communicate why its important - happy teams = happy customers. Employee retention, higher work rate. - To engage a new cohort of staff in the City of Culture activities. - To gain feedback from our people about our diversity approaches. - Promote the importance of a diverse workforce to serve our diverse customer base.
|  | WC 19th June | [6 empty] | WC 26th June | [6 empty] | WC 3rd July | [6 empty] | WC 10th July | [6 empty] | WC 17th July | [6 empty] | WC 24th July | [6 empty] | WC 31st July
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Themes and Actvities | Owner(s)
LGBT50 Events
Pride in Hull - Annual Parade, route around the city centre. Celebration in Queens Gardens
House of Kings and Queens Partner night - PES speaking?
House of Kings & Queens at Humber St Gallery - Photography of LGBT house in Freetown, Sierra Leone. Runs through to September.
Duckie Summer Tea Party in Queen Victoria Square
LGBT Entrepreneur Day
Out for a laugh comdey night - Kardomah
I Feel the Love Concert
Agree what we want from presenting partner status
Branding
Logos to feature on 6 sheet brochure being produced by Hull 2017 and tickets | HT/2017
Podium branding on Duckie Summer Tea Party staging | HT/2017
SOTG rainbow product displays | AM
SOTG site branding: Flags, 30x40 posters, till / pumps screens, floor rainbows | HT/AM/CH
Construction branding: UTC site large banner, welfare area posters | CH/HT
FM site branding: Health centre displays at 4 chosen sites | CH/HL
2x van wraps plus A-frame trailer at retail sites | CH/HL
Geneva Way branding: Window graphics, pull up banner and Geneva Way board | CH/HL
Roll out of collateral and launch | All
Internal communication, campaigns and events
"Show Your Colours Day": Posters to advertise, charity donation, lunch time events, building dressing, other ideas? | GA/AM/BO/ HT/PAS/BK/CH
Legacy images - plug on all collateral (NOTE) | HT
10 Tickets to I Feel the Love Concert - Competition? | AM/GA
Parade input - what can we do? call for volunteers? | PAS/AM/GA
Stair painting project planning and execution - Leadership Challenge | BO
Pulse survey question about equal opps focus group | BO
Focus groups (September) | BO
Any inspirational speakers we can get in? Andy/Hull 2017. | PAS
Unconcious bias session (date TBC) | BO
Equality and diversity policy reinforcement / Consider Stonewall | BO
Comms collateral: Events calendar, payslips attachments, Sewell Times pull out | CH/HT
PR and External Campaigns | KW
Reference to Sewell as presenting partner in PR issued by Hull 2017 | CH/ 2017
LGBT fact finding, demographic profiling - locally, in business - feed into messaging | AM/GA
50 years on at Sewell content. | KW
Internal and external messaging. | CH
Staff profiles - background and opportunities | KW
Partner and subcontractor engagement | CH
Digital | BK
Website and social media platform branding | HT
Social media GIFs with key messaging | HT/BK
Social media campaign plan | BK
Citrix homepage branding | HT