## PID
Project name | Look Up
Last updated | 2016-01-17 | [5 empty] | Objectives & metrics
[7 empty] | Metrics |  | Target |  | Forecast/actual
Related documents | [6 empty] | # audience |  | 500000
Project plan | Draft |  | Risk management plan |  |  | Pending |  | Hull residents |  | Y
Budget | Draft |  | Marketing & comms plan |  |  | Pending |  | regional |  | Y
[8 empty] | national |  | Y
Dates | [7 empty] | international |  | Y
Project start date | 2016-01-01 |  | Project live date |  | 2017-01-01 |  |  | children (<16) |  | Y
End of Live date | 2017-12-31 |  | End of eval. date |  | 2018-02-01 |  |  | young people (16-25) |  | Y
[8 empty] | families |  | N
Categories | [7 empty] | older people (60+) |  | N
Type | Hull 2017 Commission |  |  | Strand |  | Look Up |  | self-identify as disabled |  | N
Season | Thru 2017 |  |  | Digital requirements |  | Very high |  | BME |  | Y
[8 empty] | NEET |  | N
Finance | [6 empty] | # temporary jobs created |  | tbc
Total project budget |  | 1200000 |  |  |  |  | # freelance contracts created |  | tbc
Hull 2017 contribution |  | 750000 |  |  |  |  | # participation opportunities |  | tbc
Analysis/project code(s) | [6 empty] | of which for school age |  | tbc
[7 empty] | # commissions |  | tbc
[7 empty] | Objective |  | Met? | Notes
To create a significant programme of art in the public space, throughout the year and across the city centre of Hull, inspired by hull 2017's commitment in 'drawing on the past and present of the city in order to define and celebrate its future'
People
Project Lead | Sam Hunt |  |  | Volunteering lead |  | Shaun Crummey
Producer | Sam Hunt |  |  | Education lead |  | Ian Read
Assistant Producer | TBC |  |  | Marketing lead |  | Laura Smith
Production Manager | TBC |  |  | Community Eng lead |  | James McGuire | Transform people's understanding, appreciation and enjoyment of Hull through the imagination and creative skills of artists invited to make work in and for the city.
|  |  |  | Evaluation lead |  | Elinor Unwin
Engage new audiences for visual arts in the city and to drive footfall to the city centre
Develop and deliver a structured education and engagement programme with a clear focus on the students of HSAD
To develop a series of co-commissioning partnerships enabling extra investment in the artistic programme ensuing impact, scale and ambition is realised.
Performance, Residency & Legacy
What is the model for delivering this project? eg we will employ a creative team, we will outsource to an agency, we are contributing funding but no other resource… | [6 empty] | Performance: Summary of events, including dates, times, venues, ticketing strategy (free/paid, (un)ticketed), age guidelines (free text OR UKFC categories) etc. NB Do not duplicate information stored in Artifax.
The project management and delivery of this programme will be outsourced to specialist consultants managed directly by Hull 2017 Executive Producer | [6 empty] | The amount and type of commissions will be dependent on the confirmed programme, currently in first stage of R&D
How will delivery partners be identified and procured? Refer to the procurement flowchart and note below the agreed process (A–G) for each contract. | [6 empty] | Residency: How will you realise your residency work? What opportunities will be created within the project for our education programme? How will the project help to build new audiences through engagement? Note numbers, types and duration of participation opportunities.
The key delivery partners (the consultants) were procured through an open tender, the partners that will form the basis for co-commission relationships and artistic commissions will be exempt from standard procurement rules (artistic choice) | [6 empty] | There is an ambition that all artists engaged will work within the city and in particular HSAD in order to develop new audiences and to engage students in the process.
Who are the delivery partners? (Contact & organisation name, contract status for each) | [6 empty] | Legacy: What is built into the core project that will ensure legacy?
Curation and Project Management - Andrew Knight (a.knight@aknight@aknight.karoo.co.uk) Hazel Colquhoun(mail@hazelcolquhoun.com) Contracted to deliver full R&D and project plan as stage one by end of February 2016. | [6 empty] | There will be a legacy created through the structured programme of education and engagement focused on HSAD. There will also be a legacy through the development of new audiences for visual arts, as the city centre of Hull is transformed into a free gallery. The programme is designed to help audience view thier city afresh, helping raise aspirations and positive views of teh city centre of Hull.
Volunteer management: What is your expectation of volunteer requirements? (Numbers, roles, responsibilities, duration / period required) | [6 empty] | Project description (200–400 words) for use in marketing materials, on webpages etc. Note that this may be edited.
These will be dependent on the art works commissioned and the producers will work with volunteering at all stages of the projects development to ensure all opportunities are maximised. | [6 empty] | This is a year-long programme of artists works made specifically for public places and spaces in Hull. A diverse range of artists will create temporary, site-specific work investigating and responding to the city. These works will change and challenge people's experiences and perceptions of Hull. They will capture people's imagination and engage them in a creative dialogue about Hull, throwing a new light on who, or what, makes a city.
Version control
Date | Changes and/or approvals
2016-01-19 | Greenlit at Board
ACE
British Council
HLF
Treasury
University of Hull
Big Lottery
Health
Spirit of 2012
Trusts & Foundations
Key funders

## Option sets
Status | Type | Strand | Season | Digital | Y/N
Completed | Hull 2017 Production | 365 Grant Fund | Made in Hull | Very high | Y
Draft | Hull 2017 Commission | Blast Theory | Roots & Routes | High | N
Pending | Co-commission | Caravan of Love | Freedom | Medium
| Funded (strategic partner) | Circus | Tell the World | Low
| Funded (presenting) | Codhead | Curtain Raisers
| Grant-funded | Curtain Raiser 2016 | Thru 2017
| Non-funded (strategic partner) | Dance | Post-2017
| Non-funded (presenting) | Digital commission | n/a
| Non-artistic | Film
Freedom Festival
Fuerza Bruta
Hull 2017 @ New Theatre
Hull Truck
Humber St Arts Programme
Land of Green Ginger
Literature commission
Look Up
Museums / Libraries service
Music
Neighbourhood Network
New Years Eve
PRS New Music Biennial
Radio 1 Big Weekend
Singing City
Site-specific theatre
Slung Low
Street animation
Theatre Sector dev & commissions
Turner Prize