## Sheet1
Item | Supplier | Cost ex vat | option costs | Sub Totals Ex VAT | Description | Notes | Where we're at | More notes 08/04 | Telephone | email | Order wording | Order cost exVAT | Insurance values
LIGHTING
Show Lighting - O1 | 3d | 4000 | 4000 |  | fixtures and rigging only | ESTIMATE |  | TELL HAZEL NOT TO BOTHER
cabling | 3d |  |  |  | waiting for plan before I can cost
delivery | 3d | inc above
Holding area light | 3d | inc above
entrance path lighting | 3d | inc above
Show Lighting - O2 | HPSS |  | 1698 |  | as above |  | received updated quote 05/04
cabling | HPSS |  | 765 |  |  |  | received updated quote 05/04
festoon |  |  | 805 |  |  |  | received updated quote 05/04
delivery | HPSS |  | 330.5 |  |  |  | received updated quote 05/04
Holding area light | HPSS |  | inc in festoon |  |  |  | received updated quote 05/04
entrance path lighting | HPSS |  | 360 |  |  |  | received updated quote 05/04
Lighting crew | HPSS |  | 1870 |  | as required |  | received updated quote 05/04 | We could lose freelancers if we went with this option
Show Lighting - O3 | HSL |  | 1253 |  | no festoon included |  | received quote 04/04
cabling | HSL |  | waiting |  |  |  | received quote 04/04
delivery | HSL |  | 700 |  |  |  | received quote 04/04
Holding area light | HSL |  | inc above |  |  |  | received quote 04/04
entrance path lighting | HSL |  | inc above |  |  |  | received quote 04/04
LIGHTING SUB-TOTAL |  |  |  | 4000
AUDIO
Main Audio - O1 | 3d | 2335.2 |  |  | as spec | delivery in with lighting | received quote 13/03 | SPEAK TO HAZEL MONDAY. emailed Tom to see if we can save a bit more
batteries | 3d | 50 |  |  | for radio mics |  | received quote 13/04
PA tech | 3d | 1320 |  |  | £220 per day |  | received quote 13/05
accom/subs | 3d | 421 |  |  | accomodation & PD's |  | received quote 13/06
Holding area PA | 3d | 644 |  |  | 4 x boxes on stands - Y7p's | each corner | requested quote 13/03
Promenade PA | 3d | 432.4 |  |  | 8 x E8's |  | requested quote 13/03
Main Audio - O2 | HPSS |  | 2885.95 |  | as spec
batteries | HPSS |  | 50 |  | for radio mics
PA tech | HPSS |  | 1350.5 |  | £220 per day | inc delivery
accom/subs | HPSS | n/a | n/a |  | accomodation & PD's
Holding area PA | HPSS |  | 756.98 |  | 4 x boxes on stands - Y7p's | each corner
Promenade PA | HPSS |  | 934.15 |  | 8 x E8's
AUDIO SUB-TOTAL |  |  |  | 5202.6
STRUCTURES
promenade control position | TGE | 50 |  |  | black gazebo
control position | 3D | 450 |  |  | 4m x 3m @ 0.5m | inc delivery & build | received quote 13/03 | SPEAK TO HAZEL MONDAY
ladders | 3D | inc above |  |  | 1 x 10 rung & 1 x 14 rung |  | received quote 13/06
transport & build | 3D | inc above
production/dressing room tent | Nationwide | 465 |  |  | 9m x 6m with lighting |  | requested update 08/04
volunteer tent | periplum bringing | 0 |  |  | periplums army tent |  |  | periplum emailed 08/04
furniture | Nationwide | 95.5 |  |  | 10 x tables, 40 x folding chairs |  | requested update 08/04
additional chairs | Nationwide | 58 |  |  | 40 additional chairs, for audience | £1.45 per chair | requested update 08/04
del/coll | Nationwide | 250 |  |  |  |  | requested update 08/04
STRUCTURES SUB-TOTAL |  |  |  | 1368.5
POWER & DISTRO
Distro | IDE | 736 |  |  | as spec, inc 40 panels cable ramp |  | received quote 14/03 | waiting on plan, emailed Dave to say what's going on
Delivery | IDE | 400 |  |  |  |  | received quote 14/03
show generators | John F Hunts | 600 |  |  | 2 x 100KVA | syncd to load share | requested new quote 22/03 | Emailed Jean to let her know where we're at
tank | John F Hunts | 20 |  |  | 1000l bunded tank |  | requested new quote 22/03
Production set | John F Hunts | 135 |  |  | 40kva pink |  | requested new quote 22/03
tank | John F Hunts | 20 |  |  | 1000l bunded tank |  | requested new quote 22/03
Exit set | John F Hunts | ??? |  |  | 40kva pink |  |  | Need to work out if we need
tank | John F Hunts | ??? |  |  | 1000l bunded tank
Entry set | John F Hunts | 135 |  |  | 40kva pink |  | requested new quote 22/03
tank | John F Hunts | 20 |  |  | 1000l bunded tank |  | requested new quote 22/03
fuel | John F Hunts | 1500 |  |  | as used | ESTIMATE
tower lights | John F Hunts | 240 |  |  | 2 x LED tower lights |  | requested new quote 22/03
del/coll | John F Hunts | 1320 |  |  | delivered Sat and collected Sun |  | requested new quote 22/03
POWER & DISTRO SUB-TOTAL |  |  |  | 5126
PLANT & BARRIERS
Plant | Add plant | 150 |  |  | 9m telehandler | to move generators and fencing | received quote 30/01 | emailed Jon to tell we would be ordering by the middle of the week
del/coll | Add plant | inc above |  |  | sat 29th/Sun 7th |  | received quote 30/01
ped barriers | Actavo | 412.5 | 412.5 |  | 150 panels | May need more | received quote 03/04
Heras Fencing | Actavo | 120 | 120 |  | 40 sets |  | received quote 03/04
del/coll | Actavo | 200 | 200 |  |  |  | received quote 03/04
PLANT SUB-TOTAL |  |  |  | 882.5
CREW
Local crew | The Music Consortium | 1545 |  |  | 2 crew Sat 1000-1800, 4 crew Sun 0900-1700, 2 crew Weds 1000-1800, 6 crew Sat 1030-0230, 2 crew Sun 1000-1400 |  | ordered 05/04
Tech Crew | freelancers | 1560 | 1560 |  | 2 crew Sun, 2 crew Mon, 1 person Tues, weds, 1 person half day Thurs - Sat | 6 days @ £200 pmpd 3 half days at @ £120 | speak to Matty/Adam | If we use HPSS, don't need these two
CREW SUB-TOTAL |  |  |  | 3105
MISCELLANEOUS
ballast | MKM | 218.4 |  |  | 80 x 25kg bags of sand | £2.73 per bag |  | call to see if we can get anymore discount
hessian | J&C Joels | 150 |  |  | to dress stuff | to buy | requested unit cost 08/04 | work out how much
casement | J&C Joels | 150 |  |  | to dress stuff |  | requested unit cost 08/04 | work out how much
catering supplies | ??? | 50 |  |  | cups, tea, coffee |  |  | Gareth to supply burco's, do 2017 have supplies
comms | Events team | 0 |  |  | 20 x DP3400's | inc chargers | Gareth booked | Check with Johnny B that they have surveillance earpieces
accessories | 900 comms | 20 |  |  | 2 x noise cancelling headsets |  | ordered 08/04
del/coll | 900 comms | 25 |  |  | delivered 27th April to pacific exchange | to TGE | ordered 08/04
Cleansing | Hull CC | 672.72 |  |  | Sweep each morning after show | emailed Steve Mckee | ordered 08/04
Bins | Hull CC | 220 |  |  | 4 x 1100l bins | delivered Fri, collected Mon | received quote 21/03 see semail from Lucy | print off agreement and sign
backstage toilets | add plant | 300 |  |  | 6 x single plastics | delivered Saturday | received quote 09/03 | emailed Jon to tell we would be ordering by the middle of the week
service | add plant | 360 |  |  | Tues, Thurs-sun |  | received quote 09/03
Audience toilets | add plant | 860 |  |  | 14 x single plastics and 2 x wheelchair accessible units |  | received quote 09/03
servicing | add plant | 795 |  |  | service Thurs, fri & sat |  | received quote 09/03
del/coll | add plant | 175 |  |  |  |  | received quote 09/03
Trakway | GAP | 600 |  |  | 50 x Groundguards |  | received quote 03/04
Delivery & collection | GAP | 190 |  |  | delivered Friday, Collected Monday |  | received quote 03/04
ground works | pbs construction | 1350 |  |  | to make path safer |  | received quote 04/04 | emailed to inform that we will be the ones paying, 08/04
consumables | TGPS | 50 |  |  | tape, cable ties etc
MISCELLANEOUS SUB-TOTAL |  |  |  | 6186.12
STEWARDING
Stewarding & security - O2 | Prestige | 9661 |  |  | all as per spreadsheet |  | sent Justine updated spreadsheet 05/04
Lost kids | Prestige | 504 |  |  | cover for show nights |  | received quote 06/04
STEWARDING SUB-TOTAL |  |  |  | 10165
H&S
Show first aid | Heart Medical/red cross | 4404 | 3120 |  | 6 x first aiders, ambulance & 2 x paramedics | Gareth's preference is Heart | asked for updated on early show cover
additional show first aid | Heart Medical/red cross | 200 | 160 |  | 2 first aiders starting early 1800-2000
rehearsal first aid | Heart Medical/red cross | 336 | 200 |  | 2 first aiders for 2 rehearsals |  | received quote 10/03
Fire extinguishers | TGPS | 50
H&S SUB-TOTAL |  |  |  | 4990
TM
cones | centurion | 100 |  |  | 50 x no waiting cones | for blue badge parking | requested quote 08/04
TM SUB-TOTAL |  |  |  | 100
FEES
Handling fee | TGPS | 2056.286 |  |  | 5% of all hires
FEES SUB-TOTAL |  |  |  | 2056.286
TOTALS Ex Contingency, Ex VAT |  | 43182.006
Contingency |  | 1817.994
TOTALS inc Contingency - EX VAT |  | 45000
TOTAL inc VAT |  | 54000