## Sheet1
CURIOUS DIRECTIVE: FROGMAN PRODUCTION SCHEDULE |  | Version 2
Date & Time | Activity | Who | Notes
Tuesday 17th October
11:00-12:00 | Internet Survey | KCOM
Monday 30th October
PM 12:30-16:30 | Internet Installation | KCOM | Actual time TBC
13:30-15:00 | Arrival and Load-in | Curious Directive/HPSS/TBC(drapes)
14:30-16:00 | Pipe and Drape Install | TBC | Blackout windows
16:00-17:00 | Rig LX and begin Sound/AV Cable Lay | Curious Directive/HPSS
17:00-19:00 | Control Position Set-up | Curious Directive
Continue Cable Lay
| Continue Pipe and Drape |  | Performance Area
Tuesday 31st October
10:00-13:00 | AV Set-up | Curious Directive
Sound Check
Ethernet internet connection check
13:00-14:00 | Break | All
14:00-17:00 | Focus LX | Curious Directive/HPSS
VR Set-up
Wednesday 1st November
10:00-11:00 | Final Checks | Curious Directive
11:00-12:00 | Cast Checks Tech | Curious Directive
12:00 | Break | All
13:00 | Set up | Curious Directive
14:00 | Doors
14:30 | Show 1 | Curious Directive
15:45 | End
19:00 | Doors
19:30 | Show 2 | Curious Directive
20:45 | End
Thursday 2nd November
14:00 | Doors
14:30 | Show 3 | Curious Directive
15:45 | End
19:00 | Doors
19:30 | Show 4 | Curious Directive
20:45 | End
Friday 3rd November
14:30 | Show 5 | Curious Directive
15:45 | End
19:00 | Doors
19:30 | Show 6 | Curious Directive
20:45 | End
Saturday 4th November
14:00 | Doors
14:30 | Show 7 | Curious Directive
15:45 | End
19:00 | Doors
19:30 | Show 8 | Curious Directive
20:45 | End
Sunday 5th November
14:00 | Doors
14:30 | Show 9 | Curious Directive
15:45 | End
19:00 | Doors
19:30 | Show 10 | Curious Directive
20:45 | End
Monday 6th November - No Shows
Tuesday 7th November
14:30 | Show 11 | Curious Directive
15:45 | End
19:00 | Doors
19:30 | Show 12 | Curious Directive
20:45 | End
Wednesday 8th November
14:30 | Show 13 | Curious Directive
15:45 | End
19:00 | Doors
19:30 | Show 14 | Curious Directive
20:45 | End
Thursday 9th November
14:30 | Show 15 | Curious Directive
15:45 | End
19:00 | Doors
19:30 | Show 16 | Curious Directive
20:45 | End
Friday 10th November
14:30 | Show 17 | Curious Directive
15:45 | End
19:00 | Doors
19:30 | Show 18 | Curious Directive
20:45 | End
Saturday 11th November
14:30 | Show 19 | Curious Directive
15:45 | End
19:00 | Doors
19:30 | Show 2 | Curious Directive
20:45 | End