## Pre-Week
Table 1
|  | Caravan | David | Van | Matt
Pre- initial week
Monday 27th Feb AM | Van load 1 drop off at flat. FOH Fit Up Signage up. | Caravan to Hull; leave HUB 11am, arrive 1pm | David Drives to Leeds with all tools | Yellow van. Alan, Joanna and Alice | HUB
Monday 27th Feb PM | 1pm Alan Phone interview | 4pm-8pm Hessle Road | Work on WW Platforms |  | HUB
David stays in Dorm
Tuesday 28th Feb AM | 745 Alan BBC Humberside. Pigeon mess clean AM. |  | David at Hub, Work on WW Platforms. |  | HUB
Tuesday 28th Feb PM | Sally in Hull all day | 4pm-8pm St Stephens
David stays in Dorm
Wednesday 1st March AM | JR in Leeds 3pm, Sarah & Alice in caravan. Ground protection delivery (time tbc, will ring 1hr before) | 8am-12 Walton St Calum move caravan @ 12 | Matt drop Calum off at Walton street 1130
Wednesday 1st March PM | Jessica move from Grimsby: John Dean Skipper. 1pm Jessica departs Grimsby | 4pm-8pm Mount Pleasant | Matt, David in van at Victoria Dock midday then to Grimsby with Alan and John | 2nd van load: Silver van. Matt return to Leeds with Yellow van, leaving silver van in Hull | Van to Hull via Grimsby: drop off David
Wednesday 1st March EVE |  |  | David back in van to HUB with Matt |  | Van back to Leeds with David
Thursday 2nd March AM | Jessica winched in 8am: Central Crane hire (On site 7am) |  | David at Hub | 3rd Van Load: Matt Driving Yellow van
Thursday 2nd March PM | 1pm box office site visit (JR). George to set up kitchen. | 4pm-8pm Beverley road
Friday 3rd March AM | 11AM Meeting with Justine Potter at Flat. Matting and kerb ramps down.8-9am barrel 1 arrive |  | David at Hub: Scrap metal collection from HUB midday. (A1 Scrap Metals (Middleton) 0113 277 1704) | 4th van load, Matt Yellow with safety boat trailer. Lorry delivery of working platforms and canisters 1pm
Friday 3rd March PM |  | 4pm-8pm Beverley Road | David Drives home
Saturday 4th March AM |  | 11am-3pm North Point |  | 4th Van load. Matt in Yellow van.
Saturday 4th March PM |  | 4.30pm-8.30pm Kingswood
Sunday 5th March | Caravan in to place as office and screen down (Al) |  |  | 5th Van Load by Alan in silver as needed.

## Week 1
| Set | Site | Arrivals | Admin/ FOH
Sunday 5th March |  |  |  |  | David trains to Hull. 18:24 Fulwell-22:19
Monday 6th March AM | White Whale platforms. Mooring eyelets installed by forklift drop area | Matting and kerb ramps down. Lowering structure installed on jetty | Fork Lift arrive early(8am): Headland Plant hire. Barrel delivery 2 arrives 1-2pm | 9am George arrive. Crew into flats pre-lunch. 12noon Luke (work placement) arrives
Monday 6th March PM | Mooring weights (DF) | Jetty Shed (CC/OD) to be delivered 12noon on flatbed truck. 4 required for unload.
Monday 6th March EVE | Alan & Joanna - Village Hall Committee Meeting 7pm
Tuesday 7th March AM | Set in |  | Set from SetFree arrives 10am | 10am - Peter arrives in Hull, check in at digs prior to arrival on site.
Tuesday 7th March PM | Set in |  |  | 1pm - Alan Sodium (2 guests for lunch) 2pm - Alan Sameera meeting (25 Ha'Penny Bridge Way) 3pm - JR Meeting Lindsey, Martin A, Gareth
Wednesday 8th March AM | Set in
Wednesday 8th March PM | Set. All platforms bolted and in water. |  | Lorry 1 gone | 4.30pm Alan What's On Stage (location/format TBC) Louise (Community actor) 6.30 AL
Thursday 9th March AM | Handrailing installed. Steel building structures installed. |  | Second wave of set arrive | ESAG Meeting today (Gareth attending, may receive feedback)
Thursday 9th March PM | Handrailing installed. Steel building structures installed.
Friday 10th March AM | Car test |  |  | 11am - Mimi & Matt Burman (Alan)
Friday 10th March PM | Work continues | Lucy, Sally, Al And PB: communit cast meeting. Wayne Helicopter meeting tbc. |  | Airstream write-up to Hull 2017.
Saturday 11th March AM | Finishing touches, floating cities.
Saturday 11th March PM | Finishing touches, floating cities. |  |  |  | David trains to Fulwell ,12:20

## Week 2
|  | Lights | Arrivals
Sunday 12th March | [5 empty] | David Trains to Hull. 18:24 from Fulwell
Monday 13th March AM | Fixing points secured (AL/MA) | Lights install |  | Rain effect install (CC) | House testing (DF)
Monday 13th March PM |  | Lights install |  | Rain effect install (CC) | House testing (DF) | 3pm: Opening Monologues: OS, NE
Monday 13th March EVE | Alan & Joanna Residents Meeting 6.30pm
Tuesday 14th March AM | Water screen install (AL/DF) | Lights install | Waterscreen arrive (Laser hire) | Rain effect install (CC) |  | Midday Singing: OS, NE, HF
Tuesday 14th March PM | 6pm: David and Polly Pattison coming to chat community script | Lights install | Telehander departs 4pm | Rain effect install (CC) |  | 3pm: Opening Monologues: OS, NE
Wednesday 15th March AM | Pyro Install | Lights install | Doug arrives | Magic Gate install (CC) | Wilderness moving platform
Wednesday 15th March PM | Pyro install and evening show | Lights install | 3pm Calre Martynski PHD visiting BC/AL | Magic Gate install (CC) | Smoke effect install (Hamish) | 2PM: Emam Monologues
Wednesday 15th March EVE |  |  | Brett meeting AL et al about community video
Thursday 16th March AM | Platform choreography session | Lights install |  | Sound system install (MA)
Thursday 16th March PM | Pyro and Heli test (eve) | Lights install |  |  |  | 2PM: Senton Monologues
Friday 17th March AM | Life jacket install (DF) |  |  |  | 84 South Bridge Rd gas check
Friday 17th March PM | 1st footage test on water screen (Brett) | Lights show and note
Saturday 18th March AM | Fence to the Wilderness install and test
Saturday 18th March PM | Chorus meeting (Village Hall) |  |  |  |  | David Trains home midday