## Sheet1
Production | The Last Ballad of Lillian Bilocca
Venue | Guildhall, Hull
Artform | Site Specific
Reh weeks (inc Tech) | 5 | Actors | 8 | Subsistence | 200
Running Weeks | 2 | Musicians | 6 | No of Perfs | 14 | Capacity | 200
SUMMARY | DEPARTMENT | [9 empty] | BUDGET | FORECAST | DIFFERENCE | COMMITTED
| ZK101 - COMMISSIONING & FEES | [9 empty] | 2772 | 2772 | 0 |  | Royalties
| ZK102 - DEVELOPMENT & R&D | [9 empty] | 5250 | 50 | 5200 |  | Commission for script & music included here
| ZK103 - CREATIVE TEAM, PRODUCTION TEAM & CONSULTANTS | [9 empty] | 130909.1067 | 117108.6667 | 13800.44
| ZK104 - PERFORMERS AND MUSICIANS | [9 empty] | 72954.1867 | 47754.1867 | 25200
| ZK105 - REHEARSAL COSTS | [9 empty] | 4750 | 4750 | 0
| ZK106 - TECHNICAL & PRODUCTION | [9 empty] | 67800 | 0 | 67800
| ZK107 - VENUE & LOGISTICS | [9 empty] | 16250 | 0 | 16250
| ZK108 - PROGRAMME LEGAL & DOCUMENTATION | [9 empty] | 3500 | 0 | 3500
| ZK109 - PROGRAMME MARKETING, DIGITAL & COMMS | [9 empty] | 18000 | 0 | 18000
| ZK110 - PROGRAMME EDUCATION & COMMUNITY ENGAGEMENT | [9 empty] | 6500 | 0 | 6500
| ZK111 - PROGRAMME VOLUNTEERING | [9 empty] | 1050 | 0 | 1050
| ZK112 - ARTIST & GUEST LIAISON | [9 empty] | 1500 | 0 | 1500
| ZK113 - RUNNING COSTS | [9 empty] | 0 | 0 | 0 |  | Tech running built into Tech & Production
| ZK114 - ADMIN & MISC | [9 empty] | 500 | 0 | 500
| TOTAL | [9 empty] | 331735.2933 | 172434.8533 | 159300.44
| Net Box Office | 2200 | av net per perf | [7 empty] | 30800 | 30800 |  |  | Based on capacity of 200; AV £22 tickets (face value); 60% capacity of 200 = 120 paid tickets per night
| Hull 2017 Budget | [9 empty] | 300000 | 300000 |  |  | HD increased
| Balance | [9 empty] | -935.2933 | 158365.1467
ZK101 - COMMISSIONING & FEES | [14 empty] | Notes
Visual art commissioning & fees
| SUB TOTAL | [9 empty] | 0
Music commissioning & fees
| SUB TOTAL | [9 empty] | 0
| Drama commissioning & fees | 9% | Royalty of Net Box Office | [7 empty] | 2772 | 2772 | 2772 |  | 6% author; 3% music & lyrics; available to cover licensing of extant music (Tariff T)
| SUB TOTAL | [9 empty] | 2772 | 2772 | 2772
Dance commissioning & fees
| SUB TOTAL | [9 empty] | 0
Comedy commissioning & fees
| SUB TOTAL | [9 empty] | 0
Circus commissioning & fees
| SUB TOTAL | [9 empty] | 0
Digital commissioning & fees
| SUB TOTAL | [9 empty] | 0
Literature commissioning & fees
| SUB TOTAL | [9 empty] | 0
Opera commissioning & fees
| SUB TOTAL | [9 empty] | 0
Major Project commissioning & fees
| SUB TOTAL | [9 empty] | 0
Film commissioning & fees
| SUB TOTAL | [9 empty] | 0
Photography commissioning & fees
| SUB TOTAL | [9 empty] | 0
Technical & Production fees
| SUB TOTAL | [9 empty] | 0
Grants
| SUB TOTAL | [9 empty] | 0
| TOTAL COMMISSIONING & FEES | [9 empty] | 2772 | 2772
ZK102 - DEVELOPMENT & R&D
| R&D Fees | [9 empty] | 2250 | 2250 |  |  | Oct '16 R&D | 2250
| SUB TOTAL | [9 empty] | 2250 | 2250
| R&D Travel | [9 empty] | 500 | 500 |  |  | Oct '16 R&D
| SUB TOTAL | [9 empty] | 500 | 500
| R&D Hotels & accommodation | [9 empty] | 500 | 500 |  |  | Oct '16 R&D
| SUB TOTAL | [9 empty] | 500 | 500
| R&D Professional Fees | [9 empty] | 1500 | 1500 |  |  | reduced by £1k
| SUB TOTAL | [9 empty] | 1500 | 1500
| R&D meeting & workshop costs | [9 empty] | 500 | 500 |  |  | Assumes HD & LA travel. All other costs in kind from RET
| SUB TOTAL | [9 empty] | 500 | 500
| Subsistence | [9 empty] | 0 | 0
| SUB TOTAL | [9 empty] | 0 | 0
| TOTAL DEVELOPMENT & R&D | [9 empty] | 5250
ZK103 - CREATIVE TEAM, PRODUCTION TEAM & CONSULTANTS
Sub code | Details
Consultant Costs
| SUB TOTAL | [9 empty] | 0
|  |  |  | BUDGET | FORECAST | BUDGET | FORECAST | BUDGET | FORECAST
| Lead Creatives | Names |  | Fee |  | Travel |  | Expenses
| Production Manager |  |  | 8000 | 9500 | 500 | 500 | 1000 | 1000 |  | 9500 | 11000 |  |  | HD raised by £1k to £8k;
| Casting Director |  |  | 3000 | 3000 | 300 | 300 | 0 | 0 |  | 3300 | 3300 |  |  | LA TRAVEL TO SEE PRODUCTION IN HULL?
| Writer | MP |  | 10000.44 | 8000 | 800 | 800 | 1200 | 1200 |  | 12000.44 | 10000 |  |  | £8000 fee; £55.54 per day for 6 days per week for 6 weeks;
| Composer | AM |  | 8500 |  | 800 |  | 1200 |  |  | 10500 | 0 |  |  | LA inserted expenses & travel
| Director | SF |  | 8500 | 8500 | 800 | 800 | 1000 | 1000 |  | 10300 | 10300
| Asso Movement Director Community |  |  | 4000 | 3000 | 500 | 500 | 500 | 1000 |  | 5000 | 4500 |  |  | LA reduced from £5k; HD revised. Manc visits
| Set & Costume Designer | AS |  | 8000 | 8500 | 800 | 800 | 1000 | 1000 |  | 9800 | 10300 |  |  | LA increased 7k to 8k
| Fight Director |  |  | 700 | 700 | 300 | 300 | 0 | 0 |  | 1000 | 1000
| Lighting Designer | CD |  | 3000 | 3000 | 500 | 500 | 600 | 500 |  | 4100 | 4000 |  |  | LA offered this amount. HD to sign off. Subs question
| Sound Designer |  |  | 3000 | 3000 | 500 | 500 | 600 | 500 |  | 4100 | 4000
| Costume Supervisor |  |  | 0 |  | 0 |  | 0 |  |  | 0 | 0 |  |  | LA reduced from £5k; HD removed - covered in Production Team
| Co-direction / Choreography | IK |  | 6400 | 7000 | 1000 | 600 | 1200 | 1000 |  | 8600 | 8600 |  |  | LA Increased. Needs accommodation Manc, Hull. Flag re travel/accomm for comms cast
| Prehearsal Pianist | [9 empty] | 0 | 0
| Voice |  |  | 1000 | 1000 | 0 | 0 | 250 | 250 |  | 1250 | 1250 |  |  | LA inserted incase not all Hull actors.
| Musical Director / Supervisor |  |  | 1500 |  | 500 |  | 600 |  |  | 2600 | 0 |  |  | Assume this person is additional to AMcN; local to Hull
| Consultants |  |  | 1600 | 1600 | 300 | 300 | 0 | 0 |  | 1900 | 1900 |  |  | LA reduced fee by 1000
| Dramaturg |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | LA seems high so reduced from £5k to £4k. Scotland based so expensive T&A
63200 | TOTALS |  |  | 67200.44 | 56800 | 7600 | 5900 | 9150 | 7450 |  | 83950.44 | 70150
| Lead Creatives | [9 empty] | 67200.44 | 56800
| SUB TOTAL | [9 empty] | 67200.44 | 56800
| Assistant Creatives | [9 empty] | 0 | 0 |  |  | MOVE OVER TO CORE CREATIVE RATHER THAN ASSISTANT
| SUB TOTAL | [9 empty] | 0 | 0
| Creative Team Expenses | [9 empty] | 16750 | 13350
| SUB TOTAL | [9 empty] | 16750 | 13350
Sub code | Details | Rehearsals |  |  |  |  | Running |  |  |  | Total Run
| Production Team | Number of Production | Number Weeks | Weekly Salary | Total Salary | Subs & Travel | Weeks | Weekly Salary | Total salary | Subs & Travel | BUDGET | FORECAST
| Company Stage Manager | 1 | 5 | 600 | 3000 | 1000 | 2 | 600 | 1200 | 400 | 5600 | 5600
| Deputy Stage Manager | 1 | 5 | 500 | 2500 | 1000 | 2 | 500 | 1000 | 400 | 4900 | 4900
| Assistant Stage Manager | 1 | 5 | 450 | 2250 | 1000 | 2 | 450 | 900 | 400 | 4550 | 4550
| Assistant Stage Manager Comm Cast / Crew | 1 | 5 | 450 | 2250 | 1000 | 2 | 450 | 900 | 400 | 4550 | 4550 |  |  | ASM to support community rehearsals in Hull prior to run
| Stage Management Overtime |  | 8% |  | 620 |  |  | 5% | 155 |  | 775 | 775
| Stage Management NI |  | 13.8% |  |  |  |  | 13.8% | [6 empty] | NI not applicable
| Stage Management Holiday |  | 8.333% |  | 645.8333 |  |  | 8.333% | 258.3333 |  | 904.1667 | 904.1667
| Stage Management Pensions |  | 3% |  | 232.5 |  |  | 3% | 93 |  | 325.5 | 325.5
| Sound Production | 1 | 3 | 1000 | 3000 | 600 | 0 | 1000 | 0 | 0 | 3600 | 3600 |  |  | Left this as 3 weeks rather than 5 in original budget
| Sound No 1 | 1 | 2 | 600 | 1200 | 400 | 2 | 600 | 1200 | 400 | 3200 | 3200
| LX Production | 1 | 3 | 1000 | 3000 | 600 | 0 | 1000 | 0 | 0 | 3600 | 3600
| LX & Operator | 1 | 2 | 500 | 1000 | 400 | 2 | 500 | 1000 | 400 | 2800 | 2800
| Costume Supervisor | 1 | 5 | 600 | 3000 | 1000 | 1 | 600 | 600 | 200 | 4800 | 4800 |  |  | Present for all rehearsal weeks, tech week and 1 more week to cover prep
| Wigs Supervisor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Wardrobe Maintenance / Dresser | 2 | 1 | 450 | 900 |  | 2 | 450 | 1800 |  | 2700 | 2700 |  |  | LA increased to 2 people. Will we need washing separate due to hours? Likely to be lots due to community cast. Assume local person
| Crew / Instrument tech | 1 | 1 | 450 | 450 |  | 2 | 450 | 900 |  | 1350 | 1350 |  |  | 1 Crew; 1 additiona ASM / Tech added; Assume local person
| Tech Staff Overtime |  | 8% |  | 1004 |  |  | 5% | 140 |  | 1144 | 1144
| Tech Staff NI |  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  | NI not applicable
| Production Team Travel | 12 |  | 90 |  | 1080 |  | 90 |  | 1080 | 2160 | 2160 |  |  | Increased due to additional dresser & crew
| Production Team Expenses | 0
| SUB TOTAL |  |  |  | 25052.3333 | 8080 |  |  | 10146.3333 | 3680 | 46958.6667 | 46958.6667 |  |  | 46958.6667
| TOTAL CREATIVE TEAM, PRODUCTION & CONSULTANTS | [9 empty] | 130909.1067 | 117108.6667
ZK104 - PERFORMERS AND MUSICIANS
Sub code | Details | Rehearsals |  |  |  |  | Running |  |  |  | BUDGET | FORECAST |  |  | Including Sunday payments
| Performers Salaries | Number Artists | Number Weeks | Weekly Salary | Total Salary | Subs | Weeks | Weekly Salary | Total Salary | Subs | TOTAL |  |  |  | 7 show week
| Actors | 8 | 5 | 500 | 20000 | 8000 | 2 | 500 | 8000 | 3200 | 39200 | 39200 |  |  | Inclusive instrument hire
| Understudies | 0 | 5 | 60 | 0 | 0 | 2 | 60 | 0 | 0 | 0 | 0
| Dance Captain | 1 | 5 | 37 | 185 | 1000 | 2 | 37 | 74 | 74 | 1333 | 1333 |  |  | LA included a dance captain due to movement.
| Company Overtime |  | 8% |  | 1614.8 |  |  | 5% | 403.7 |  | 2018.5 | 2018.5
| Company NI |  | 13.8% |  |  |  |  | 13.8% |  |  | 0 | 0 |  |  | NI not applicable
| Company Holiday Pay |  | 8.333% |  | 1682.0833 |  |  | 8.333% | 672.8333 |  | 2354.9167 | 2354.9167
| Company Pensions |  | 3% |  | 605.55 |  |  | 3% | 242.22 |  | 847.77 | 847.77
| Company Medical Costs | 8 | 5 | 10 | 400 |  | 2 | 10 | 160 |  | 560 | 560
| Company Travel/Misc | 8 |  | 90 | 720 |  | 2 | 90 | 720 |  | 1440 | 1440
| Totals Company Costs |  |  |  | 25207.4333 | 9000 |  |  | 10272.7533 | 3274 | 47754.1867 | 47754.1867
| Musicians | 6 | 3 | 500 | 9000 | 3600 | 2 | 500 | 6000 | 2400 | 21000 | 21000 |  |  | Full Band for 2 wks reh plus tech
| Musicians Overtime |  | 8% |  | 720 |  |  | 5% | 300 |  | 1020 | 1020
| Musicians NI |  | 13.8% |  |  |  |  | 13.8% |  |  | 0 | 0
| Musicians Holiday Pay |  | 8.333% |  | 750 |  |  | 8.333% | 500 |  | 1250 | 1250
| Musicians Pensions |  | 3% |  | 270 |  |  | 3% | 180 |  | 450 | 450
| Musicians Travel | 6 |  | 90 | 540 |  | 2 | 90 | 540 |  | 1080 | 1080
| Musicians Porterage | 6 |  | 50 | 300 |  | 2 | 50 | 100 |  | 400 | 400
| Total Musicians Costs |  |  |  | 11580 | 3600 |  |  | 7620 | 2400 | 25200 | 25200
| SUB TOTAL |  |  |  | 11580 | 3600 |  |  | 7620 | 2400 | 25200 | 25200
| Performer Fees | [9 empty] | 35480.1867 | 35480.1867
| SUB TOTAL | [9 empty] | 35480.1867 | 35480.1867
| Performer Expenses | [9 empty] | 12274 | 12274
| SUB TOTAL | [9 empty] | 12274 | 12274
| TOTAL PERFORMERS & MUSICIANS | [9 empty] | 72954.1867 | 47754.1867
47754.1867
ZK105 - REHEARSAL COSTS
[11 empty] | BUDGET | FORECAST
| Rehearsal venue | [9 empty] | 2000 | 2000 |  |  | Assume MRE space provided without cost for Manchester rehearsals; Hull space required for community and full rehearsals
| SUB TOTAL | [9 empty] | 2000 | 2000
Rehearsal set-up costs
| Scripts & Photocopying | [9 empty] | 250 | 250
| Music Copying & Orchestration costs | [9 empty] | 1000 | 1000
| Model Box Costs | [9 empty] | 500 | 500 |  |  | LA reduced 1.5k to 500 as per agreement with AS
| SUB TOTAL | [9 empty] | 1250 | 1250
Rehearsal running costs
| Rehearsal costs | [9 empty] | 1000 | 1000 |  |  | LA increased from £500 to include rehearsal set, steel deck, PA etc.
| SUB TOTAL | [9 empty] | 1000 | 1000
| Volunteer Cast Costs | [9 empty] | 500 | 500
| SUB TOTAL | [9 empty] | 500 | 500
| TOTAL REHEARSAL COSTS | [9 empty] | 4750 | 4750
ZK106 - TECHNICAL & PRODUCTION
Technical Stage
| TSM Materials | [9 empty] | 2000
| Fit-Up | [9 empty] | 10000
| Get-Out | to cover weekly changeovers | [8 empty] | 10000
| Venue Preparation | dressing rooms, box office, company office, wifi etc | [8 empty] | 15000
| Transport costs | [9 empty] | 2000
| SUB TOTAL | [9 empty] | 39000
Costume & Wigs
| Wardrobe Materials | [9 empty] | 8000
| Costume - running & hires | 200 | per running week | [7 empty] | 400
| SUB TOTAL | [9 empty] | 8400
Set & Props
| Materials | [9 empty] | 7000
| Props - running & hires | 200 | per running week | [7 empty] | 400
| SUB TOTAL | [9 empty] | 7400
Lighting & AV
| Build materials | [9 empty] | 1000
| LX & AV running & hires | 1000 | tech week plus per running week | [7 empty] | 3000
| SUB TOTAL | [9 empty] | 4000
| Audio & Comms | [13 empty] | To include radio mics, CANS, 6 Piece band, vocals, backline etc
| Build Materials | [9 empty] | 1000
| Instrument maintenance | [9 empty] | 500
| Sound running & hires | 2500 | tech week plus per running week | [7 empty] | 7500
| SUB TOTAL | [9 empty] | 9000
Rigging
| SUB TOTAL | [9 empty] | 0
Power & Generators
| SUB TOTAL | [9 empty] | 0
Pyrotechnics
| SUB TOTAL | [9 empty] | 0
| TOTAL TECHNICAL & PRODUCTION | [9 empty] | 67800 |  |  |  | Includes running physical
ZK107 - VENUE & LOGISTICS
Venue costs
| Audition costs | [9 empty] | 1000
| Venue fees | [9 empty] | 10000 |  |  |  | Requires Guildhall to be 'provided' for reduced hire and basic costs
| SUB TOTAL | [9 empty] | 11000
Comms Equipment
| SUB TOTAL | [9 empty] | 0
Production Transport
| SUB TOTAL | [9 empty] | 0
Temporary Buildings
| SUB TOTAL | [9 empty] | 0
Temporary Structures
| SUB TOTAL | [9 empty] | 0
Policing, Safety & Medical
| SUB TOTAL | [9 empty] | 0
| Cleaning & Waste | [13 empty] | LA included in venue costs
| SUB TOTAL | [9 empty] | 0
Plant Hire
| SUB TOTAL | [9 empty] | 0
Site Prep & Security
| FOH Attendants / Security | 6 @ £50 per perf; plus 1 session prep | [8 empty] | 4500
| FOH Fireman / First Aid | £50 per perf; plus 1 session prep | [8 empty] | 750
| FOH MANAGER | 1 @ £75 per perf, plus 3 sessions prep | [8 empty] | 1275
| BOX OFFICE Staff | 2 @ £75 per perf | [8 empty] | 2100
| TOTAL | [9 empty] | 5250
| TOTAL VENUE & LOGISTICS | [9 empty] | 16250
ZK108 - PROGRAMME LEGAL & DOCUMENTATION
Legal
| Insurance | [9 empty] | 3500 |  |  |  | Venue insurance for found space & all kit, instruments etc
| SUB TOTAL | [9 empty] | 3500
Documentation
| SUB TOTAL | [9 empty] | 0
| TOTAL PROGRAMME LEGAL & DOCUMENTATION | [9 empty] | 3500
ZK109 - PROGRAMME MARKETING, DIGITAL & COMMS
Branding & Design
| Marketing costs | [9 empty] | 15000 |  |  |  | LA to discuss with PB. Note this is the same as R2V. Site dressing, instructions etc.
| SUB TOTAL | [9 empty] | 15000
Distribution Costs
| SUB TOTAL | [9 empty] | 0
Print Costs
| SUB TOTAL | [9 empty] | 0
| Photography | inc image generation | [8 empty] | 2500
| SUB TOTAL | [9 empty] | 2500
| Filming | [9 empty] | 500 |  |  |  | LA inserted as we will want an archive of the show.
| SUB TOTAL | [9 empty] | 500
Digital Content Creation
| SUB TOTAL | [9 empty] | 0
Web Development
| SUB TOTAL | [9 empty] | 0
Evaluation & Research
| SUB TOTAL | [9 empty] | 0
| TOTAL PROGRAMME MARKETING, DIGITAL & COMMS | [9 empty] | 18000
ZK110 - PROGRAMME EDUCATION & COMMUNITY ENGAGEMENT
Engagement Events
| Education resources | [9 empty] | 1500
| SUB TOTAL | [9 empty] | 1500
School Activity
| SUB TOTAL | [9 empty] | 0
Public Programming
| SUB TOTAL | [9 empty] | 0
Access Initiatives
| Interpreted Performances | [9 empty] | 800
| SUB TOTAL | [9 empty] | 800
Participation Workshops
| SUB TOTALS | [9 empty] | 0
| Community Cast | [9 empty] | 4200 |  |  |  | £10 per perf for 30 community cast
| SUB TOTAL | [9 empty] | 4200
| TOTAL PROGRAMME, EDUCATION & COMMUNITY | [9 empty] | 6500
ZK111 - PROGRAMME VOLUNTEERING
PPE
| SUB TOTAL | [9 empty] | 0
Costume & Wigs
| SUB TOTAL | [9 empty] | 0
External Training
| SUB TOTAL | [9 empty] | 0
| Volunteer Co-ordinator | 1 @ £75 per show | [8 empty] | 1050 |  |  |  | LA inserted. Based on 1 FOH (including volunteering) & 2 BO. This might still be too low?
| SUB TOTAL | [9 empty] | 1050
DBS Checks
| SUB TOTAL | [9 empty] | 0
| TOTAL PROGRAMME VOLUNTEERING | [9 empty] | 1050
ZK112 - ARTIST & GUEST LIAISON
Accreditation
| SUB TOTAL | [9 empty] | 0
HLT Costs
| SUB TOTAL | [9 empty] | 0
VIP Guests
| SUB TOTAL | [9 empty] | 0
| Catering | Press Night | [8 empty] | 500
| Green Room Facilities | [9 empty] | 1000
| SUB TOTAL | [9 empty] | 1500
Media Guests
| SUB TOTAL | [9 empty] | 0
| TOTAL ARTIST & GUEST LIAISON | [9 empty] | 1500
ZK113 - RUNNING COSTS
Venue Extension Running Costs
| SUB TOTALS | [9 empty] | 0
Weekly Extension Wages Costs
| SUB TOTAL | [9 empty] | 0
Weekly Extension Running Costs
| SUB TOTAL | [9 empty] | 0
| TOTAL RUNNING COSTS | [9 empty] | 0
ZK114 - ADMIN & MISC
Admin Costs
| Producer Costs | [9 empty] | 500 |  |  |  | LA increased due to rehearsals in Manchester; reduced as provision in R&D costs
| SUB TOTAL | [9 empty] | 500
Equipment & Tools
| SUB TOTAL | [9 empty] | 0
| TOTAL ADMIN & MISC | [9 empty] | 500
TOTAL COSTS OF THE PRODUCTION | [10 empty] | 331735.2933 |  |  |  | 328165.96
Original budget | [10 empty] | 340448 |  |  |  | 340448
[11 empty] | 8712.7067 |  |  |  | 12282.04
Note on F109: Alvisl: Includes model box
Note on B119: Alvisl: Covered by SF
Note on D161: Alvisl: Includes tech