## Top Level Budget
Hull Comedy Festival Student Night 26 September
Production
Projection | 5000
Production Person | 150
Room Dressing
Comedy Festival Banners | 2000
Other dressing | 1000
Tables x 10 | 105
Marketing
Flyers | 200
Posters | 200
EDM
Design | 200
Feather Banners
Campus Banner | 750
Performance
Comedians | 13000
Rider | 150
BSL | 500
Operations
Event Manager | 150
Venue Hire | 1830
First Aid | 102
Venue Staff
Venue Security | 300
25637

## Timeline
Date | Activity
2017-08-28
2017-08-29 | Confirmed Line Up
Marketing Material designed
Site dressing designed
2017-08-30 | Off the Kerb contracted
2017-08-31
2017-09-01 | Feedback on marketing material designed and site dressing materials
2017-09-02
2017-09-03
2017-09-04 | Receive Final Marketing designs
2017-09-05 | Send marketing to print
2017-09-06
2017-09-07
2017-09-08 | Receive Marketing Materials
All production confirmed
2017-09-09
2017-09-10
2017-09-11 | Deliver marketing to university
2017-09-12
2017-09-13
2017-09-14
2017-09-15
2017-09-16
2017-09-17
2017-09-18 | Hull Comedy Festival Miniguide to print
2017-09-19
2017-09-20
2017-09-21
2017-09-22
2017-09-23
2017-09-24
2017-09-25 | Delivery of site dressing
Receive Hull Comedy Festival mini guide
2017-09-26 | Comedy Festival Launch and Student Comedy Festival