Hull 2017 
Project Plan

Return to Vegas 
from an idea by Roland Gift 
by Bob Carlton & Roland Gift 
music & arrangements by Roland Gift & Fine Young Cannibals 

"A True Story that Never Happened"

Summary

Johnny Holloway, a faded pop star, has been serving time for a drugs related crime, the exact nature of which we will find out during the action of the play. The story concerns his problems caused by an unexpected inheritance; his troubled relationship with an ex lover, Carol; and his eventual redemption and exoneration for a crime he did not commit.

Venue		The Welly, Beverley Road, Hull

A nightclub with sufficient interior capacity to allow a standing audience, to  move to see the action in 3-5 locations around the club space.

Music 		Original new works by Roland Gift
		Extant works to include ‘I’m Not the Man I Used to Be’ and 
 		‘Johnny Come Home’

Project Timeline
May ’16	Commission Full Script & Licence Music (‘new’ music & FYC songs)

Confirm Venue terms - Welly

June ’16    	Creative Team confirm (Set/Costume, LX & Sound) & Production Manager

		Confirm & set-up photoshoot / commission artwork for production     		 	image.

July ’16       	Full Draft Delivered – 1st Delivery
           	Script Workshop (creative team & cast & band – read/sing through –  		 	Hull)

                   	Marketing - Production Copy & Image Deadline – NB start of July

August ’16    	Script – Final Draft – Acceptance Pending

Prelim Designs
 	Outline Costings

Sept ’16       	Final Designs
Detailed Production Costings

Casting & Production Team confirm

22 Sept – Hull 2017 Press Launch Event

Oct ’16       	Pre-Production – Build & venue prep

Nov ’16       	Pre-Production – Build & venue prep

Dec ’16     	Rehearsals
                	Pre-Production – Build & venue prep

Jan ’17       	Final Rehearsals	
Tech & Open w/c 16 Jan

Feb ’17         	Run & Close w/c 13 Feb

The following details describe the production parameters which reflect the project budget 

Creative Team
Composer & MD/Arranger 		Roland Gift
Writers 				Bob Carlton & Roland Gift

Director 				Bob Carlton
Set & Costume Designer
Lighting Designer
Sound Designer
AV Designer
Casting Director

Production Team 
Production Manager
Company Manager
DSM
ASM
Sound Op 
LX & AV Op
Dresser / Wardrobe Maint x1
Technician x 1
FOH Manager
Stewards 
Security
Access Performance Interpreter

Production Sound			
Production LX & AV
Wardrobe Supervisor

Cast & Band 
Maximum cast size = 8; Maximum band size = 5

JOHNNY HOLLOWAY			Roland Gift
RICKY WHEELER
CAROL [A.K.A. ANGEL]
EZRA
KAISHA
SEAN
BOUNCER 1 
BOUNCER 2  

BAND MEMBER 1	
BAND MEMBER 2
BAND MEMBER 3
BAND MEMBER 4
BAND MEMBER 5

Production Schedule
Rehearsals Week 1			wc 12 Dec
Rehearsals Week 2 			wc 19 Dec
Holiday Week 				wc 26 Dec
Rehearsals Week 3			wc 2 Jan
Rehearsals Week 4			wc 9 Jan
Production Week			wc 16 Jan			x perfs
Performances				22 – 16 Jan			5 perfs
					29 Jan – 2 Feb 		5 perfs
 					5 – 9 Feb 			5 perfs
					12 – 16 Feb 			5 perfs

All details of performance schedule at Welly subject to venue negotiation

Previews & Press Night 		TBC