RIBA/LOOK UP 2017 COMPETITION

Draft Programme v1 290116

2016

Competition Launch/Issue Competitors Invitations

Invites out:	23rd May (2 weeks) – up to 20 practices

Accepted by:	3rd June

Press Launch:	w/c 6th June

Briefs issued:	w/c 6th June

RFC’s :		by 17th June

EOI’s in:	by 24th June

Shortlist:	Review & finalise by 1st July (1 week)

Detail Design (3 competitors)

Commence:	w/c 4th July (12 weeks)

Submit:	by 23rd September

Review Detail Designs & Select Winning Scheme

Commence:	w/c 26th September (1 week)

Announce Winning Design (delivery subject to consents)

Commence:	w/c 3rd October

Consents (inc. planning)

Commence:	w/c 10th October (12 weeks)

2017

Consents secured

By:		 3rd January

Fabrication & Installation

Commence:	w/c 9th January

Complete:	w/c 26th June (25 weeks)

Public Launch & Display

Launch:	w/c 3rd July (to coincide with 2017 ‘Freedom’ season

Conclude:	w/c 23rd October (extends beyond ‘Freedom’ to cover opening of Turner Prize Competition & potential activities around Stirling Prize.

Expressions of Interest to include statement re; form of architect/artist collaboration, outline concept (no more than 2 pages of visuals, 500 word rationale, detailed cv’s of design team

Submissions to include model, renderings, plans, material samples, written description, programme and approximation of costs (i.e. to establish reasonable degree of aesthetic, cost, programme and technical feasibility)