PROJECT OVERVIEW – SLUNG LOW: FLOOD

| NAME OF PROJECT | Slung Low: Flood |
| --- | --- |
| PROJECT START - FINISH DATES | 11 May 2016 - ??/??/2017 |
| PROJECT LIVE DATES | Part 1: Prologue (27 February 2016 – 4 March Airstream Tour; 27 February – indefinite online) – short film Part 2: Abundance (11 April - 15 April 2017) – live play Part 3: To the Sea (Summer 2017) – live play on BBC TV Part 4: New World (October 2017) – live play |
| COC PROJECT LEAD | Martin Green |
| PROJECT SUMMARY | Flood is an extraordinary year-long epic commissioned for Hull 2017 that will be told online, live in Hull and on BBC television. It is created by the ground-breaking Leeds-based theatre company Slung Low, directed by artistic director Alan Lane and written by award-winning playwright James Phillips. One day it starts to rain and no-one knows why. And it doesn’t stop. Far out on the North Sea a fisherman raises a girl in his net, miraculously alive from the deep sea. Is she one of the migrants now washing up on English shores? Or someone sent for some higher purpose? |
| TARGET AUDIENCES - ATTENDERS | - Residents of Victoria Dock - Disabled audiences - General audience (or are there other target communities, e.g. schools, young people, older people, BAME groups,) |
| TARGET AUDIENCES - PARTICIPANTS | - Residents of Victoria Dock - Part 2: Hull 2017 Volunteers – general (or specific?) - Part 4: Hull 2017 Volunteers and wider general public (or specific?) |
| CREATIVE CORE TEAM | - Martin Green (Executive Producer, Hull 2017) - Lindsey Alvis (Producer, Hull 2017) - Martin Atkinson (Assistant Producer, Hull 2017) - [Insert key leads at Slung Low and Job Title] - Alan Lane (Director) - James Phillips (Writer) - [Insert any others that are missing] |
| CAST MEMBERS / ARTISTS | - Professional cast - Community cast (Hull 2017 Volunteers and wider general public) |
| DELIVERY PARTNERS (IF APPLICABLE) | - BBC – who are key individuals? - The Space - who are key individuals? - Hull 2017 Digital Team (David Watson) - Hull 2017 Volunteering Team (Anna Route) - Hull 2017 Monitoring & Evaluation Team (Elinor Unwin & Pippa Gardner) - Any other key partners? |
| PROJECT SPECIFIC OBJECTIVES/ OUTPUTS TO MEASURE | - Scale up the artistic work of Slung Low to produce a long-running site specific theatrical production for Hull 2017 - Slung Low to develop skills and confidence in online digital engagement, film-making and broadcast - Engage the residents of Victoria Dock, through Slung Low being in-residence throughout the project - Produce a short film (prologue) and tour this around the city - Create two high quality pieces of live outdoor/ site specific performance - Create a live performance for TV - Create intervening online content to build character profiles - Ensure that all four pieces of work connect with one another - Provide captioning and wheelchair access at all live performances – please expand on access provision here - Engage a large community cast in the live/outdoor site specific performances (is there a target number and / or specific communities that you want to reach?) - To challenge attitudes and behaviours on the issue of immigration (do you want this included?) - Slung Low and Hull 2017 to share project learnings and expertise with Ambition for Excellence Consortium - Slung Low to offer a Producer placement to local cultural sector partner (Martin mentioned Mungo worked with them for a time) - Encourage local suppliers and freelancers to engage with tender opportunities for Slung Low – suggestion, but remove if not true |
| HULL 2017 STRATEGIC OBJECTIVES THAT THE PROJECT IS CONTRIBUTING TO | - 365-day cultural programme that is ‘of the city’ yet outward looking, including 60 commissions – do we class this as 1 or 4 commissions? - Increase total audiences for Hull’s art, cultural and heritage offer - Increase engagement and participation in arts and heritage amongst Hull residents - Increase the diversity of audiences for Hull’s arts and heritage offer - Develop the city’s cultural infrastructure through capacity building and collaborative work - Enhance positive media coverage of Hull’s arts and heritage offer - Increase in Hull residents who are proud to live in Hull and would speak positively about it to others - Improve positive attitudes towards Hull as a place to live, study, visit and do business - Increase visitor numbers to Hull - Delivering economic benefits to the city and the city region - Engage volunteers from Hull and beyond - Increase levels of happiness and enjoyment as a result of engaging with arts and culture - Increase levels of confidence and community cohesion among local audiences and participants - Delivery of training and development opportunities to local residents through arts and culture initiatives - Ensure partners are satisfied with their Hull 2017 partnership experience |

PROJECT MONITORING & EVALUATION PLAN – SLUNG LOW: FLOOD

| OBJECTIVES | WHAT YOU WANT TO KNOW: OUTPUTS AND OUTCOMES | STAKEHOLDERS: WHO YOU’LL GATHER INFORMATION FROM | SOURCES OF DATA COLLECTION: WHAT METHODS WILL YOU USE TO COLLECT YOUR EVIDENCE? | TIMING OF DATA COLLECTION: WHEN WILL YOU GATHER INFORMATION? | DATA COLLECTION: PERSON (S) RESPONSIBLE |
| --- | --- | --- | --- | --- | --- |
| Project Specific - Scale up the artistic work of Slung Low to produce a long-running site specific theatrical production for Hull 2017 - Slung Low to develop skills and confidence in online digital engagement, film-making and broadcast - Engage the residents of Victoria Dock, through Slung Low being in-residence throughout the project - Produce a short film (prologue) and tour this around the city - Create two high quality pieces of live outdoor/ site specific performance - Create a live performance for TV - Create intervening online content to build character profiles - Ensure that all four pieces of work connect with one another - Provide captioning and wheelchair access at all live performances – please expand on access provision here if not all included - Engage a large community cast in the live/outdoor site specific performances (is there a target number and / or specific communities that you want to reach?) - To challenge attitudes and behaviours on the issue of immigration (do you want this included?) - Slung Low and Hull 2017 to share project learnings and expertise with Ambition for Excellence Consortium - Slung Low to offer placement(s) to local cultural sector partner (Martin mentioned Mungo worked with them for a time) - Encourage local suppliers and freelancers to engage with tender opportunities for Slung Low – suggestion, but remove if not true Hull 2017 objectives this project will contribute to: - 365-day cultural programme that is ‘of the city’ yet outward looking, including 60 commissions – do we class this as 1 or 4 commissions? - Increase total audiences for Hull’s art, cultural and heritage offer - Increase engagement and participation in arts and heritage amongst Hull residents - Increase the diversity of audiences for Hull’s arts and heritage offer - Develop the city’s cultural infrastructure through capacity building and collaborative work - Enhance positive media coverage of Hull’s arts and heritage offer - Increase in Hull residents who are proud to live in Hull and would speak positively about it to others - Improve positive attitudes towards Hull as a place to live, study, visit and do business - Increase visitor numbers to Hull - Delivering economic benefits to the city and the city region - Engage volunteers from Hull and beyond - Increase levels of happiness and enjoyment as a result of engaging with arts and culture - Increase levels of confidence and community cohesion among local audiences and participants - Delivery of training and development opportunities to local residents through arts and culture initiatives - Ensure partners are satisfied with their Hull 2017 partnership experience | - Length of project (compared with previous projects delivered by Slung Low) | - Creative Core Team - Slung Low | - Project Delivery Plan - Creative Core Team Depth Interviews | - Ongoing - TBC | - TBC - External consultant |
|  | - Project budget (compared with previous projects delivered by Slung Low) | - Creative Core Team - Slung Low | - Project Budget - Creative Core Team Depth Interviews | - Ongoing - TBC | - TBC - Lindsey Alvis - External consultant |
|  | - Record of activities delivered by Slung Low (identifying which activities are first-time activities for the company) | - Creative Core Team | - Project Monitoring Workbook - Depth interviews | - Ongoing - TBC | - Pippa Gardner - Lindsey Alvis - Slung Low - External consultant |
|  | - New skills and knowledge acquired by Slung Low staff throughout the project | - Slung Low staff | - Creative Core Team Survey - Creative Core Team Depth Interviews | - End of project | - External consultant |
|  | - Existing skills and knowledge further developed by Slung Low staff throughout the project | - Slung Low staff | - Creative Core Team Survey - Creative Core Team Depth Interviews | - End of project | - External consultant |
|  | - Confidence level of Slung Low staff in delivering projects of a similar nature in future, with a particular focus on delivery of: - Long-running projects - Multi-part projects - Multi-platform projects | - Slung Low staff | - Creative Core Team Survey - Creative Core Team Depth Interviews | - End of project | - External consultant |
|  | - Intention of Slung Low staff to deliver projects of a similar nature in future | - Slung Low staff | - Creative Core Team Survey - Creative Core Team Depth Interviews | - End of project | - External consultant |
|  | - New skills and knowledge acquired by other Creative Core Team members throughout the project | - Creative Core Team | - Creative Core Team Survey - Creative Core Team Depth Interviews | - End of project | - External consultant |
|  | - Existing skills and knowledge further developed by other Creative Core Team members throughout the project | - Creative Core Team | - Creative Core Team Survey - Creative Core Team Depth Interviews | - End of project | - External consultant |
|  | - Confidence level of other Creative Core Team members in delivering projects of a similar nature in future | - Creative Core Team | - Creative Core Team Survey - Creative Core Team Depth Interviews | - End of project | - External consultant |
|  | - Number of Victoria Dock residents engaged as participants in the project | - TBC | - Participant Survey – Part 2 - Participant Survey – Part 4 | - End of Part 2 - End of Part 4 | - Hull 2017 - Fieldwork Agency |
|  | - Number of Victoria Dock residents interacting with Slung Low throughout the course of the project | - Slung Low | - TBC - Audience Counts at Residents Association meetings attended (using clicker counter) | - Ongoing (dates TBC) | - Slung Low |
|  | - Number of Victoria Dock residents who come to see rehearsals of Flood: Abundance (Part 2) and Flood: New World (Part 4) | - TBC | - TBC | - 10 April - Other dates TBC | - TBC |
|  | - Attitudes and behaviours of Victoria Dock residents towards Slung Low and project, during and after the project | - Victoria Dock Residents | - Community Consultation (exact methodology TBC) | - Ongoing (dates TBC) - End of Project | - External consultant |
|  | - Impact on Victoria Dock residents of having Slung Low in-residence at Victoria Dock | - Victoria Dock Residents | - Community Consultation (exact methodology TBC) | - Ongoing (dates TBC) - End of Project | - External consultant |
|  | - Script and storyboards for Flood: From the Sea (Part 1) | - TBC | - N/A | - End of Part 1 | - TBC |
|  | - Final Edit of Flood: From the Sea (Part 1) – Digital File | - TBC | - N/A | - End of Part 1 | - TBC |
|  | - Number and location of tour stops for Flood: From the Sea (Part 1) | - Slung Low | - Airstream Caravan Tour Schedule | - End of Part 1 | - Slung Low |
|  | - Script of Flood: Abundance (Part 2) | - TBC | - N/A | - End of Part 2 | - TBC |
|  | - Number of workshops and / or rehearsals of Flood: Abundance (Part 2) | - Slung Low | - Production Schedule - Project Monitoring Workbook | - End of Part 2 | - Pippa Gardner - Lindsey Alvis - Slung Lo |
|  | - Number of performances of Flood: Abundance (Part 2) | - Slung Low | - Production Schedule - Project Monitoring Workbook | - End of Part 2 | - Pippa Gardner - Lindsey Alvis - Slung Low |
|  | - Number of workshops and / or rehearsals of Flood: To The Sea (Part 3) | - Slung Low | - Production Schedule - Project Monitoring Workbook | - End of Part 3 | - Pippa Gardner - Lindsey Alvis - Slung Low |
|  | - Number of screenings of Flood: To The Sea (Part 3) | - BBC | - Project Monitoring Workbook | - End of Part 3 | - Pippa Gardner - Lindsey Alvis - BBC |
|  | - Number of workshops and / or rehearsals of Flood: New World (Part 4) | - Slung Low | - Production Schedule - Project Monitoring Workbook | - End of Part 4 | - Pippa Gardner - Lindsey Alvis - Slung Low |
|  | - Number of performances of Flood: New World (Part 4) | - Slung Low | - Project Monitoring Workbook | - End of Part 4 | - Pippa Gardner - Lindsey Alvis - Slung Low |
|  | - Number of clips / videos made for intervening online content | - Slung Low - Hull 2017 Digital | - Project Monitoring Workbook | - Ongoing | - Pippa Gardner - David Watson - Slung Low |
|  | - Number profiles made for intervening online content | - Slung Low - Hull 2017 Digital | - Project Monitoring Workbook | - Ongoing | - Pippa Gardner - David Watson - Slung Low |
|  | - Number of editorial pieces made for intervening online content | - Slung Low - Hull 2017 Digital | - Project Monitoring Workbook | - Ongoing | - Pippa Gardner - David Watson - Slung Low |
|  | - Number of access provisions provided for each part of Flood | - Creative Core Team | - Project Monitoring Workbook | - End of Part 1 - End of Part 2 - End of Part 3 - End of Part 3 | - Pippa Gardner - Lindsey Alvis - Slung Low |
|  | - Number of professional cast members for Flood: Abundance (Part 2) | - Slung Low | - Project Monitoring Workbook - Contracts (?) | - End of Part 2 | - Pippa Gardner - Lindsey Alvis - Slung Low |
|  | - Post code data for professional cast members for Flood: Abundance (Part 2) | - Slung Low | - Project Monitoring Workbook - Contracts (?) | - End of Part 2 | - Pippa Gardner - Lindsey Alvis - Slung Low |
|  | - Equal opportunities data on professional cast members for Flood: Abundance (Part 2) | - Slung Low | - Project Monitoring Workbook - Contracts (?) | - End of Part 2 | - Pippa Gardner - Lindsey Alvis - Slung Low |
|  | - Number of professional cast members for Flood: New World (Part 4) | - Slung Low | - Project Monitoring Workbook - Contracts (?) | - End of Part 4 | - Pippa Gardner - Lindsey Alvis - Slung Low |
|  | - Post code data for professional cast members for Flood: New World (Part 4) | - Slung Low | - Project Monitoring Workbook - Contracts (?) | - End of Part 4 | - Pippa Gardner - Lindsey Alvis - Slung Low |
|  | - Equal opportunities data on professional cast members for Flood: New World (Part 4) | - Slung Low | - Project Monitoring Workbook - Contracts (?) | - End of Part 4 | - Pippa Gardner - Slung Low |
|  | - Number of Hull 2017 Volunteer cast members for Flood: Abundance (Part 2) | - Participants | - Better Impacts - Project Monitoring Workbook | - End of Part 2 | - Anna Route - Pippa Gardner |
|  | - Post code data for Hull 2017 Volunteer cast members for Flood: Abundance (Part 2) | - Participants | - Better Impacts - Participant Survey – Part 2 - Project Monitoring Workbook | - End of Part 2 | - Anna Route - Pippa Gardner |
|  | - Equal opportunities data Hull 2017 Volunteer cast members for Flood: Abundance (Part 2) | - Participants | - Better Impacts - Participant Survey – Part 2 - Project Monitoring Workbook | - End of Part 2 | - Anna Route - Pippa Gardner |
|  | - Number of community cast members for Flood: New World (Part 4): broken down by Hull 2017 Volunteers and general public (TBC) | - TBC | - Registration Forms - Project Monitoring Workbook | - Sign up for Part 4 | - Pippa Gardner - Lindsey Alvis - Slung Low |
|  | - Post code data for community cast members for Flood: New World (Part 4) | - Participants | - Registration Forms | - Sign up for Part 4 | - Lindsey Alvis - Slung Low |
|  | - Equal opportunities data on community cast members for Flood: New World (Part 4) | - Participants | - Registration Forms | - Sign up for Part 4 | - Lindsey Alvis - Slung Low |
|  | - Current attitudes towards immigration | - Participants - Audiences | - Participant Survey – Part 2 - Audience Survey - Part 2 | - End of Part 2 | - Elinor Unwin - Fieldwork Agency |
|  | - Post-project attitudes towards immigration | - Participants - Audiences | - Participant Survey – Part 4 - Audience Survey - Part 4 | - End of Part 4 | - Elinor Unwin - Fieldwork Agency |
|  | - Current behaviours towards immigrants | - Participants - Audiences | - Participant Survey – Part 2 - Audience Survey - Part 2 | - End of Part 2 | - Elinor Unwin - Fieldwork Agency |
|  | - Post-project attitudes towards immigrants | - Participants - Audiences | - Participant Survey – Part 4 - Audience Survey - Part 4 | - End of Part 4 | - Elinor Unwin - Fieldwork Agency |
|  | - Number of activities delivered for Ambition for Excellence Consortium linked to Flood | - Core Creative Team | - Project Monitoring Workbook | - Ongoing | - Pippa Gardner - Cian Smyth - Slung Low |
|  | - Number of placements for Hull-based sector professionals or emerging artists on Flood | - Core Creative Team | - Project Monitoring Workbook | - Ongoing | - Pippa Gardner - Cian Smyth - Slung Low |
|  | - Number of local suppliers (including freelancers) involved in the supply chain for Flood | - Core Creative Team | - Project Budget - Project Monitoring Workbook | - Ongoing | - Pippa Gardner - Cian Smyth - Slung Low |
|  | - Arts Council England Quality Metrics rating of Flood | - Core Creative Team - Peer Assessors - Audiences - Participants | - Creative Core Team Survey - Creative Core Team Depth Interviews - Peer Assessor Depth Interviews - Audience Survey – Part 2 - Audience Survey – Part 4 - Audience Qual - Participant Survey – Part 2 - Participant Survey – Part 4 - Participant Qual | - Now - End of Part 2 - End of Part 4 | - External Consultant |
|  | - Equal opportunities data on Core Creative Team | - Core Creative Team | - Equal opportunities form - Project Monitoring Workbook | - Now | - Pippa Gardner - Lindsey Alvis - Slung Low |
|  | - Number of commissions within Flood project | - Core Creative Team | - Project Monitoring Workbook | - Ongoing | - Pippa Gardner - Lindsey Alvis - Slung Low |
|  | - Number of views of Flood: From the Sea (Part 1) – David, do we need to review all social media separately, or is this all captured just via YouTube? | - TBC | - TBC | - Ongoing - End of Project | - David Watson |
|  | - Number of people who watched Flood: From the Sea (Part 1) via Airstream Caravan Tour | - Slung Low | - Project Monitoring Workbook | - End of Part 1 | - Slung Low |
|  | - Ticket sales for Flood: Abundance (Part 2) | - Spektrix | - Box Office Report | - End of Part 2 | - David Watson |
|  | - Viewing figures for Flood: To The Sea (Part 3) | - BBC | - TBC | - End of Part 3 | - BBC (person?) |
|  | - Ticket sales for Flood: New World (Part 4) | - Spektrix | - Box Office Report | - End of Part 4 | - David Watson |
|  | - Location stats for viewings of Flood: From the Sea (Part 1) – David, how detailed does this go, can we get it by city? | - YouTube (?) | - YouTube Analytics | - End of Part 1 - End of Project | - David Watson |
|  | - Audience post code data for those attending Flood: Abundance (Part 2) | - Audiences | - Audience Survey – Part 2 | - End of Part 2 | - Hull 2017 - Fieldwork Agency |
|  | - Location stats on Flood: To The Sea (Part 3) | - TBC | - TBC | - TBC | - BBC (person?) |
|  | - Audience post code data for those attending Flood: New World (Part 4) | - Audiences | - Audience Survey – Part 4 | - End of Part 4 | - Elinor Unwin - Fieldwork Agency |
|  | - Equal opportunities data on audiences for Flood: Abundance (Part 2) | - Audiences | - Audience Survey – Part 2 | - End of Part 2 | - Elinor Unwin - Fieldwork Agency |
|  | - Equal opportunities data on audiences for Flood: New World (Part 4) | - Audiences | - Audience Survey – Part 4 | - End of Part 4 | - Elinor Unwin - Fieldwork Agency |
|  | - New skills and knowledge acquired by professional cast | - Professional cast | - Professional Cast Survey – Part 2 - Professional Cast Survey – Part 4 - Professional Cast - Qual | - End of Part 2 - End of Part 4 | - Elinor Unwin - External consultant |
|  | - Existing skills and knowledge further developed by professional cast | - Participants | - Professional Cast Survey – Part 2 - Professional Cast Survey – Part 4 - Professional Cast - Qual | - End of Part 2 - End of Part 4 | - Elinor Unwin - External consultant |
|  | - Confidence level of participants in taking part in arts projects | - Participants | - Professional Cast Survey – Part 2 - Professional Cast Survey – Part 4 | - End of Part 2 - End of Part 4 | - Elinor Unwin - External consultant |
|  | - New skills and knowledge acquired by professional cast | - Participants | - Participant Survey – Part 2 - Participant Survey – Part 4 - Participant Qual | - End of Part 2 - End of Part 4 | - Elinor Unwin - Fieldwork Agency |
|  | - Existing skills and knowledge further developed by project participants | - Participants | - Participant Survey – Part 2 - Participant Survey – Part 4 - Participant Qual | - End of Part 2 - End of Part 4 | - Elinor Unwin - Fieldwork Agency |
|  | - Confidence level of participants in taking part in arts projects | - Participants | - Participant Survey – Part 2 - Participant Survey – Part 4 - Participant Qual | - End of Part 2 - End of Part 4 | - Elinor Unwin - Fieldwork Agency |
|  | - New skills and knowledge acquired by Ambition for Excellence Consortium | - Ambition for Excellence Consortium | - Post event feedback forms | - Post event | - Elinor Unwin - Cian Smyth |
|  | - Existing skills and knowledge further developed by Ambition for Excellence Consortium | - Ambition for Excellence Consortium | - Post event feedback forms | - Post event | - Elinor Unwin - Cian Smyth |
|  | - New skills and knowledge acquired by placement recipients | - Placement recipients | - Post placement feedback forms | - Post placement | - Elinor Unwin - Cian Smyth |
|  | - Existing skills and knowledge further developed by placement recipients | - Placement recipients | - Post placement feedback forms | - Post placement | - Elinor Unwin - Cian Smyth |
|  | - Confidence level of placement recipients in taking part in arts projects | - Placement recipients | - Post placement feedback forms | - Post placement | - Elinor Unwin - Cian Smyth |
|  | - New skills acquired and knowledge by local organisations and freelancers supplying supply chain services | - Local organisations - Freelancers | - Supplier & Freelancer Survey | - End of project | - Elinor Unwin - Cian Smyth |
|  | - Existing skills and knowledge further developed by local organisations and freelancers supplying supply chain services | - Local organisations - Freelancers | - Supplier & Freelancer Survey | - End of project | - Elinor Unwin - Cian Smyth |
|  | - Confidence level of local organisations and freelancers supplying supply chain services in working on similar projects in future | - Local organisations - Freelancers | - Supplier & Freelancer Survey | - End of project | - Elinor Unwin - Cian Smyth |
|  | - Number of press release, TV and radio appearances | - Hull 2017 Comms | - TBC – Ben and Alix? | - Ongoing | - Ben McKnight |
|  | - Levels and messaging of media coverage across all channels (including social media) | - Gorkana - Falcon - Other (?) | - Media monitoring and analysis - Social Media Analysis | - Ongoing | - PR Agency - Ben McKnight - Chris Marr |
|  | - Number of visitors (non-Hull residents) amongst audiences | - Participants - Audiences | - Participant Survey – Part 2 - Audience Survey - Part 2 - Participant Survey – Part 4 - Audience Survey - Part 4 | - End of Part 2 - End of Part 4 | - Elinor Unwin - Fieldwork Agency |
|  | - Audience spend on accommodation (staying visitors) and all other spend areas (all audiences) | - Participants - Audiences | - Participant Survey – Part 2 - Audience Survey - Part 2 - Participant Survey – Part 4 - Audience Survey - Part 4 | - End of Part 2 - End of Part 4 | - Elinor Unwin - Fieldwork Agency |
|  | - Perceptions of Hull at during the project and reasons for any changes since before project began | - Core Creative Team - Delivery Partners - Audiences - Participants - Residents of Victoria Dock | - Depth interviews - Participant Survey – Part 2 - Audience Survey - Part 2 - Participant Survey – Part 4 - Audience Survey - Part 4 | - End of Part 2 - End of Part 4 | - Elinor Unwin - External consultant - Fieldwork Agency |
|  | - Perceptions of Hull at end of project and reasons for any changes | - Core Creative Team - Delivery Partners - Audiences - Participants - Residents of Victoria Dock | - Depth interviews - Participant Survey – Part 2 - Audience Survey - Part 2 - Participant Survey – Part 4 - Audience Survey - Part 4 | - End of Part 2 - End of Part 4 | - Elinor Unwin - External consultant - Fieldwork Agency |
|  | - Level of enjoyment linked to the project | - Core Creative Team - Delivery Partners - Audiences - Participants - Residents of Victoria Dock | - Depth interviews - Participant Survey – Part 2 - Audience Survey - Part 2 - Participant Survey – Part 4 - Audience Survey - Part 4 - Audience Qual - Participant Qual | - End of Part 2 - End of Part 4 | - Elinor Unwin - External consultant - Fieldwork Agency |
|  | - Perceived level of success against motivations to be involved amongst delivery partners | - Delivery Partners | - Delivery Partner Survey - Delivery Partner Depth interviews | - End of Part 2 - End of project | - External consultant |
|  | - Attitudes towards project management and support provided by Hull 2017 | - Core Creative Team (non-Hull 2017) - Delivery Partners | - Creative Core Team Survey - Creative Core Team Depth Interviews - Delivery Partner Survey - Delivery Partner Depth interviews | - End of Part 2 - End of project | - External consultant |