WOW Hull

November 21st Thinkin

Mercure Hotel Edwardian Suite

6pm – 8pm

Requirements

Room Set Up

- Tables set in a cabaret style arrangement

- A small stage/raised area for Jude, Kate, and our circle of friends Tish, Suzanne, Burnsy TBC.

- Badges, paper and pens/pencils on each table for attendee

- Drinks Area/Refreshments area

- A means to display our trailblazer boards.

- 4 Pop Up Screens to be displayed, in foyer and in the room.

- Copies of Revolutionary Makers Info - to take away

Technical

- 3 wireless Mics for introductions and circle of friends. (costs?)

- Projector

- Projectors Screen and link to PA or speakers

- I-pads for signing into WOW and email addresses.

Digital

- Power Point of the evening, including trailblazers, dates, website etc.

- Means to display the WOW Hull Manifesto of the evening

6 volunteers

4.30 – 8.30pm

Schedule for the Evening

16:00		Room setup and technical checks,

16:30		2017 Volunteers arrive

17:30	 	Doors open, sign in with Ipads, refreshments served.

EVENT START

18:00             	EVENT START

Henri’s introduction – to the evening and housekeeping.

18:05		Henri introduces Kate Fox – Poem and her poetry challenge for the evening.

18:10		Rosie Millard introduces Jude Kelly, founder of WOW.

Jude Kelly speaks about WOW, the origins of the festival and how the

movement has grown.
 	WOW Film - new film to be shown (7m21s)

18:20		Either Jude leads introduction session of all attendees

Make a call on the day depending on numbers

3 Roving mics available.

OR

Extend time Jude Introduction (+5mins)  and  for Panel (+10mins)

18:35		WOW Hull Panel
		Jude leads conversation with guests

Expectations for WOW Hull, why it’s important to do

Suzanne Clisby (The State of Girls Rights in the UK)

Tish Lamb (the Women’s Equality Party)

Burnsy (Equality in local media and awareness)
	Ruth & Sarah (St Mary’s College Students)

Melanie Eusebe (Intersectionality & Diversity)

Bea Campbell

18:55		Jude and Henri introduce idea of creating a WOWifesto in Hull and the plans   		for a future Global WOW Manifesto.

For example

What would we like to change? (one of these examples)

- Hull Branch of the Women's Equality Party

- I would like to see the women’s football matches and rugby matches to be screened in local pubs on Saturdays alongside the men’s matches.

- We tackle low level sexism in workplaces.

Pledges

- We will launch the Hull branch at the WOW Hull festival in March.

- Finding media companies to film matches and talk to pubs about finding ways of screening women’s matches (following model BBC Olympics coverage)

- We’ll create misogyny swear boxes all proceeds going to domestic violence charities.

19:00		Thinkin Session led by Jude Kelly & Maddie O’Reilly

Includes asking attendees to think about actions for the WOWifesto in Hull and what they would like to see at the festival.

19:30               	Feedback around the room from the tables. 
 		To manage the room, and ensure everyone is involved, we ask people their 		top 3  ideas and 1 pledge for the WOWifesto.

19:45		Henri and Ian introduce the call out for the Revolutionary Maker’s crafts

project.

19:50 		Kate Fox performs another freshly written poem inspired by the evening.

19:55               	Thank you – to attendees, Jude, Kate and circle of friends

Rosie Millard to do the summary.

Next Key Dates - Tickets on Sale in January - Festival Dates March

Revolutionary Craft project sign up.

Keep sharing #wowhull

You can always contact us on wow@hull2017.co.uk

20:00 		EVENT END