## Summary
| 15-21 May | 22-28 May | 29 May - 4 June | 5 - 11 June | 12-18 June | 19-25 June | 26 June - 2 July | 3-9 July | 10-16 July | 17-23 July | 24-30 July | 31 July - 6 Aug | 7-13 Aug | 14-20 Aug | 21-27 Aug | 28 Aug - 3 Sept | 4-10 Sept | 11-17 Sept | 18-24 Sept | 25 Sept - 1 Oct | 2-8 Oct | 9-15 Oct | 16-22 Oct | 23-29 Oct | 30 Oct - 5 Nov | 6-12 Nov | 13-19 Nov | 20-26 Nov | 27 Nov - 3 Dec | 4-10 Dec | 11-17 Dec | 18-24 Dec | 25-31 Dec | 1-7 Jan 2018 | 8-14 Jan 2018 | 15-21 Jan 2018
All |  |  |  |  | 16 DEADLINE FOR LEARNING COPY |  |  | Visual Identity slides ready to share with Tate early July | Visual Identity slides ready to share with Tate early July | [5 empty] | Pre-fabrication off site | Pre-fabrication off site | Pre-fabrication off site | Build on site, Install works | Build on site, Install works | 25 Press preview | Stakeholder and Learning events | Stakeholder and Learning events | Stakeholder and Learning events | Stakeholder and Learning events | Stakeholder and Learning events | Stakeholder and Learning events | Stakeholder and Learning events | Stakeholder and Learning events | Stakeholder and Learning events | 5 AM Press preview | Stakeholder and Learning events | FOR INFO: Ferens Closed 23/12 4pm - 10am 29th | FOR INFO: Ferens Closed until 10am 29th. Closes 31/1 4pm | FOR INFO: Ferens Closed 1/1 | Deinstall | Deinstall | 23 Artwork Shipped
[16 empty] | 29 Collection/Delivery TBC |  |  |  | 25 Opening event |  | 10 Guestlist for Awards Ceremony signed off | [5 empty] | FOR INFO: Junior Open begins 25/11 |  | PM Technical TV rehearsal |  |  |  | 7 Exhibition closes
[20 empty] | 26 Exhibition open | [9 empty] | PM Awards Ceremony
FOR INFO: 1418 Now Conference
Programme |  | Lead images selected and copyright cleared. Tate/artists sign off | 31-1 Artists visit | Initial proposals submitted to H17 by artists | 15 Hurvin Studio visit and Artists films (Andrea) |  | Awards presenter confirmed and contract signed | Outline volunteer request (12 weeks notice) | 14 Artists' guestlists for Opening Ceremony received by H17 | 21 Internal catalogue copychecking complete | Final Volunteer request deadline (8 weeks notice) | 4 Guest list for opening event signed off by parties | Curator media training (if required) | Volunteer shift offer deadline (6 weeks notice) |  | 29 Collection/Delivery |  |  | 18 Catalogue lands | [10 empty] | 5 10am Jury meeting @ Ferens to decide winner
[5 empty] | 16 FOR INFO: Andrea filming at Liberty |  |  | 4 Final exhibition content agreed with H17 | 14 Tate guestlist for Opening Ceremony received by H17 | 21 All catalogue copy, images and credits sent to marketing | 24 Raw catalogue copy send to artists and Tate for approval |  | 8 Catalogue proofing by partners, curators and artists begins - final amends | 14/15 Assess build quotes
|  |  | First draft of Education programme schedule |  |  |  |  | Proposed exhibition layout submitted | 14 Catalogue first draft deadline |  | 24/25 Meet DK to sign off exhibition build |  | 11 Receive quotes for build install | 16 Appoint contractor to build
28 Issue DK drawing pack to contractors
Learning |  |  | First draft of Education schedule |  | 16 DEADLINE FOR LEARNING COPY 50/100 words on each project | Education schedule finalised/released | 26 Deadline for first Learning comms design TBC |  | 10 First Learning comms LANDS and distributed TBC |  |  |  |  | 14 All event detail confirmed and contracts signed |  |  |  |  | 22 School cut off to book A Day in the Life
17 Freelance contracts drafted
MarComms |  |  | 31 Artist photographs |  | 15 Artists films in London (Andrea) |  | 26 Deadline for first Learning comms design TBC | 3 First Learning comms to print TBC | Deadline for copy of Tate Members guide (Sept release) | 21 Internal catalogue copychecking complete | 24 Raw catalogue copy send to artists and Tate for approval | 2 Catalogue copy and images in to design phase | Curator media training (if required) | Deadline for Tate Members E-Bullitin (Sept release) |  | 29 Catalogue to print |  |  | 20 Opening press release written, approved by parties | [9 empty] | 1 Awards press release written, approved by all parties
|  |  | 31 Bolton & Quinn meeting |  |  |  | 30 Catalogue pagination agreed and circulated. Confirm word count and print spec, raise order | Visual Identity slides ready to share with Tate early July | 10 First Learning comms LANDS and distributed TBC | 21 All catalogue copy, images and credits sent to marketing |  |  | 7 Internal catalogue proof (marketing) | [5 empty] | 20 Internal briefing pack completed/ circulated to staff attending the Press Preview event | [9 empty] | 1 Internal briefing pack completed/ circulated to staff attending awards
[9 empty] | 14 Catalogue first draft deadline |  |  |  | 8 Catalogue proofing by partners, curators and artists begins - final amends | [5 empty] | 18 Catalogue lands
Events | [8 empty] | 14 Artists' guestlists for Opening Ceremony received by H17 |  |  | 4 Guest list for opening event signed off by parties | 11 Opening event invites sent out | [7 empty] | 6 Artists' guestlist for Awards Ceremony received by H17 | 10 Guestlist for Awards Ceremony signed off | 20 Awards Ceremony invites sent out
[9 empty] | 14 Tate guestlist for Opening Ceremony received by H17 | [11 empty] | 6 Tate guestlist for Awards Ceremony received by H17

## Catalogue
TURNER PRIZE CATALOGUE SCHEDULE
MAY
|  | m | t | w | t | f | s | s
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7
AM
PM
|  | 8 | 9 | 10 | 11 | 12 | 13 | 14
AM
PM
|  | 15 | 16 | 17 | 18 | 19 | 20 | 21
AM
PM
|  | 22 | 23 | 24 | 25 | 26 | 27 | 28
AM
PM
|  | 29 | 30 | 31
AM
PM
JUNE
|  | m | t | w | t | f | s | s
[5 empty] | 1 | 2 | 3 | 4
AM
PM
|  | 5 | 6 | 7 | 8 | 9 | 10 | 11
AM
PM
|  | 12 | 13 | 14 | 15 | 16 | 17 | 18
AM
PM
|  | 19 | 20 | 21 | 22 | 23 | 24 | 25
AM
PM
|  | 26 | 27 | 28 | 29 | 30
| AM | 23: Pagination agreed and approved by wider team
| PM | 23: Word count and print spec confirmed and order raised
JULY
|  | m | t | w | t | f | s | s
[7 empty] | 1 | 2
AM
PM
Visual Identity slides ready to share with Tate early July |  | 3 | 4 | 5 | 6 | 7 | 8 | 9
AM
PM
|  | 10 | 11 | 12 | 13 | 14 | 15 | 16
| AM | 14: Catalogue copy submitted by curators
PM
|  | 17 | 18 | 19 | 20 | 21 | 22 | 23
| AM | Copychecking/ copyediting | Copychecking/ copyediting | Copychecking/ copyediting | Copychecking/ copyediting | Final content (copy, imagery and credits) sent to marketing
PM
|  | 24 | 25 | 26 | 27 | 28 | 29 | 30
| AM | 24: Raw copy sent to artists and Tate for approval
PM
31
AM
PM
AUGUST
|  | m | t | w | t | f | s | s
|  |  | 1 | 2 | 3 | 4 | 5 | 6
| AM |  | Artists and Tate comments back | Copy and image design phase | Copy and image design phase | Copy and image design phase | Copy and image design phase | Copy and image design phase
PM
|  | 7 | 8 | 9 | 10 | 11 | 12 | 13
| AM | Marketing internal proof | Proofing from curators and artists FINAL CHANCE FOR AMENDS | Proofing from curators and artists FINAL CHANCE FOR AMENDS | Proofing from curators and artists FINAL CHANCE FOR AMENDS | Proofing from curators and artists FINAL CHANCE FOR AMENDS | Proofing from curators and artists FINAL CHANCE FOR AMENDS | Proofing from curators and artists FINAL CHANCE FOR AMENDS
| PM |  | Proofing from creative partners (HCAL, Tate, BBC) | Proofing from creative partners (HCAL, Tate, BBC) | Proofing from creative partners (HCAL, Tate, BBC) | Proofing from creative partners (HCAL, Tate, BBC) | Proofing from creative partners (HCAL, Tate, BBC) | Proofing from creative partners (HCAL, Tate, BBC)
|  | 14 | 15 | 16 | 17 | 18 | 19 | 20
| AM | Proofing from curators and artists FINAL CHANCE FOR AMENDS | Proofing from curators and artists FINAL CHANCE FOR AMENDS | Proofing from curators and artists FINAL CHANCE FOR AMENDS | Proofing from curators and artists FINAL CHANCE FOR AMENDS | Proofing from curators and artists FINAL CHANCE FOR AMENDS
| PM | Proofing from creative partners (HCAL, Tate, BBC) | Proofing from creative partners (HCAL, Tate, BBC) | Proofing from creative partners (HCAL, Tate, BBC) | Proofing from creative partners (HCAL, Tate, BBC) | Proofing from creative partners (HCAL, Tate, BBC)
|  | 21 | 22 | 23 | 24 | 25 | 26 | 27
AM
PM
|  | 28 | 29 | 30 | 31
| AM | 22: Go to print
PM
SEPTEMBER
|  | m | t | w | t | f | s | s
[6 empty] | 1 | 2 | 3
AM
PM
|  | 4 | 5 | 6 | 7 | 8 | 9 | 10
AM
PM
|  | 11 | 12 | 13 | 14 | 15 | 16 | 17
AM
PM
|  | 18 | 19 | 20 | 21 | 22 | 23 | 24
| AM | 18: Delivery of catalogues; 20: Opening press release approved by parties
PM
|  | 25 | 26 | 27 | 28 | 29 | 30
| AM | 25: Press preview; 26: Exhibition opens
| PM | 25: Opening event

## Build
TURNER PRIZE INSTALL/DEINSTALL PROGRAMME
JULY
| m | t | w | t | f | s | s
[6 empty] | 1 | 2
AM
PM
| 3 | 4 | 5 | 6 | 7 | 8 | 9
AM |  |  | David Kohn site visit | Loan forms issued
PM |  |  | Final works confirmed
| 10 | 11 | 12 | 13 | 14 | 15 | 16
AM | Transport arranged | Transport arranged | Transport arranged | Transport arranged | Transport arranged | Transport arranged | Transport arranged
PM | Design exhibition build | Design exhibition build | Design exhibition build | Design exhibition build | Design exhibition build | Design exhibition build | Design exhibition build
| 17 | 18 | 19 | 20 | 21 | 22 | 23
AM | Transport arranged | Transport arranged | Transport arranged | Transport arranged | Transport arranged
PM | Design exhibition build | Design exhibition build | Design exhibition build | Design exhibition build | Design exhibition build
| 24 | 25 SCHOOLS BREAK UP | 26 | 27 | 28 | 29 | 30
AM | Meet DK to sign off exhibition build | Meet DK to sign off exhibition build |  |  | Issue drawing pack to contractors
PM
31
AM
PM
AUGUST
| m | t | w | t | f | s | s
|  | 1 | 2 | 3 | 4 | 5 | 6
AM
PM
| 7 | 8 | 9 | 10 | 11 | 12 | 13
AM |  | 4: Receive quotes for build install
PM
| 14 | 15 | 16 | 17 | 18 | 19 | 20
AM | Assess build quotes | 1: Assess build quotes; 2: Appoint contractor to build
PM
| 21 | 22 | 23 | 24 | 25 | 26 | 27
AM | Pre-Fabrication off site | Pre-Fabrication off site | Pre-Fabrication off site | Pre-Fabrication off site | Pre-Fabrication off site | Pre-Fabrication off site | Pre-Fabrication off site
PM
| 28 | 1: 29 Ferens Closed BMS; 2: 30 Ferens Closed BMS; 3: 31 Ferens Closed BMS | Ferens Closed BMS
AM | Pre-Fabrication off site | 1: Pre-Fabrication off site; 2: Pre-Fabrication off site; 3: Pre-Fabrication off site
PM |  | 1: Collection/Delivery TBC
SEPTEMBER
| m | t | w | t | f | s | s
|  | 4: 1 Ferens Closed BMS; 5: 2 Ferens Closed BMS; 6: 3 Ferens Closed BMS | Ferens Closed BMS
AM |  | 4: Pre-Fabrication off site; 5: Pre-Fabrication off site; 6: Pre-Fabrication off site
PM
| 4 Ferens Closed BMS | 5 Ferens Closed BMS | 6 Ferens Closed BMS | 7 Ferens Closed BMS | 8 Ferens Closed BMS | 9 | 10 | Ferens Closed BMS
AM | Pre-Fabrication off site | Pre-Fabrication off site | Pre-Fabrication off site | Pre-Fabrication off site | Pre-Fabrication off site
PM
| 11 | 12 | 13 | 14 | 15 | 16 | 17
AM | Build on site | Build on site | Build on site | Build on site | Build on site | Build on site | Build on site
PM | Install works | Install works | Install works | Install works | Install works | Install works | Install works
| 18 | 19 | 20 | 21 | 22 | 23 | 24
AM | Build on site | Build on site | Build on site | Build on site | Photography | Advance press & BBC
PM | Install works | Install works | Install works | Install works |  | Training of Volunteer and Gallery Assistants
| 25 | 26 | 27 | 28 | 29 | 30
AM | Press preview | 1: Exhibition opens
PM | Opening event
OCTOBER
| m | t | w | t | f | s | s
1
AM
PM
| 2 | 3 | 4 | 5 | 6 | 7 | 8
AM
PM
| 9 | 10 | 11 | 12 | 13 | 14 | 15
AM
PM
| 16 | 17 | 18 | 19 | 20 | 21 | 22
AM
PM
| 23 | 24 | 25 | 26 | 27 | 28 | 29
AM
PM
| 30 | 1: 31
AM
PM
NOVEMBER
| m | t | w | t | f | s | s
|  |  | 1 | 2 | 3 | 4 | 5
AM
PM
| 6 | 7 | 8 | 9 | 10 | 11 | 12
AM
PM
| 13 | 14 | 15 | 16 | 17 | 18 | 19
AM
PM
| 20 | 21 | 22 | 23 | 24 | 25 | 26
AM
PM
| 27 | 28 | 29 | 30 | 31
AM
PM
DECEMBER
| m | t | w | t | f | s | s
[5 empty] | 1 | 2 | 3
AM
PM
| 4 | 5 | 6 | 7 | 8 | 9 | 10
AM
PM |  | 1: Awards Ceremony
| 11 | 12 | 13 | 14 | 15 | 16 | 17
AM
PM
| 18 | 19 | 20 | 21 | 22 | 23 Closes at 4pm | 24 Closed
AM
PM
| 25 Closed | 26 Closed | 27 Closed | 28 Closed | 29 | 30 | 31 Closes at 4pm
AM
PM
JANUARY
| m | t | w | t | f | s | s
| 1 Closed | 2 | 3 | 4 | 5 | 6 | 7
AM |  | 6: Exhibition Ends; 7: Deinstall begins
PM
| 8 | 9 | 10 | 11 | 12 | 13 | 14
AM | Deinstall | Deinstall | Deinstall | Deinstall | Deinstall | Deinstall | Deinstall
PM
| 15 | 16 | 17 | 18 | 19 | 20 | 21
AM | Deinstall | Deinstall | Deinstall | Deinstall | Deinstall ends
PM
| 22 | 23 | 24 | 25 | 26 | 27 | 28
AM |  | 2: Artwork returned
PM
| 29 | 2: 30; 3: 31
AM
PM

## Learning Programme
| TURNER PRIZE LEARNING PROGRAMME | [8 empty] | BOOKING LEADS
| JUNE | [8 empty] | Event | Ticketed? | Paid/Free | Lead
|  | m | t | w | t | f | s | s |  | Turner Intense | Yes | Free | Ian
[5 empty] | 1 | 2 | 3 | 4 |  | Masterclasses | Yes | Paid | Heritage Learning
| AM | [8 empty] | Turner//Return | Yes | Free | Hull 2017
| PM | [8 empty] | Supper Club | Yes | Paid | Hull 2017 | Invite only? Is this public?
|  | 5 | 6 | 7 | 8 | 9 | 10 | 11 |  | Language Tours | Yes | Free | Hull 2017
| AM | [8 empty] | Journeys in Art | TBC | Paid | Heritage Learning
PM
|  | 12 | 13 | 14 | 15 | 16 | 17 | 18
| AM | [8 empty] | TARGET AUDIENCES (Subsidised Stakeholder Slots)
PM
|  | 19 | 20 | 21 | 22 | 23 | 24 | 25 |  | The Warren
| AM | 20: Hack & Host T//R outline |  | Young families (especially from children’s centres on North Bransholme / Orchard Park / Greatfield / Hessle Road)
| PM | [8 empty] | Groups associated with the Older People’s Partnership
|  | 26 | 27 | 28 | 29 | 30 |  |  |  | CASE
| AM | [8 empty] | The Disabilities Trust
| PM | [8 empty] | Mencap Hull / Talent Match Humber
5 senses
| JULY | [8 empty] | Open Doors
|  | m | t | w | t | f | s | s |  | Hull Homeless Commuinity Project
[7 empty] | 1 | 2
AM
PM
|  | 3 | 4 | 5 | 6 | 7 | 8 | 9
AM
PM
|  | 10 | 11 | 12 | 13 | 14 | 15 | 16
| AM | 10: Teacher e-flyer distributed; 11: Hack & Host Proposal Deadline; 14: Film ideas deadline
| PM | 10: Teacher flyer to print
|  | 17 | 18 | 19 | 20 | 21 | 22 | 23
AM
PM
|  | 24 | 25 SCHOOLS BREAK UP | 26 | 27 | 28 | 29 | 30
| AM | Teacher flyer to print 21: Confirm T/R artists/speakers etc.
PM
31
| AM | Teacher flyer to print 17: All freelance contracts drafted
PM
AUGUST
|  | m | t | w | t Open till 19:30 | f | s | s
T/R Community Engagement begins - end Sept |  |  | 1 | 2 | 3 | 4 | 5 | 6
AM
PM
|  | 7 | 8 | 9 | 10 | 11 | 12 | 13
| AM | 7: Freelance contracts sent out; 11: All freelance contracts signed
PM
|  | 14 | 15 | 16 | 17 | 18 | 19 | 20
AM
PM
|  | 21 | 22 | 23 | 24 | 25 | 26 | 27
| AM | 21: All event detail confirmed
PM
|  | 28 Bank Hol | 29 | 30 | 31
| AM | 22: Website programme launch TBC; 23: The Warren @ Ferens
PM
SEPTEMBER
|  | m | t | w | t Open till 19:30 | f | s | s
[6 empty] | 1 Lets Talk About Freedom | 2 Lets Talk About Freedom | 3 Lets Talk About Freedom
AM
PM
|  | 4 | 5 | 6 | 7 | 8 Heritage Open Day | 9 Heritage Open Day | 10 Heritage Open Day
| AM | 21: Additional e-flyers for specific events TBC
PM
|  | 11 | 12 | 13 | 14 | 15 Exchange booking deadline | 16 | 17
AM
PM
|  | 18 | 19 | 20 | 21 | 22 School cut off to book A Day in the Life | 23 | 24
| AM | STUDIO BOOKED FOR STAFF TRAINING | STUDIO BOOKED FOR STAFF TRAINING | STUDIO BOOKED FOR STAFF TRAINING | STUDIO BOOKED FOR STAFF TRAINING | STUDIO BOOKED FOR STAFF TRAINING | STUDIO BOOKED FOR STAFF TRAINING | STUDIO BOOKED FOR STAFF TRAINING
| PM | STUDIO BOOKED FOR STAFF TRAINING | STUDIO BOOKED FOR STAFF TRAINING | STUDIO BOOKED FOR STAFF TRAINING | STUDIO BOOKED FOR STAFF TRAINING | STUDIO BOOKED FOR STAFF TRAINING | STUDIO BOOKED FOR STAFF TRAINING | STUDIO BOOKED FOR STAFF TRAINING
|  | 25 | 26 | 27 | 28 Humber Mouth Fest New Contemp BALTIC | 29 Humber Mouth Fest | 30 Humber Mouth Fest
| AM | 21: Press preview; 22: Exhibition opens; 23: British Council Discussion w/curators
| PM | 21: Opening event
OCTOBER
|  | m | t | w | t Open till 19:30 | f | s | s
1 Humber Mouth Fest
AM
PM
|  | 2 | 3 | 4 | 5 | 6 | 7 Humber Mouth Ends, Albemarle Saturdays | 8
| AM | 22: 08:00 - 10:00 Stakeholder; 26: Workshop - Film Heritage Learning
| PM | 22: Art Curator Tour 12:30pm; 23: 18:00 - 21:00 Stakeholder; 25: AD Tour 1.30PM; 26: Workshop - Film Heritage Learning
|  | 9 | 10 | 11 | 12 | 13 | 14 | 15
| AM | 10: 08:00 - 10:00 Stakeholder; 13: BSL Tour 11AM
| PM | 11: 18:00 - 21:00 Stakeholder; 12: Curator Tour 6pm
|  | 16 | 17 | 18 | 19 | 20 | 21 | 22
| AM | 17: 08:00 - 10:00 Stakeholder
| PM | 17: Art Curator Tour 12:30pm; 18:00 - 21:00 Stakeholder 18: 18:00 - 21:00 Stakeholder; Curator Tour 6pm 21: Engage (Teacher CPD)
|  | 23 A Day in the Life HL | 24 A Day in the Life HL | 25 A Day in the Life HL | 26 A Day in the Life HL | 27 A Day in the Life HL | 28 Big Draw Family Takeover HSG | 29 Big Draw
| AM | 17: 08:00 - 10:00 Stakeholder; Curator Tour 6pm 21: Workshop: Drawing (Heritage Learning)
| PM | 18:00 - 21:00 Stakeholder 18: 18:00 - 21:00 Stakeholder; Curator Tour 6pm 19: Curator Tour 6pm; Curator Tour 6pm 21: Workshop: Drawing (Heritage Learning)
HALF TERM |  | 16: 30 Big Draw; 17: 31 Big Draw
AM
PM
NOVEMBER
|  | m | t | w | t Open till 19:30 | f | s | s
HALF TERM |  |  |  | 1 Big Draw | 2 Big Draw | 3 Big Draw | 4 Big Draw Family Day | 5 Big Draw
AM
| PM | Curator Tour 6pm 21: Engage (Teacher CPD) NOT IN STUDIO; Curator Tour 6pm 22: AD Tour 1:30pm
|  | 6 A Day in the Life HL | 7 A Day in the Life HL | 8 A Day in the Life HL | 9 A Day in the Life HL | 10 A Day in the Life HL | 11 | 12
| AM | 17: 08:00 - 10:00 Stakeholder
| PM | 17: 18:00 - 21:00 This Way Up PV; 18:00 - 21:00 Stakeholder 18: 18:00 - 21:00 Stakeholder; Curator Tour 6pm 19: Curator tour 6pm; Curator Tour 6pm 21: Engage (Teacher CPD)
|  | 13 | 14 | 15 | 16 | 17 | 18 Hull Noir Writing, Ballad (Play), Archives Awareness | 19
| AM | 17: 08:00 - 10:00 Stakeholder; Curator Tour 6pm 20: Art Curator Tour 12:30pm; Curator Tour 6pm 21: Workshop - Curating (Hull 2017)
| PM | 18:00 - 21:00 Stakeholder 18: 18:00 - 21:00 Stakeholder; Curator Tour 6pm 19: TURNER//RETURN till 11; Curator Tour 6pm 21: Workshop - Curating (Hull 2017)
Junior Open |  | 20 | 21 | 22 | 23 | 24 | 25 Junior Open PV and Awards | 26 | George Away
| AM | 16: AD Tour w/ HIRIB 12:30; 17: 08:00 - 10:00 Stakeholder; Curator Tour 6pm 22: BSL Tour 11AM
| PM | 18:00 - 21:00 Stakeholder 18: 18:00 - 21:00 Stakeholder
Junior Open |  | 16: 27 Engage Fringe Events; 17: 28 Engage Conference; 18:00 - 21:00 Stakeholder 18: 29 Engage Conference; Curator Tour 6pm 19: 30 Engage Conference
| AM | 17: 08:00 - 10:00 Stakeholder
| PM | 17: Art Curator Tour 12:30pm; 18:00 - 21:00 Stakeholder 18: 18:00 - 21:00 Engage TBC
DECEMBER
|  | m | t | w | t Open till 19:30 | f | s | s
Junior Open |  | Curator Tour 6pm 20: 1; Curator Tour 6pm 21: 2 RADIO 6 BREAKFAST; Curator Tour 6pm 22: 3 RADIO 6 BREAKFAST
| AM | Curator Tour 6pm 22: Curator tour 10am
| PM | Curator Tour 6pm 21: Engage (Teacher CPD)
Junior Open |  | 4 | 5 | 6 | 7 | 8 | 9 Blast Theory | 10
| AM | Curator Tour 6pm 21: Workshop - Writing (Hull 2017)
| PM | 17: Awards Ceremony; Curator Tour 6pm 21: Workshop - Writing (Hull 2017)
Junior Open |  | 11 | 12 | 13 | 14 | 15 | 16 | 17
AM
PM
Junior Open |  | 18 | 19 | 20 | 21 | 22 | 23 Closes at 4pm | 24 Closed
AM
PM
Junior Open |  | 25 Closed | 26 Closed | 27 Closed | 28 Closed | 29 | 30 | 31 Closes at 4pm
AM
PM
JANUARY
|  | m | t | w | t Open till 19:30 | f | s | s
Junior Open |  | 1 Closed | 2 | 3 | 4 | 5 | 6 | 7
| AM |  | 6: Exhibition Ends; 7: Deinstall begins
PM
Junior Open |  | 8 | 9 | 10 | 11 | 12 | 13 | 14
AM
PM
Junior Open |  | 15 | 16 | 17 | 18 | 19 | 20 | 21 Junior Open finishes
| AM | 19: Deinstall ends
PM
|  | 22 | 23 | 24 | 25 | 26 | 27 | 28
AM
PM
|  | 29 | 30 | 31
AM
PM

## Stakeholder Events
TURNER PRIZE STAKEHOLDER EVENTS
TARGET AUDIENCES (Subsidised Stakeholder Slots)
| SEPTEMBER | [7 empty] | The Warren
|  | m | t | w | t | f | s | s | Young families (especially from children’s centres on North Bransholme / Orchard Park / Greatfield / Hessle Road)
|  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | Groups associated with the Older People’s Partnership
| AM | 21: Install finishes; 22: Exhibition photographed; 23: Press photographs; 24: Press photographs | CASE
| PM | [7 empty] | The Disabilities Trust
NO BOOKINGS - Opening week |  | 25 | 26 | 27 | 28 | 29 | 30 |  | Mencap Hull / Talent Match Humber
| AM | 25: Press preview; 26: Exhibition opens |  | 5 senses
| PM | 25: Opening event |  | Open Doors
Hull Homeless Commuinity Project
OCTOBER
|  | m | t | w | t | f | s | s | Requests
1
| AM | [7 empty] | Name | Date | Timeslot
| PM | [7 empty] | Kcom | TBC | TBC
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8
AM
| PM | 3: 18:00 - 20:30 Partnerships w/Curator talk
|  | 9 | 10 | 11 | 12 | 13 | 14 | 15
AM
PM
|  | 16 | 17 | 18 | 19 | 20 | 21 | 22
AM
| PM | 19: 18:00 - 20:30 Ernest & Young w/Curator talk (TBC)
|  | 23 | 24 | 25 | 26 | 27 | 28 | 29
AM
PM
HALF TERM |  | 23: 30; 24: 31
AM
PM
NOVEMBER
|  | m | t | w | t | f | s | s
HALF TERM |  |  |  | 1 | 2 | 3 | 4 | 5
AM
PM
|  | 6 | 7 This Way Up Conference | 8 This Way Up Conference | 9 | 10 | 11 | 12
AM
| PM | 24: 18:00 - 20:30 This Way Up PV
|  | 13 | 14 | 15 | 16 | 17 | 18 | 19
AM
PM
Junior Open |  | 20 | 21 | 22 | 23 | 24 | 25 | 26
AM
PM
Junior Open |  | 20: 27; 21: 28; 22: 29; 23: 30
| AM | 22: Engage Conference; 23: Engage Conference
PM
DECEMBER
|  | m | t | w | t | f | s | s
Junior Open |  | 24: 1; 25: 2; 26: 3
AM
PM
Junior Open |  | 4 | 5 | 6 | 7 | 8 | 9 | 10
AM
| PM | 5: Awards Ceremony
Junior Open |  | 11 | 12 | 13 | 14 | 15 | 16 | 17
AM
PM
Junior Open |  | 18 | 19 | 20 | 21 | 22 | 23 Closes at 4pm | 24 Closed
AM
PM
Junior Open |  | 25 Closed | 26 Closed | 27 Closed | 28 Closed | 29 | 30 | 31 Closes at 4pm
AM
PM
JANUARY
|  | m | t | w | t | f | s | s
Junior Open |  | 1 Closed | 2 | 3 | 4 | 5 | 6 | 7
| AM |  | 6: Exhibition Ends; 7: Deinstall begins
PM