## Timeline
| 2016-06-01 | 2016-07-01 | 2016-08-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | September | October | November | December | 2017-01-01 | February | March | April | May | June | July | August | September | October | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | Autumn 2018
Student CPD | Advertise CPD to students | [5 empty] | Recruitment |  | First Core Skills day/intro - 5 November |  | Second core skills |  |  |  | Development of 2017 pices | Development of 2017 pieces | Performances at NMB |  |  | Connector workshops | Composition workshops |  |  | Core Skills |  |  | Development of LoGG | Dev of LoGG | Delivery of LoGG
Evaluation | Set up framework | [5 empty] | First Phase with MoL | First Phase with MoL |  |  | Interim report |  |  |  | Link to dev of 2017 pieces |  | Obesrvation of MoL mass workshop and community NMB commissions |  |  | Report timeline for 2018 agreed | Second MoL project workshop observations |  |  | Check back with schools to see impact of MoL |  |  |  |  | Draft report to RPS | Delivery of report
Minute of Listening | CPD with teachers. Early adopter primary schools start MoL after Spring Bank | [5 empty] | MoL training | MoL delivery | [7 empty] | Work with composers for NMB - if school selected by composer for NMB | Possible involvement as one of the groups for composers |  | Development of new packs |  | Second MoL project | [6 empty] | Possible school group involed in LoGG? | Invited to attend LoGG performances
Developing community pieces | Work with Composers to identify community groups, set up shape and timeframe for delivery of pieces and specify requirements from each community group |  |  |  |  | Groups agreed |  |  |  | Intro session for community groups |  |  |  |  | Development of 2017 pices | Development of 2017 pieces | MoL massed workshop at festival; audience composition workshops at Festival; performances of x5 pieces during the festival |  | invites out for connector workshops and feedback from July 2017 | x3 connector workshops | compositions from scratch workshops - max of 10, 2 hour workshops - delivered by James Redwood, composers, local music leaders. Attended by groups & music leader students |  |  |  | Recruitment for 2018 and profile for LoGG |  | create pieces | create pieces | performances LoGG | review
Communication | Prepare press release | Press Launch for project |  |  |  | Photo/interview possibility & Media Partner |  |  | Recruitment flyers continue | Intro. Session - profile raising | Recruitment and audience marketing | Festival campaigns |  |  |  | Festival campaigns | Festival |  | Press opportunity | recruitment profiling for connector workshops |  |  |  |  | Campaign for LoGG |  |  | press opportunities within individual groups | Performance press and flag research report
Participants |  | details to be confirmed
Production | Detail To be Confirmed
Funding | Detail To be Confirmed
Partners | Partnership agreements drafted
Monitoring | First partnership meeting. Schedule for monitoring to be agreed | Establish the steering and advisory groups

## Stakeholders
Stakeholder list |  | Role | Other people / details
Core | PRS | Lead project deliver, links to NMB 2017 and strategic development for composers | Vanesssa King; Naomi Belshaw
| Hull City of Culture | Management of City of Culture, housing the project co-ordinator and links with strategic delivery | Sam Hunt; Ian Reed (Head of Educaiton); Katy Fuller
| Sound and Music | Schools project and research, linked to Minute of Listening project | Judith Robinson; Susanna Eastburn
| Pam Burnard | Research Supervisor | Reporting to Alastair Borthwick
Local Partners | Hull University | trainee music leaders programme and development of young composers and hosting the evaluation of the project | Alastair Borthwick;
| Music Hub | legacy development - ensembles and supports inks with schools in Hull, based at Arbemarle Centre | Chris Maynard
| Schools | Primary Schools in Hull: partners for Minute of Listening project and teacher taster sessions
Community Groups | Group 1: Freedom Choir | Initial groups involved in year one of the projects
| Group 2 | tbc
| Group 3 | tbc
| Group 4 | tbc
| Group 5 | tbc
Composers | Sam Lee | Commission: Travellers community and fishing - interested in NE Yorkshire oral tradition. | Work with his group, plus local singers and players
| Errolyn Wallen | Mighty Rivers' existing piece | Orchestra X, plus local people
| Barry Irvine | 13 Vices - existing piece about vices | 3 professional musos, plus community
| Jason Singh | Footsteps2' - new piece, blend of Gaelic song and North Indian Raga | Schools and Music Tech in Hull, plus x2 of his own musicians and community groups
| Eliza Carthy | New piece, currently researching trade routes and slavery, inspired by rivers, migration and movement of people | Freedom Choir, plus Moulettes folk group
| James Redwood | Composer mentor and facilitator across the project
Funders | Hamlyn Foundation
Media Partners | BBC Radio 3 | Coverage for the festival and also potential support through BBC Young Composers programme. NB Early discussions with Simon Webb at BBC Symphony Orchestra

## Task List
NB Green italic - completed action
Green | moving forward
Amber | keep an eye on, pending action required
Red | needs urgent attention
Oct internal meeting | What - draft set of tasks | Action | Deadline | Subsequent notes updates from monitoring meetings
Communications | Lead to be agreed
Sign off press statement partnership listing and logos
Agree communication strategy and schedule
Meet with BBC Radio 3 and agree partnership and project schedule
Agree print schedule for the project, linking across to Sound and Music, Trainees and Performance Groups
Support recruitment and profile raising to building awareness for participants taster days and project recruitment
Local, national and international press contacts
General | Project Director and Co-ordinator lead
Partnership agreements - draft and agree
Put together joint timeline for project delivery
Appointment of Co-ordinator and induction
Selection of schools and set schedule for introduction and training sessions
Visit and agree community groups
Agree and activate recruitment schedule, set introduction sessions - checking CoC activity to see if this might link with any key projects and critical communication dates
Meet and agree recruitment and cohort for HEI apprentice music leaders
Contract James Redwood and pencil dates
Contract and agree delivery schedule for NMB composers - delivery of each of the 5 compositions and links with community
Build in Hull Composer project into NMB composer meetings
Attend PRS steering group meeting
Dovetail Land of Green Ginger schedule into the
Recruitment local music leaders to work with each of the groups
Scope venues for rehearsals
Meet with Music Hub to define role within the project
Fundraising / Finance | PRS Naomi Belshaw
Complete a project delivery budget and agree with PRS
Agree process for management of invoices and payment reporting for the project
Check dates for Hamlyn Foundation reporting and put these into the schedule
Recruitment | Project Co-ordinator to lead
Set schedule for each group and timeline
Draft copy for each of the projects
Draft project pack for participants as apprentice music leaders
Assessment of recruitment gaps
Performance | Project Co-ordintator and HCoC to lead
To be devised once groups are understood more fully and Hull Composers are contacted
Participants / volunteers | HCOC and Co-ordinator to lead
Look at volunteering for stewarding and participants in place for HCoC. Use as a way of networking 'on the ground' for recruitment to groups and festival performances
Logistics - H&S etc
To be devised once groups are understood more fully and Hull Composers are contacted