## Summary (hidden)
Tab name: | 1 |  | Tab name: | Tab name: | Tab name:
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!

## Timeline
[9 empty] | NOV |  | DEC |  |  |  | JAN |  |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  |  |  |  | JUN |  |  |  | JUL |  |  |  |  | AUG |  |  |  | SEP |  |  |  | OCT |  |  |  |  | NOV |  |  |  | DEC
ITEM | NOTES | PROJECT LEAD | START | END | time axis 2016-10-24 to 2018-01-01
TEMPLATE ROW |  |  | 2017-04-10 | 2017-04-10 | bar: 2016-10-24 to 2018-01-01
PRODUCTION | bar: 2016-10-24 to 2018-01-01
Creative Team Design Meeting - Hull | Pete Malkin & Paul Veysey | PV | 2017-04-25 | 2017-04-25 | bar: 2016-10-24 to 2018-01-01
Creative Team Design Meeting - Hull | Amanda S, Chris Davey, Pete M and Paul Veysey | PV | 2017-05-17 | 2017-05-17 | bar: 2016-10-24 to 2018-01-01
Full Creative Team Visit | All | PV | 2017-06-01 | 2017-06-01 | bar: 2016-10-24 to 2018-01-01
Creative Team Design Meeting - Hull | Imogen & Sarah F, Paul V | PV | 2017-06-16 | 2017-06-16 | bar: 2016-10-24 to 2018-01-01
DESIGN DEADLINE - COSTING LISTS | From All creative Team | PV | 2017-06-19 | 2017-06-19 | bar: 2016-10-24 to 2018-01-01
DESIGN FINAL MODEL | All Creative Team | PV | 2017-07-28 | 2017-07-28 | bar: 2016-10-24 to 2018-01-01
SCHEDULE LOCK DOWN | For Budget & Brochure | PRODUCER
[5 empty] | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
COMMUNITY CAST | bar: 2016-10-24 to 2018-01-01
xxxx | yyy | PV | 2017-04-25 | 2017-04-25 | bar: 2016-10-24 to 2018-01-01
xxxx | yyy | PV | 2017-05-17 | 2017-05-17 | bar: 2016-10-24 to 2018-01-01
xxxx | yyy | PV | 2017-06-01 | 2017-06-01
xxxx | yyy | PV | 2017-06-16 | 2017-06-16
xxxx | yyy | PV | 2017-06-01 | 2017-06-01 | bar: 2016-10-24 to 2018-01-01
xxxx | yyy | PV | 2017-06-01 | 2017-06-01 | bar: 2016-10-24 to 2018-01-01
[5 empty] | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
REHEARSALS & PERFORMANCE SCHEDULE | bar: 2016-10-24 to 2018-01-01
Community Cast Rehearsals |  | PV | 2017-04-25 | 2017-04-25 | bar: 2016-10-24 to 2018-01-01
Professional Cast | Manchester | PV | 2017-10-02 | 2017-10-02 | bar: 2016-10-24 to 2018-01-01
Professional Cast | Manchester | PV | 2017-10-09 | 2017-10-09 | bar: 2016-10-24 to 2018-01-01
Professional Cast | Hull | PV | 2017-10-16 | 2017-10-16 | bar: 2016-10-24 to 2018-01-01
Professional Cast | Hull | PV | 2017-10-23 | 2017-10-23 | bar: 2016-10-24 to 2018-01-01
Technical Rehearsals | Full | PV | 2017-10-30 | 2017-10-30 | bar: 2016-10-24 to 2018-01-01
1st Preview |  | PV | 2017-11-04 | 2017-11-04 | bar: 2016-10-24 to 2018-01-01
Press Night |  | PV | 2017-10-30 | 2017-10-30 | bar: 2016-10-24 to 2018-01-01
Perfromance Week 1 |  | PV | 2017-10-30 | 2017-10-30 | bar: 2016-10-24 to 2018-01-01
[5 empty] | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
MARCOMMS - DIGITAL - TICKETING | bar: 2016-10-24 to 2018-01-01
Creative Brief | Image, Copy, | MARCOMMS LEAD | 2017-04-25 | 2017-04-25 | bar: 2016-10-24 to 2018-01-01
Strategy Draft |  | MARCOMMS LEAD | 2017-10-02 | 2017-10-02 | bar: 2016-10-24 to 2018-01-01
Comm Cast Recruitment Strategy |  | MARCOMMS LEAD | 2017-06-01 | 2017-06-01
SEASON BROCHURE DEADLINE |  | MARCOMMS LEAD | 2017-06-15 | 2017-06-15
Box Office Forms |  | MARCOMMS LEAD | 2017-09-01 | 2017-09-01 | bar: 2016-10-24 to 2018-01-01
Press Release Announcement |  | MARCOMMS LEAD | 2017-08-28 | 2017-08-28 | bar: 2016-10-24 to 2018-01-01
ON SALE DATE | 6 WEEKS IN ADVANCE |  | 2017-09-15 | 2017-09-15 | bar: 2016-10-24 to 2018-01-01
Thing | bar: 2016-10-24 to 2018-01-01
Thing | bar: 2016-10-24 to 2018-01-01
Thing | bar: 2016-10-24 to 2018-01-01
Thing | bar: 2016-10-24 to 2018-01-01