In with a Bang Humber Coordination Meeting
10th November 2016

Attending: Chris Clay, Melissa McVeigh, Cheryl Ribbitt, Pete Curry, Gary Beestone, Zoe Snow, Simon Page, Kim Harrop, Mark Collier, Andrew Swift, Ian Schramm, David Parkinson, James Glansfield

Apologies: Martin (Humber Rescue)

| POINT | ACTION |
| --- | --- |
| 1. LOAD-IN – KING GEORGE DOCK (KGD) |  |
| 1a. Access and Deliveries 1b. Delivery of Barges Schedule / Loading of barges at KGD SP (Titanium) – confirmed delivery of 12 minute firework display as follows: - Titanium arrival 28/12/2016 to load 2 x sea worthy vessels - Delivery in either 2 x 7.5 ton / 1 x 18 ton vehicles (tbc) - Fireworks will be safe and waterproof once in pre-firing configuration - 01/01 vessels into position from midday. 8 hours to carry out checks. - Keeping exclusion zone (20/30m minimum) - After shows completion, 5 minutes required to check everything has fired and cooled down before removal of barges from the channel - 01/02 de-rig. Complete by 5pm |  |
| 2c. Movement of Barges in and out KH – questioned whether Titanium needs barges in place 8 hours prior ABP - Titanium can leave KGD at 17:00, before the ferries depart, to be in position by 18:00 ahead of 20:17 sequence |  |
| 3. SHOW DAY |  |
| 3a. Marina Closure MM - 16:00 is desired closure time MC – confirmed there have been enquiries about boats visiting for fireworks display. A message has been circulated for boats to arrive in the before 12:00 |  |
| 3b. Exclusions Zones i. Marine traffic on Humber SP – confirmed Titanium are happy with 30m minimum exclusion zone ABP – Preferable 300m as allows zone to be policed |  |
| 3c. Public gathering on Victoria Promenade |  |
| 3d. Humber Rescue and Police Launch SP – confirmed there will be crew on the vessel. Asked if there is a requirement of safety boat. MM – Humber rescue will be patrolling from Albert Dock to Siemens Dock and will be on call. ABP - Lock keepers confirmed on workboats, double staff numbers on 01/01 Comms - Channel 22 decided ABP – confirmed use of Wind Guru for weather forecast - accurate to 15-20 minutes |  |
| 4. PERMISSIONS |  |
| 4a. Notice to Mariners AS – ABP to issues notice to mariners of barge positions and 300m exclusion zone to be broadcast by VTS on 01/12/16 | AS |
| 5. AOB |  |
| 5a. Scale Lane Bridge MM - confirmed it will be open as it is emergency egress |  |
| 5b. Residents GB – confirmed staff will be properly briefed regarding allowing access to residents in the Marina. MM - to speak to Marina residents throughout December due to boat owners attending the event MM - to circulate wristbands to ABP to give to residents in the Marina/docks MC (ABP) - to contact residents and ask them to contact Hull 2017 | GB MM MM MC |
| 5c. Accreditation Titanium to send a list of names, vehicles and full schedule to ABP MM – confirmed all staff will be accredited | SP |
| 5d. Stewarding GB - confirmed stewards will be onsite from 16:00. Site to open 18:30 and early opening is an option if there is a swelling crowd. GB - confirmed 8 stewards on Spencer land GB - confirmed use of Headline Barriers and any low walls will have barriers on them as the main concern is children standing on walls. 5e. Security CC - Princes Quay car park is currently an issue, plans to hold event on 01/01. Hull 2017 looking into this and feedback to Police. 5f. A63 CC – Use of VMS to notify motorists to reduce speed CR - confirmed HCC have used this in the past GB/CC – to speak to Graham Hall at HCC about use of VMS | CC CC |
| 5g. Event Control GB – Head of security will be in contact with all the stewards - with a representative of Hull 2017 (CC) GB – Control room TBC CC – Nominate member of event team at Clough Road with Silver Command CC – Look at Ask Italian building as event control location. NPS/Scotts | GB GB CC CC |
| 5h. Food & drink concessions MM – confirmed 4 concessions in Zone B GB – to confirm location of concessions in Zone B. Hull 2017 to manage location and not operations. MM – confirmed no sale of alcohol | GB |