CREATIVE PARTNERS 
END OF PROJECT REPORT – EDINBURGH TAKEOVER

| ORGANISATION/PROJECT NAME: | Sad Little Man – Pub Corner Poets |
| --- | --- |
| MAIN CONTACT: | Tyler Mortimer |

Overall, how did you do reaching the targets laid out in your agreement?

* Target: target(s) listed within your agreement with Hull UK City of Culture 2017

* Actual: final figures for your project

|  | TARGET* | ACTUAL |
| --- | --- | --- |
| PRODUCTIONS AND PERFORMANCES (IN EDINBURGH) |  |  |
| No. of productions or co-productions | 1 | 1 |
| No. of performances | 5 | 5 |
| No. of accessible performances (e.g. captioning/audio description/relaxed) | 0 | 0 |

Please provide a short description of the activities delivered:

A 5-date fringe run of Sad little man By Josh Overton.

Thinking about your project as a whole, what would you say have been the main successes and challenges in terms of the activity delivered. Please include or attach a record of any press/media coverage and any awards won:

Joining the festival late on in the final week presented a challenge in generating audiences. However, this was hugely successful for us as well as generating press interest. Being part of #Hulltakeover really helped lock in interest in our production early on.

http://www.edinburghguide.com/festival/2017/edinburghfringe/sadlittlemanparadiseinthevaultreview-18536

https://www.thestage.co.uk/reviews/2017/sad-little-man-review-paradise-vault-edinburgh-devastating-meditation-grief/

http://www.miromagazine.com/edinburgh-review-sad-little-man/

https://www.thestage.co.uk/features/interviews/2017/director-tyler-mortimer-show-doesnt-need-age-rating-suicide-also-affects-people-16/

In the table below, please enter the details of people contracted by your organisation to make this project happen.

| ROLE | GENDER | AGE | ETHNICITY | DISABILITY/LONG TERM ILLNESS | HULL RESIDENT? | TOTAL NO. OF DAYS WORKED |
| --- | --- | --- | --- | --- | --- | --- |
| Tech 1 | male | 23 | White British | na | yes | 5 |
| Tech 2 | Male | 22 | White British | na | yes | 5 |
| Director | Male | 29 | White british | na | no | 12 |
| Actor | Male | 24 | White british | na | yes | 12 |
| Actor | Female | 22 | White british | na | yes | 12 |
| writer | male | 24 | White british | na | Yes | 6 |

In total, how many people have attended your performances?

| DATE | TOTAL TICKETS SOLD | TOTAL AUDIENCE ATTENDING |
| --- | --- | --- |
| 23rd aug | 40 |  |
| 24th aug | 30 |  |
| 25th aug | 40 |  |
| 26th aug | 36 |  |
| 27th aug | 28 |  |
|  |  | 174 |
|  |  | (see attached full sales report) |

Please provide a description and estimated total number of contacts made or strengthened through your activities in Edinburgh:

40.