## Sheet1
East Mount - AndNow - Longhill Burn
SHOW STAFFING AND ROLES
SCHEDULE
20:00 | Security Briefing
20:30 | Security deployment
21:00 | Gates open
21:30 | Show start
22:00 | Bonfire lit
22:30 | Show ends
23:00 | Audience cleared
RADIO CHANNELS
9 | Event Control
10 | Security
11 | Show
EMERGENCY ACTIONS
CORE TEAM
CALL SIGN |  |  | Radio | CH | LOCATION
Gareth | Hull2017 | Event Manager | 1 | 9 | Roaming
Maddie | Hull2017 | Producer - Artist Liaison | 1 | 9 | Roaming
Adam | Hull2017 | Production Manager | 1 | 9 | Roaming
Sarah H | Hull2017 | Volunteer Lead | 1 | 9 | Roaming
Katy F | Hull2017 | Executive Producer | 1 | 9 | Roaming
Elizabeth | Hull2017 | Assistant Producer - Participants/Volunteers | 1 | 9 | Roaming
Mandy D | And Now | Fire Safety Manager | 1 | 11 | Roaming
Ben | And Now | Pyro Gaffer | 1 | 11 | Roaming
Mark | And Now | Pryo crew | 1 | 11 | Roaming
Pete | And Now | Pyro Crew | 1 | 11 | Roaming
Lis | And Now | Stage Manager - Participants | 1 | 11 | Roaming
Security Manager | Prestige | Security Lead | 1 | 9 & 10 | Roaming
SPARE |  |  | 1
SPARE |  |  | 1
SPARE |  |  | 1
VOLUNTEERS | NUMBER |  |  |  | LOCATION |  | DUTIES
Wayfinding 1 | 2 |  |  |  | Shannon Road / Brent Avenue | DUTIES | Directing people to Waveney Road
[6 empty] | NOTES | No parking on site - plenty on street parking further down Shannon Road
Wayfinding 2 | 2 |  |  |  | Shannon Road / Limerick Close | DUTIES | Directing people to Waveney Road
[6 empty] | NOTES | No parking on site - plenty on street parking further down Shannon Road
Wayfinding 3 | 2 |  |  |  | Shannon Road / Frome Road | DUTIES | Directing people to Waveney Road
[6 empty] | NOTES | No parking on site - plenty on street parking further down Shannon Road
Wayfinding 4 | 2 |  |  |  | Brent Avenue / Waveney Road | DUTIES | Directing people to Waveney entrance (roadway to the left)
[6 empty] | NOTES | No parking on site - plenty on street parking further down Shannon Road
Wayfinding 5 | 2 |  |  |  | Frome Road / Waveney Road | DUTIES | Directing people to Eastmount Community Centre entrance (path to the right)
[6 empty] | NOTES | No parking on site - plenty on street parking further down Shannon Road
Access 1 | 2 |  |  |  | Eastmount Community Centre car park | DUTIES | Meeting blue badge holders directing them to parking and viewing - viewing to the right of the bonfire
[6 empty] | NOTES | First come first served
Access 2 | 2 |  |  |  | Viewing area - front of bonfire (right) | DUTIES | Meeting viewing platform users and aiding
[6 empty] | NOTES | First come first served
Meet Greet 1 | 2 |  |  |  | Waveney Road pedestrain entrance | DUTIES | giving information, start times, toilets etc
Meet Greet 2 | 2 |  |  |  | East mount car park to main field (lampost) | DUTIES | giving information, start times, toilets etc
Meet Greet 3 | 2 |  |  |  | Ellingham Road roadway entrance | DUTIES | giving information, start times, toilets etc
Meet Greet 4 | 2 |  |  |  | East mount car park to main field | DUTIES | giving information, start times, toilets etc
Info 1 | 2 |  |  |  | Main field - festoon | DUTIES | giving information, start times, toilets etc
Info 2 | 2 |  |  |  | Main field - festoon | DUTIES | giving information, start times, toilets etc
Info 3 | 2 |  |  |  | Main field - toilets | DUTIES | giving information, start times, toilets etc
Info 4 | 2 |  |  |  | Main field - stage | DUTIES | giving information, start times, toilets etc
30
SECURITY
CALL SIGN | SIA | Stewards |  | RAD CH | LOCATION |  | DUTIES
Gate 1 | 1 |  | 1 | 10 | Gate from Waveney Road | DUTIES | Click people in
[6 empty] | DUTIES | If at capacity close gates and inform people we are at capacity
[5 empty] | Amber to Red | EMERGENCY ACTION | Ensure gates are open for people to evacuate
[6 empty] | NOTES | We don't expect to get to capacity - the decision to close the gates is that of the Event Manager (Gareth Hughes(
Gate 2 | 1 |  | 1 | 10 | Gate from Ellingham Close | DUTIES | Click people in
[6 empty] | DUTIES | If at capacity close gates and inform people we are at capacity
[6 empty] | DUTIES | Blue Badge parking - access
[5 empty] | Amber to Red | EMERGENCY ACTION | Ensure gates are open for people to evacuate
[6 empty] | NOTES | We don't expect to get to capacity - the decision to close the gates is that of the Event Manager (Gareth Hughes(
Waveney | 2 | 2 | 2 | 10 | Patroling Waveney Road | DUTIES | Advising people trying to park - no parking (unless a resident)
[6 empty] | DUTIES | Ensuring a vehicular access is maintained
[5 empty] | Amber to Red | EMERGENCY ACTION | Position to meet and walk blue lights onto site
[6 empty] | NOTES | This is an advisory role - there will be no enforcement ie towing available
SECURITY
CALL SIGN | SIA | Stewards |  | RAD CH | LOCATION |  | DUTIES
Audience A | 1 | 1 | 1 | 10 | To the left of the site | DUTIES | Mobile patrol and response
[6 empty] | DUTIES | Check perimeter
[5 empty] | Amber to Red | EMERGENCY ACTION | Ensure exits are clear for evacuation
[5 empty] | Amber to Red | EMERGENCY ACTION | Direct people to the nearest exit
Audience B | 1 | 1 | 1 | 10 | To the right of the site | DUTIES | Mobile patrol and response
[6 empty] | DUTIES | Check perimeter
[5 empty] | Amber to Red | EMERGENCY ACTION | Ensure exits are clear for evacuation
[5 empty] | Amber to Red | EMERGENCY ACTION | Direct people to the nearest exit
Hardington | 2 |  | 1 | 10 | Hardington Close gate and nature reserve | DUTIES | one static to man the gate from Hardington Close
[6 empty] | DUTIES | one to patrol to the nature walk
[5 empty] | Amber to Red | EMERGENCY ACTION | Ensure exits are clear for evacuation
[5 empty] | Amber to Red | EMERGENCY ACTION | Direct people to the nearest exit
Holderness | 2 |  | 1 | 10 | From Holderness Drain perimeter | DUTIES | one static at production area - checking accreditation
[6 empty] | DUTIES | one patroling barrier line
[5 empty] | Amber to Red | EMERGENCY ACTION | Ensure exits are clear for evacuation
[5 empty] | Amber to Red | EMERGENCY ACTION | Direct people to the nearest exit
Rope line | 2 | 2 | 2 | 10 | Barrier line - front of bonfire | DUTIES | Advise people not to cross barrier line
[6 empty] | DUTIES | Mobile patrol the barrier line
[5 empty] | Amber to Red | EMERGENCY ACTION | Ensure people are not moving towards the bonfire
[5 empty] | Amber to Red | EMERGENCY ACTION | Sweep area to front of bonfire to ensure public are clear
[6 empty] | NOTES | Do not stray from the line
Pyro | 4 |  |  |  | Rear of bonfire | DUTIES | Protecting back line from dog walker etc
[6 empty] | DUTIES | Escorting walkers to Hardington Close - to leave site
[5 empty] | Amber to Red | EMERGENCY ACTION | Ensure rear pyro area is not accessed by public
WELFARE
CALL SIGN |  |  |  | RADIO CH | LOCATION |  | DUTIES
First Aid 1 |  |  | 1 | 9 | Car park | DUTIES | Treatment / Evac
First Aid 2 |  |  | 1 | 9 | Mobile | DUTIES | Treatment / Evac
Lost clhildren |  |  | 1 |  | Eastmount Community Centre | DUTIES | Lost children (inc paperwork)
| 16 | 6 | 28