## Sheet1
Part II | AUG - NOV
LOGG
Heralding
DATE
W/C | WHAT | NARRATIVE | VISUAL | ANIMATION |  | LOCATION | ELEMENTS
2017-08-28 | Brochure Launch | Crate stunt | Stack of crates - include GNGG stencil and ACT I, II, III | Green Ginger Fellowship attending/Facilitating - volunteers? |  | At Freedom Festival, somewhere
Potential 23 AUG in |  |  | Previous branding OK | Chalking around crates
|  |  | clue of the locations, riddle? | map on side with locations of previous shows
11 SEPT- 2 OCT | ASWARM Heralding | FOH crate appears | Crate large (10ftx10ft) - with Rerediffusion logo and dates on | Sound |  | Pickering Park | ???
| "Super Voice" |  | Full of voice vessels
Taking the parkies voice - as the last voice and squeeze into the crate
Stylised map of where the voices collected
2017-09-25 | Cardboard city Heralding | Tiny people crate | Crate with peep holes, with tiny props | Static tableauxs |  | Staples - photoshoot | Large crate? | "For delivery to Derringham" - inside
Lighting
Props
|  | Intervention | footprints at Pickering Park - leading to drain - | Leading to Pumping Station
2017-10-02 | Cardboard city Heralding | Tiny people crate | As above | As above |  | Need to scope 3 locations
LOGG mark appears
Crate appears at Pumping Station - dates?
|  | Intervention | footprints at Pickering Park - leading to drain - | Leading to Pumping Station
2017-10-16 | Macnas Heralding | Road closure notifications out
2017-10-23 | Macnas Heralding | Large crates | TBC | TBC |  | Land of Green Ginger / Whitefriar Gate | ???
|  | Date and time | Map of Route
|  | Other crates appear along the route | TBC | TBC
2017-11-10 | Macnas Heralding | Giant crate | Animation as part of the parade |  |  | Queens Gardens
NEW ELEMENTS
ASWARM CRATE | FOH | Big enough to stand in | 10ft x 10ft | Needs to be weather proof | Scenic painted | Branding and map
TINY PEOPLE CRATE | Movable
| Lighting inside | Davey to spec size and interior | Power
MACNAS CRATE | ???
ACTIONS
Shed options to KF/MM | GH
Locations in Derringham - 3x - with drains (for footprints) and crate | GH/MM
Budget crate moves for Freedom - check location | GH
As above confirm scope of freedom intervention | MM
Scope the large crate - Macnas - what does it do etc - Noleen conversation | KF/MM