WOW A proposal for engagement and participation

| HELLO HULL Made In Hull Roots & Routes | In the first edition children are asked to respond iconic women of the world. Using the Big Lil mural on Anlaby Road as inspiration In the second edition there is a focus on Shirley Craven in the HULL HERO section | Made in Hull NOW Roots & Routes 13 Feb All primary schools Approx. 22,500 Not all schools will be using the same magazine at the same time, but leading up to WOW, and during WOW, both editions will be in schools | £8000* |
| --- | --- | --- | --- |
| CREATIVE CURRICULUM | Made in Hull season contains A Great Hullensian flashcard game. People included are; Lucy Beaumont, Maureen Lipman, Shirley Craven and Karen Briggs | 2 January 2017 All primary schools Approx. 22,500 |  |
| GROWING UP GIRL | Safety & Body Image – using two of the key findings from the Girls Rights report. One Day Creative will create a one day workshop that responds to; Growing Up Girl, and, Growing Up Boy | w/c 27 Feb w/c 6 March 10 primary schools (one class in each), one per day over two weeks | £500 development £395 per school £4450 |
| REVOLUTIONARY MAKER | Artist’s commission will include a self-led participatory project. This resource can be used by schools to get their students engaged Workshops delivered in some of the schools? | 9 January – 3 March 2017 All primary schools Approx. 22,500 All Secondary schools | Commission £15000* |

| ACHIEVING EQUALITY | Include animation Could this be Jackie Fleming’s involvement – HD to speak to JF WHO WOULD create the narrative for this film? (Suzanne Clisby – would she need paying for this?) | WC 6 March All secondary schools & colleges | Create a film / animation £1000 |
| --- | --- | --- | --- |
| HULL SPEAKS | SLIDE SHOW to be displayed in all school foyers on International Women’s Day Using the information from the State of the Girls Rights report Created by digital (EC) or marketing (RC) | Wednesday 8 March 2017 All secondary schools & colleges |  |
| WOW Satellite | Take speakers and performers/performances that are in Hull for WOW and programme that at ONE school. Thom to manage on the day? Go, with Thom, to SMSC and see the available spaces Nancy Birtwhistle | Friday 10 March 2017 ST MARY’S Reserve / Book the theatre space for this date Contact - Martin McAllister | £booking space |
| TYPECAST | Launch IDENTITY project in The Boulevard Centre on International Women’s Day with Emilie Taylor When is the next meeting? | Wednesday 8 March | £15000 |
| THE SALON | Hack & Host Salon SPACE ISSUE at City Hall, can we revisit the idea with H&H and make it work somewhere else potentially | Friday 10 – Sunday 12 March | £4290 |
| FUZZFEED | Review of weekend? What access is required? Will the young people attend some of the talks? Appear on one of the panels? | Check with MY POCKETS |  |
| INTO FILM? | Conversation still to be had |  |  |

*costs not specific to WOW