PRSF NEW MUSIC BIENNIAL

HULL

29th JUNE to 2nd JULY 2017

ARTIST PACK

ARTIST: Ray Lee

ARTIST CONTACT (Mobile number): TBC – PROMOTER TO CONFIRM

James Ball - +44(0)7508 112 753

VENUE: Zebedee’s Yard

Address: Zebedee’s Yard, 23 Posterngate, Hull HU12JT

Phone:

LOADING IN FROM: Posterngate (orange dot)

PARKING REQUIREMENT and LOCATION:

TBC – PROMOTER TO CONFIRM

PERSONNEL

STAGE MANAGER (Primary contact show weekend only):

PRODUCTION MANAGER: Gareth Hughes – 07733112272

PRODUCTION ASSISTANT: Joanna Morley – 07725 942808

VENUE CONTACT:

DATE AND TIME OF PERFORMANCE: Friday 30th June 11:00,16:00 and 22:00, Saturday 1st July 11:00. 16:00 and 22:00 and Sunday 2nd July 10:00 and 12:00 (all performances 45mins)

PRODUCTION SCHEDULE:

| WEDNESDAY 28 JUNE |  |  |
| --- | --- | --- |
| AM | Pick up keys from Mike (gates and green room) | GDH |
| 07:00 | CAR PARK CLOSED | Trinity House |
| 08:00:00 - 22:00 | Set up | Invisible Forces |
| 22:30 | Isolate ambient lighting | GDH |
| THURSDAY 29 JUNE |  |  |
| 12:00 | 12 rung Zarges dropped off | HPSS |
| DAY | 2x TV and media player set up - Greenroom | HPSS |
| 12:00 - 16:00 | Crew call x6 | Music Consortium |
| 16:00 - 20:00 | Crew call x2 | Music Consortium |
| 20:00 - 23:00 | Lighting and sound test | Invisible Forces |
| 23:00 - 00:00 | Lighting test only | Invisible Forces |
| 23:00 - 10:30 | 2x SIA - over night security | Prestige |
| FRIDAY 30 JUNE |  |  |
| 07:00 | CAR PARK CLOSED | Trinity House |
| 10:30:00 - 23:00 | 2x sia 2x stewards - event security | Prestige |
| 11:00 - 11:45 | PERFORMANCE - Ray Lee - Ring Out | Invisible Forces |
| 16:00 - 16:45 | PERFORMANCE - Ray Lee - Ring Out | Invisible Forces |
| 22:00 - 22:45 | PERFORMANCE - Ray Lee - Ring Out | Invisible Forces |
| 23:00 - 08:00 | 2x sia - over night security | Prestige |
| SATURDAY 1 JULY |  |  |
| 07:00 | CAR PARK CLOSED | Trinity House |
| 10:30:00 - 23:00 | 2x sia 2x stewards - event security | Prestige |
| 11:00 - 11:45 | PERFORMANCE - Ray Lee - Ring Out | Invisible Forces |
| 16:00 - 16:45 | PERFORMANCE - Ray Lee - Ring Out | Invisible Forces |
| 22:00 - 22:45 | PERFORMANCE - Ray Lee - Ring Out | Invisible Forces |
| 23:00 - 08:00 | 2x sia - over night security | Prestige |
| SUNDAY 2 JULY |  |  |
| 07:00 | CAR PARK CLOSED | Trinity House |
| 10:00 - 10:45 | PERFORMANCE - Ray Lee - Ring Out | Invisible Forces |
| 12:00 - 12:45 | PERFORMANCE - Ray Lee - Ring Out | Invisible Forces |
| 14:00 - 20:00 | OUT | Invisible Forces |
| 14:00 - 20:00 | Crew call x6 | Music Consortium |
| 20:00 | CAR PARK OPEN | Trinity House |

TECHNICAL

Material

1 Laptop

1 Samsung 55inch LCD Screen

1 Unicol K Stand Complete

RIDER:

TBC

BACKLINE:

N/A

ACCREDITATION

David & Alice Porter (Directors)

Steve & Sam Shaw (Directors)

Peter & Lorraine Boardman (Directors)

Wes Zepherin (Director)

Kirsty & Gary Halliday (Marketing)

Ben Pugh (Production)