Agenda

Artistic update

90 mins / 70 if possible

Chorus are more important

Read-through on Friday 
Noreen Kershaw – TV Director

Site management

Sustainable transportation

45mins before show arrival

Toilet break at Deep

AP Geographical data from audiences

AP access bookings

Platforms for 5-10 wheelchair users. AP SL to confirm

AP JR to confirm budget for site management

Take clearance from Gareth & Joanna

Site map

Gareth to circulate

Access provision

Captioner & tech support to dress rehearsal

10 tablets

Residents’ dress rehearsal

400

Staff to be added to figures.

Volunteers to see dress rehearsal?

BO management as well

Industry invites

Paul Hamlyn

UK Culture launch – BBC connection – 4th April

David Watson – re 600 on sale

James Maguire – 400

Ian Read – Hull College invites & capturing viewing figures. South Holderness Tech College.

Volunteer tickets

Partners, volunteers (take email addresses) & Jenny Hutt

Oct Extension (time permitting)

Ticketing each show

Running the show back to back

First week part 4, second 2 weeks are joint tickets

Design & Constructer

Meeting on last Friday to call extension

w/c 19 Sept – Set deliverable in this time

Marketing update

Eco stencils

Railings & lampposts

Back up signs

Bus stop signage

Signage on the road

Dress rehearsal – fit up signs come down

Pop up gazebo gala tent – pack it down at the end of each night

Set in place over summer – Hull 2017 to create signage

Part 4 is coming in Oct. Sign ups to participate in part 4.

Press night

AP list to Alan & Joanna asap

October – wider selection of media – land & sea. John Harris Guardian Closing of the year piece.

Space project – trade story

WhatsOnStage – Alan live

BBC Radio 3 Free Thinking 4th April

New Statesman piece

M&E responses from audiences

Community company info.

Resident’s story.

Peter Levy.

AP call the BBC.

Partnerships – RC to speak to signage company.