## Sheet1
Timeline | Substance Combined Timeline | Responsibility | Complete | Notes
Future Forum (FF)
Film Festival
Hull Venue
Entire Festival
2017-07-24
2017-07-31 | Venues confirmed for FF | Martin | Yes | Need to look into using The Warehouse next to Thieving Harry's with Wykeland.
2017-08-07
2017-08-14
2017-08-21 | Budget Updated for entire project | Martin
2017-08-25 | At least half of the sessions confirmed and partners in place | Luke
| Warp confirmed for Hull Arena performance | BR/Martin/Sam
| Website complete on Hull2017 site | Eleanor/Luke
| List of key attendees drawn up | Luke/Martin/Sam/Partnerships/Martin G
| Aesthetica have statement in place for what the film festival for Substance will contain in terms of themes | Liam/Cherie
2017-08-28
2017-08-29 | Contract/MOU as many partners as possible | Martin/Liam
2017-08-31 | Hull 2017 Programme Announcement
| Invites land to key attendees/Save the Date | Eleanor/Luke
| Tickets on sale for FF | Martin/Luke/Eleanor
2017-09-04 | Update from Aesthetica about Film Festival | Liam/Cherie/HIC
| Marketing/PR plan for Substance complete | Rachel/Ben/Luke/Martin
| Venues secured at Vue for Film Festival | Liam/HIC
2017-09-11 | Hotels and travel booked for all those required | Martin/Luke/Liam/Liz
Invites land to key attendees/Save the Date
2017-09-18 | First draft Press Release | Ben/Martin/Luke/Sam |  | This is a starter for 10 date. Does this all want to be announced in November during Short Film Fest? Just seems a little late.
2017-09-25 | Press Release complete for Substance Festival. Hull Venue/Film Festival. | Ben/Martin/Luke/Sam
2017-10-02 | Announce all other panelists and partners for FF | Luke
Contract/MOU as many partners as possible
| Films and panel discussions on sale for Substance | Liam/Cherie
| Tickets on sale for Hull Venue Performance | Martin/Chris/Eleanor/Box Office
| Marketing Materials for Substance FF complete | Rachel/Luke/Martin/Sam
2017-10-09 | Final Budget for Hull Venue Project finalised. Tender decided. | Chris/Sam/Martin
2017-10-16 | Final Budget for Substance FF finalised | Martin
2017-10-23
2017-10-30
2017-11-06 | Aesthetica Short Film Festival York: Substance moment to happen in here. Or trailer to advertise Substance | Liam/Cherie/Luke/Martin/Sam
| Update Hotel bookings | Martin/Luke/Liam
2017-11-13
2017-11-20
2017-11-27
2017-11-29 | An evening with Reece Shearsmith | Hull Uni/Cherie
2017-12-04
2017-12-05 | Install at the Venue | Aidan/Chris/Company
2017-12-06 | Install at the Venue | Aidan/Chris/Company
2017-12-07 | Substance Future Forum | All Project Team
Install/Dress Run at the Venue
2017-12-08 | Performance at The Venue
2017-12-09 | Performance at The Venue
2017-12-10 | Performance at The Venue
2017-12-11 | Get Out at The Venue | Aidan/Chris/Company
2017-12-18