Traffic and Waste Management Update
30/01/2017

Attending:

Chris Clay

Helen Thackeray

Melissa McVeigh

Apologies: Jonathon Black

| POINT | ACTION |
| --- | --- |
| 1. Traffic Management |  |
| CC suggested using a Transport Management company in Beverley who are on an East Riding Framework – avoid procurement regulations CC to meet with Kerry Ryan, Local transport projects, Stagecoach and EYMS on Wednesday 01/02/2017 HT to meet with fencing company CC to chase Liz Draper for contact at Sewell’s for Groundwork for buses Sustrans – Suggestion to cycle to Park and Ride. To be discussed once the Park and Ride points have been identified | CC HT CC |
| 2. Security |  |
| BBC security plan for Exeter 2016 – security patrol around the fence and manage the bus queues and arrival/departure points Designate Premise Supervisor before next SAG meeting CC confirmed Showsec as Security and Stewarding company of choice CC to share contact details and MM to complete Addendum. | ALL CC |
| 3. Procurement |  |
| Contract states Hull 2017 provides medical, however BBC will be recharging for marquee RFQ - Waste Management due back 08/01/2017 RFQ - Medical due back 10/01/2017 RFQ - Welfare to be discussed RFQ - H&S – MM to issue, CC budgeted at 10 day’s work @ £350 per day. CC and MM to compile list of H&S companies MM / HT / CC to go through RFQs w/c 13th February |  |
| 4. Noise Management |  |
| Noise Management – CC to pick this up |  |
| 5. Volunteer Requirement |  |
| HT suggested using volunteers to distribute Yorkshire Cancer research wristbands, give them out at Park and Ride points |  |
| 6. Resident Liaison |  |
| Will at ERC to be confirmed as resident liaison (renaissance team) Next resident liaison to include more concrete information |  |