## production schedule
DAY/DATE | TIME | DETAIL | NOTES | WHO | COMPANY | CREW REQD | VEHICLES
Fri 28th April | am | collect water from staples |  | AL | TGE | 0 | Van
| am | groundworks to path | 20t of grit being layed |  | PBS construction |  | 2 x trucks
| pm | Pick up Radios | Council Guild hall store? Collect additional hired comms from Pacific exchange | AL/GH |  | 0
| pm | Pick up welfare Gear | Water, Tea, Coffee, Urn, Cups etc | AL/GH |  | 0
| pm | Barriers delivered to site | Adam to locate | AL/GH | Actavo | 0 | 18t Hiab
| pm | Bins delivered | put near production compound |  | Council | 0 | 3.5t pick up
| pm | do site walk round with parks |  | AL/GH | HCAL
Sat 29th April | 800 | Adam on site | Provisional mark out | AL | TGE | 0 | Van
| 800 | Gareth on Site | To sort crates | GH |  | 0 | Van
| 900 | Production toilets delivered | 6 single units |  | Add Plant | 0 | Car & trailer
| am | Crates arrive | Gareth to sort & brief Adam on battery changeover | GH | Walk The Plank |  | Flatbed
| 900 | Crew on site | Adam to Brief | AL | Music Consortium | 2
| 900 | Telehandler delivered |  |  | Add Plant | 0 | 18t flatbed
| 930 | Fence off production compound | followed by show site compound | Crew | Music Consortium | 2
| 1000 | Marquee company onsite | Build Production tent |  | Nationwide | 0 | 7.5t flatbed
| 1000 | Generators delivered | Adam to locate |  | John F Hunts/FTS | 0 | Artic
| 1100 | Distribute Gens | Set-up | AL | TGE | 0 | telehandler
| 1200 | Distro delivered | Drop near build compound |  | IDE Rental | 2
| 1300 | LUNCH |  |  | ALL | ALL
| 1400 | Continue gens & Install heavy power |  | AL | TGE | 2 | Telehandler
| pm | Periplum truck arrives | Park near production compound |  | Periplum | 0 | 7.5t box
| 1600 | Set-up production compound |  | crew |  | 2
| 1800 | Crew finish |  |  |  | 0
| 1800 | Security onsite | Adam to brief |  | Prestige | 0
| 1800 | begin mains testing | Do all distro and spikes | AL |  | 0
| 2030 | Park Closes | turn off crates and charge batteries | AL
Sun 30th April | 800 | security changeover |  |  | Prestige
| 800 | Adam on site | replace batteries, in crate, and turn on | AL |  |  | Van
| 900 | Periplum on site |  |  | Periplum |  | 3 x cars & van
| 900 | Crew on site |  |  | Music Consortium | 4
| 900 | Unload truck & set build |  |  | Periplum | 4
| 900 | Freelancers on site |  |  |  | 2
| 1000 | Lighting delivered |  | JG | Nitelites | 2 | 18t box
| 1200 | Begin LX rig |  | JG | Freelancers | 2
| 1300 | LUNCH
| 1400 | sound & FOH delivered |  | AL + 2 x TMC | 3d productions | 2 x TMC | 18t box
| 1400 | Continue LX rig |  | JG | freelancers | 2
| 1400 | Begin festoon install |  | AL + 2 x TMC | Music consortium | 2
| 1400 | Rehearsals | Performers only |  | Periplum
| 1400 | Distribute extinguishers |  | AL
| 1700 | Crew finish |  |  | Music Consortium | 4
| 1800 | Dinner | tech staff | JG, AL, Freelancers
| 1800 | Participant performers arrive | briefed by Periplum | LY | Periplum
| 1800-2100 | partricipant workshop |  | LY | Periplum
| 1800 | security changeover |  |  | Prestige
| 1900 | Begin LX focus | plot when finished
| 2030 | Park closes | turn off crates and charge batteries | AL | HCAL
| 2100 | Light fires van arrives | park in compound, brief security |  | Lightfires |  | LWB van
| 2300 | Finish - Plotting may continue | Handover to security | All | All
Mon 1st April | 800 | security changeover |  |  | Prestige
| 800 | Adam on site | replace batteries, in crate, and turn on | AL |  |  | Van
| 900 | toilets serviced |  |  | AddPlant
| 900 | Periplum on site |  |  |  |  | 3 x cars & van
| 900 | Unload pyro van | into safe working areas |  | Periplum/lightfires
| 900 | Continue & finish festoon |  | AL | Freelancers | 2
| 1000 | Prouction meeting | pavillion? | AL, GH, KF, MM, EB
| 1200 | Lunch |  | All | All
| 1300 | sound on site | begin set-up |  | 3d/HPSS | 2 freelancers | van/car
| 1300 | performers on site | walk through and continue set-build | LY | Periplum
| 1445 | set props | & slow walk through |  | Periplum
| 1700 | Low level sound test |  |  | 3d/HPSS/periplum
| 1700 | Dinner |  |  | All
| 1730 | participants - arrive | Meeting & workshop | LY | Periplum
| 1800 | continue LX & sound |  |  | 3d/HPSS | 2 freelancers
| 1800 | security changeover |  |  | Prestige
| 1800 | Medical on site |  |  | Heart medical |  | car
| 1830-1915 | Participant run through |  | LY | Periplum
| 2000 | final rough plot |  | JG | Periplum
| 2030 | Park shuts | turn off crates and charge batteries | AL
| 2100 | Standby for run through |  | All | All
| 2115 | Runthrough | No horse and carriage | All | All
| 2130 | Run through continues at Arena |  | All | All
| 2230 | Site lighting test |  | AL, GH
| 2300 | Finish - Plotting may continue | Handover to security | All | All
Tues 2nd May | 800 | security changeover |  |  | Prestige
| 800 | Adam on site | replace batteries, in crate, and turn on | AL |  |  | Van
| 900 | Continue as required |  | AL |  | 1 freelancer
| 1000 | Lightfires on site | Prep pyro |  | Lightfires/Periplum |  | Van
| 1000 | Prouction meeting | pavillion? | AL, GH, KF, MM, EB
| 1200 | Company meeting | inc notes. AL to feed notes from earlier meeting |  | Periplum
| 1300-1400 | Tech lunch
| 1300 | Performers set props
| 1400 | continue tech work as required |  | AL |  | 1 freelancer
| 1430 | Walk through | with full sound |  | Periplum + 3d/HPSS
| 1700 | Dinner |  |  | All
| 1730 | participants - arrive | Meeting & workshop | LY | Periplum
| 1800 | security changeover |  |  | Prestige
| 1800 | Medical on site |  |  | Heart medical |  | car
| 1830 | Participants run through | inc fire torches | LY
| 1900 | Horse & carriage arrive on site |  |  | KRM carriages |  | 7.5t box
| 1930 | pre show routine | mics, warm-ups, make-up and costume |  | Periplum
| 1945 | Stewards/security briefing | Prestige supervisor to attend with Gareth and volunteer co-ordinator | GH, AL | Periplum
| 2000 | Park shuts | turn off crates and charge batteries | AL | HCAL
| 2000 | Horse & Carriage rehearsal |  |  | Periplum, KRM
| 20:30 | Volunteers arrive for briefing |  | SH/MM/EB
| 2115 | Tech/Dress Rehearsal |  | All | All
| 2230 | Rehearsal finish | Pack up, secure & turn off | All | All
| 2300 | Finish - Plotting may continue | Handover to security | All | All
Weds 3rd May | 800 | security changeover |  |  | Prestige
| 800 | Cleansing on site | Clean main arena | Council
| 800 | Adam on site | replace batteries, in crate, and turn on | AL |  |  | Van
| 900 | Public toilets delivered, production toilets serviced | Adam to site | AL | Add plant
| 1000 | Crew on site | Tidy & prep for show, install show signage | AL | Music consortium
| 1000 | Lightfires on site | Prep pyro |  | Lightfires/Periplum |  | Van
| 1000 | Prouction meeting | pavillion? | AL, GH, KF, MM, EB
| 1200 | Lunch/Company meeting | inc notes. AL to feed notes from earlier meeting |  | Periplum
| 1300 | Performers set props
| 1400 | continue tech work as required |  | AL |  | 1 freelancer
| 1430 | Walk through | with full sound |  | Periplum + 3d/HPSS
| 1700 | Dinner |  |  | All
| 1730 | Mallet Lambert steward on site | Gareth to brief | GH | Prestige
| 1730 | participants - arrive | Meeting & workshop | LY | Periplum
| 1800 | 2 x medics on site |  |  | Heart medical
| 1830 | Participants run through | inc fire torches | LY
| 1900 | Horse & carriage arrive on site |  |  | KRM carriages
| 1900 | Pre show checks |  | AL | Periplum, TGE, 3D | 1 freelancer
| 19:30 | Volunteers on site | briefed by volunteer co-ordinator | SH
| 1930 | pre show routine | mics, warm-ups, make-up and costume |  | Periplum
| 1930 | Stewards/security briefing | Gareth to brief all stewards, then send out | GH, AL | Prestige
| 2000 | Medical on site |  |  | Heart medical
| 2000 | Park closes | turn off crates and charge batteries | AL | HCAL
| 2000 | Horse & carriage outside park | 1 hour max |  | KRM carriages
| 2000 | Event control operational | inc lost kids | ?? | Hull 17
| 2000 | Volunteers sent out to positions | wayfinding/gates etc | SH
| 2045 | GATES OPEN
| 2115 | SHOW
| 2215 | SHOW FINISH | pack up |  | Periplum
| 2215 | secure and waterproof | Barrier off where required | AL | 3d | freelancer
| 2230 | Clear site & close gates | secure and waterproof |  | Prestige
| 2300 | Final sweep & lock gates |  |  | Prestige
| 2300 | Finish |  |  | All
| 2330 | security changeover |  |  | Prestige
Thurs 4th | 800 | security changeover |  |  | Prestige
| 800 | Cleansing on site | Clean main arena | Council
| 800 | Adam on site | check fuel and site, replace batteries, in crate, and turn on | AL |  |  | Van
| 900 | Toilets serviced |  |  | Add plant
| 1000 | Lightfires on site | Prep pyro |  | Lightfires/Periplum |  | Van
| 1000 | Prouction meeting | pavillion? | AL, GH, KF, MM, EB
| 1200 | Lunch/Company meeting | inc notes. AL to feed notes from earlier meeting |  | Periplum
| 1300 | on site rehearsals as required |  |  | Periplum
| 1430 | Walk through | with full sound |  | Periplum + 3d/HPSS
| 1700 | Dinner |  |  | All
| 1730 | Mallet Lambert steward on site | Gareth to brief | GH | Prestige
| 1730 | participants - arrive | Meeting & workshop | LY | Periplum
| 1800 | 2 x medics on site |  |  | Heart medical
| 1830 | Participants run through | inc fire torches | LY
| 1900 | Horse & carriage arrive on site |  |  | KRM carriages
| 1900 | Pre show checks |  | AL | Periplum, TGE, 3D | 1 freelancer
| 19:30 | Volunteers on site | briefed by volunteer co-ordinator | SH
| 1930 | pre show routine | mics, warm-ups, make-up and costume |  | Periplum
| 1930 | Stewards/security briefing | Gareth to brief all stewards, then send out | GH, AL | Prestige
| 2000 | Medical on site |  |  | Heart medical
| 2000 | Park closes | turn off crates and charge batteries | AL | HCAL
| 2000 | Horse & carriage outside park | 1 hour max |  | KRM carriages
| 2000 | Event control operational | inc lost kids | ?? | Hull 17
| 2000 | Volunteers sent out to positions | wayfinding/gates etc | SH
| 2045 | GATES OPEN
| 2115 | SHOW
| 2215 | SHOW FINISH | pack up |  | Periplum
| 2215 | secure and waterproof | Barrier off where required | AL | 3d | freelancer
| 2230 | Clear site & close gates | secure and waterproof |  | Prestige
| 2300 | Final sweep & lock gates |  |  | Prestige
| 2300 | Finish |  |  | All
| 2330 | security changeover |  |  | Prestige
Fri 5th May | 800 | security changeover |  |  | Prestige
| 800 | Cleansing on site | Clean main arena | Council
| 800 | Adam on site | check fuel and site, replace batteries, in crate, and turn on | AL |  |  | Van
| 900 | Toilets serviced |  |  | Add plant
| 900 | Re-fuel gens | if required | AL | John F Hunts
| 1000 | Lightfires on site | Prep pyro |  | Lightfires/Periplum |  | Van
| 1000 | Prouction meeting | pavillion? | AL, GH, KF, MM, EB
| 1200 | Lunch/Company meeting | inc notes. AL to feed notes from earlier meeting |  | Periplum
| 1300 | on site rehearsals as required |  |  | Periplum
| 1300 | And Now production meeting | with Mandy | AL
| 1430 | Walk through | with full sound |  | Periplum + 3d/HPSS
| 1700 | Dinner |  |  | All
| 1730 | Mallet Lambert steward on site | Gareth to brief | GH | Prestige
| 1730 | participants - arrive | Meeting & workshop | LY | Periplum
| 1800 | 2 x medics on site |  |  | Heart medical
| 1830 | Participants run through | inc fire torches | LY
| 1900 | Horse & carriage arrive on site |  |  | KRM carriages
| 1900 | Pre show checks |  | AL | Periplum, TGE, 3D | 1 freelancer
| 19:30 | Volunteers on site | briefed by volunteer co-ordinator | SH
| 1930 | pre show routine | mics, warm-ups, make-up and costume |  | Periplum
| 1930 | Stewards/security briefing | Gareth to brief all stewards, then send out | GH, AL | Prestige
| 2000 | Medical on site |  |  | Heart medical
| 2000 | Park closes | turn off crates and charge batteries | AL | HCAL
| 2000 | Horse & carriage outside park | 1 hour max |  | KRM carriages
| 2000 | Event control operational | inc lost kids | ?? | Hull 17
| 2000 | Volunteers sent out to positions | wayfinding/gates etc | SH
| 2045 | GATES OPEN
| 2115 | SHOW
| 2215 | SHOW FINISH | pack up |  | Periplum
| 2215 | secure and waterproof | Barrier off where required | AL | 3d | freelancer
| 2230 | Clear site & close gates | secure and waterproof |  | Prestige
| 2300 | Final sweep & lock gates |  |  | Prestige
| 2300 | Finish |  |  | All
| 2330 | security changeover |  |  | Prestige
Sat 6th May | 800 | security changeover |  |  | Prestige
| 800 | Cleansing on site | Clean main arena | Council
| 800 | Adam on site | check fuel and site, replace batteries, in crate, and turn on | AL |  |  | Van
| 900 | Toilets serviced |  |  | Add plant
| 1000 | Lightfires on site | Prep pyro |  | Lightfires/Periplum |  | Van
| 1000 | Prouction meeting | pavillion? | AL, GH, KF, MM, EB
| 1200 | Lunch/Company meeting | inc notes. AL to feed notes from earlier meeting |  | Periplum
| 1300 | on site rehearsals as required |  |  | Periplum
| 1430 | Walk through | with full sound |  | Periplum + 3d/HPSS
| 1700 | Dinner |  |  | All
| 1730 | Mallet Lambert steward on site | Gareth to brief | GH | Prestige
| 1730 | participants - arrive | Meeting & workshop | LY | Periplum
| 1800 | 2 x medics on site |  |  | Heart medical
| 1830 | Participants run through | inc fire torches | LY
| 1900 | Horse & carriage arrive on site |  |  | KRM carriages
| 1900 | Pre show checks |  | AL | Periplum, TGE, 3D | 1 freelancer
| 19:30 | Volunteers on site | briefed by volunteer co-ordinator | SH
| 1930 | pre show routine | mics, warm-ups, make-up and costume |  | Periplum
| 1930 | Stewards/security briefing | Gareth to brief all stewards, then send out | GH, AL | Prestige
| 2000 | Medical on site |  |  | Heart medical
| 2000 | Park closes | turn off crates and charge batteries | AL | HCAL
| 2000 | Horse & carriage outside park | 1 hour max |  | KRM carriages
| 2000 | Event control operational | inc lost kids | ?? | Hull 17
| 2000 | Volunteers sent out to positions | wayfinding/gates etc | SH
| 2045 | GATES OPEN
| 2115 | SHOW
| 2215 | SHOW FINISH | pack up |  | Periplum
| 2230 | Clear site & close gates |  |  | Prestige
| 2230 | Start get-out | all Periplum all sound and start lighting | AL | Periplum, 3d/HPSS | 4 crew, 1 freelancer
| 2300 | Final sweep & lock gates |  |  | Prestige
| 2330 | security changeover |  |  | Prestige
| 230 | Finish get out |  |  | All
Sun 7th May | 800 | security changeover |  |  | Prestige
| 900 | Continue get-out | Lighting first |  | 3d/HPSS | 2 x crew, 2 freelancers
| 900 | power get-out |  | AL |  | 2 x crew
| 900 | Public toilets collected |  |  | Addplant |  | vehicle and trailer
| am | clear production tent and pavillion | into Adams van | AL
| 1300 | LUNCH
| 1400 | Lighting collected | inc FOH |  | 3d/HPSS | 2 x crew, 2 freelancers | 18t
| 1400 | De-rig signs |  |  |  | 2 x crew
| 1400 | Marquee de-rigged |  |  |  | 4 crew
| 1500 | Tidy all barriers
| 1500 | Generators collected |  | Al | John F Hunts |  | 18t Hiab
| 1500 | Distro collected | telehandler required | AL | IDE |  | 3.5t
| 1500 | Backstage toilets collected |  |  | Addplant |  | vehicle and trailer
| 1600 | Final tidy - groundguards, barriers etc | leave for Monday collection
| 1700 | telehandler collected |  |  | Addplant |  | 18t
| 2000 | security finished |  |  | Prestige
Mon 8th May | am | return Radios | Council Guild hall store? return additional hired comms from Pacific exchange | AL |  | 0
|  | return welfare Gear | Water, Tea, Coffee, Urn, Cups etc | AL |  | 0
|  | Barriers collected |  | AL | Actavo/all occasions | 0 | 18t Hiab
|  | Bins collected | put near production compound |  | Council | 0 | 3.5t pick up

## production contacts
NAME | COMPANY | WHAT | MOBILE NUMBER
Adam Long | TGE | Prodction manager | 07754 728316
Katy Fuller | Hull 17 | Exec producer | 07771 764656
Gareth Hughes | Hull 17 | Event manager | 07733 112272
Maddie Maughan | Hull 17 | Producer | 07738 822568
Louise Yates | Hull 17 | Producer | 07753 171181
Elizabeth Bergeron | Hull 17 | Producer | 07702 922475
Sarah Harris | Hull 17 | Volunteer co-ordinator
Steve McKee | Hull cc | Cleansing | 07789 372506
Claire Rafferty | Periplum | Director | 07867 794158
Damien | Periplum | Director
Johnny Goodwin |  | LD | 07850 745475
Howard | HCAL | Parks
Sound engineer
audio hire
Lighting hire
Brian | Nationwide | Marquee Hire | 07775 515398
Dave Rogers | IDE | Distro Hire | 01543 574111
Jean Byers | John F Hunt | Generators | 0191 4111200
|  | Barriers & fencing | 0844 870 9802
Paul | Heart Medical | Medical | 07764 926970
Justine peacocock | Prestige | Stewarding & child protection | 07886 838597
Jon Masters | Add Plant | toilets & plant | 07738 817940
Rona | The Music consortium | local crew
??? | Freelancer
??? | Freelancer