## PILOT PHASE
MONITORING & EVALUATION DELIVERY PLAN
NAME OF ORGANISATION | Hull UK City of Culture 2017 Limited
NAME OF PROJECT/EVENT | Land of Green Ginger
MONITORING & EVALUATION
|  |  | W/C 14 NOVEMBER | [6 empty] | W/C 21 NOVEMBER | [6 empty] | W/C 28 NOVEMBER | [6 empty] | W/C 5 DECEMBER | [6 empty] | W/C 12 DECEMBER | [6 empty] | W/C 19 DECEMBER | [6 empty] | W/C 26 DECEMBER | [6 empty] | W/C 2 JANUARY | [6 empty] | W/C 9 JANUARY | [6 empty] | W/C 16 JANUARY | [6 empty] | W/C 23 JANUARY | [6 empty] | W/C 30 JANUARY | [6 empty] | W/C 6 FEBRUARY | [6 empty] | W/C 13 FEBRUARY
ACTIVITY | RESPONSIBILITY | RESPONDENTS | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su
PROJECT MONITORING SHEET
Creative team to complete Equal Opps Form | NH / LH | n/a | bar: W/C 5 DECEMBER F
Commissioned artists to complete Equal Opps Form | NH / LH | n/a | bar: W/C 5 DECEMBER F
Populate sheet with existing data | NH / LH | n/a | bar: W/C 12 DECEMBER M to W/C 12 DECEMBER W
Enter data into sheet for the previous week | NH / LH | n/a | bar: W/C 19 DECEMBER M; W/C 26 DECEMBER M; W/C 2 JANUARY M; W/C 9 JANUARY M
Submit completed sheet to EU | NH / LH | n/a | bar: W/C 9 JANUARY F
AUDIENCE RESEARCH
Pilot project observational research | EU | n/a | bar: W/C 14 NOVEMBER T
Write up and code observational research | FB & MLS | n/a | bar: W/C 14 NOVEMBER F
| FB & MLS | n/a | bar: W/C 28 NOVEMBER T
| EU, FB | n/a | bar: W/C 5 DECEMBER M
| EU & PB | n/a | bar: W/C 5 DECEMBER F
| EU & PB | n/a | bar: W/C 12 DECEMBER F
| Information by Design | Sample of attenders | bar: W/C 12 DECEMBER M to W/C 23 JANUARY M
| Information by Design | n/a | bar: W/C 23 JANUARY W
| Information by Design | n/a | bar: W/C 30 JANUARY F
| Regeneris | n/a | bar: W/C 6 FEBRUARY M to W/C 13 FEBRUARY Su
EXPERENTIAL / EMOTIVE DATA CAPTURE
Pre-recruit 4 groups | Regeneris | n/a | bar: W/C 12 DECEMBER M to W/C 12 DECEMBER W
Partners (guided tour) | Regeneris | Partners | bar: W/C 12 DECEMBER M to W/C 12 DECEMBER W
Group 2 | Regeneris | Hull residents | bar: W/C 12 DECEMBER M to W/C 12 DECEMBER W
Group 3 | Regeneris | Hull residents | bar: W/C 12 DECEMBER M to W/C 12 DECEMBER W
Group 4 | Regeneris | East Riding residents | bar: W/C 12 DECEMBER M to W/C 12 DECEMBER W
Select data capture methodology for groups | Regeneris, EU, PB | n/a | bar: W/C 5 DECEMBER W to W/C 5 DECEMBER Su
Fieldwork | TBC | As above | bar: W/C 26 DECEMBER Su to W/C 9 JANUARY M
Analysis of data | TBC | n/a | bar: W/C 9 JANUARY T to W/C 16 JANUARY F
CREATIVE CORE TEAM SURVEY
Design pre-event survey | Regeneris, EU, PB | n/a | bar: W/C 28 NOVEMBER W to W/C 28 NOVEMBER F
Design post-event survey | Regeneris, EU, PB | n/a | bar: W/C 28 NOVEMBER W to W/C 28 NOVEMBER F
Deliver pre-event Survey | Regeneris | Creative Core Team (see 'Notes' below)
Deliver post- event Survey | Regeneris | Creative Core Team (see 'Notes' below)
Analysis of data | Regeneris | n/a
CREATIVE CORE TEAM DEPTH DISCUSSION GROUP
Design discussion group guide for pre-event | Regeneris, EU, PB | n/a | bar: W/C 28 NOVEMBER W to W/C 28 NOVEMBER F
Design discussion group guide for post-event | Regeneris, EU, PB | n/a | bar: W/C 28 NOVEMBER W to W/C 28 NOVEMBER F
Pre-event discussion group | Regeneris | Creative Core Team (see 'Notes' below)
Post-event discussion group | Regeneris | Creative Core Team (see 'Notes' below)
Analysis of data | Regeneris | n/a
ARTIST & HERITAGE PARTNER INTERVIEWS
Design discussion guide for pre-event | Regeneris, EU, PB | n/a | bar: W/C 28 NOVEMBER W to W/C 28 NOVEMBER F
Design discussion guide for post-event | Regeneris, EU, PB | n/a | bar: W/C 28 NOVEMBER W to W/C 28 NOVEMBER F
Pre-event depth interviews | Regeneris | Artists, Heritage Partners (see 'Notes' below)
Post-event depth interviews | Regeneris | Artists, Heritage Partners (see 'Notes' below)
Analysis of data | Regeneris | n/a
PEER SURVEY
Design pre-event survey | Regeneris, EU, PB | n/a | bar: W/C 28 NOVEMBER W to W/C 28 NOVEMBER F
Design post-event survey | Regeneris, EU, PB | n/a | bar: W/C 28 NOVEMBER W to W/C 28 NOVEMBER F
Pre-event Survey | Regeneris | Peer - TBC
Post-event Survey | Regeneris | Peer - TBC
Analysis of data | Regeneris | n/a
PEER DEPTH INTERVIEWS
Design discussion guide for pre-event | Regeneris, EU, PB | n/a | bar: W/C 28 NOVEMBER W to W/C 28 NOVEMBER F
Design discussion guide for post-event | Regeneris, EU, PB | n/a | bar: W/C 28 NOVEMBER W to W/C 28 NOVEMBER F
Pre-event depth interviews | Regeneris | Peer - TBC
Post-event depth interviews | Regeneris | Peer - TBC
Analysis of data | Regeneris | n/a
DELIVERY PARTNER SURVEY
Design post-event survey | Regeneris, EU, PB | n/a | bar: W/C 28 NOVEMBER W to W/C 28 NOVEMBER F
Post-event Survey | Regeneris | Delivery Partners (see 'Notes' below)
Analysis of data | Regeneris | n/a
MEDIA & PR
Media Monitoring | AJ & Gorkana | n/a | bar: W/C 21 NOVEMBER T to W/C 9 JANUARY Su
Media Analysis | AJ & Gorkana | n/a | bar: W/C 21 NOVEMBER T to W/C 16 JANUARY F
PR Report | BMc & PR Company | n/a | bar: W/C 23 JANUARY M to W/C 23 JANUARY W
DOCUMENTING
Design vox pops questions | Regeneris, EU, PB | n/a | bar: W/C 5 DECEMBER W to W/C 5 DECEMBER F
Design brief for film documentation | TBC | n/a
Filming | Contracted filmographer | All audiences, TBC
Editing | Contracted filmographer | n/a
Provide raw footage | Contracted filmographer | n/a
Provide edited cut | Contracted filmographer | n/a
PROJECT DEBRIEF
Design agenda | NH / LH | n/a
Debrief meeting | NH / LH
Analysis | Regeneris | n/a
NOTES
Creative Core Team | Niccy Halifax
Sean McAlister
Rupert Creed
Ala Lloyd
Durham Marenghi
Dan Jones
Artists | Zsolt Balogh
Chris Hees
Helga Gift
Sodium
Invisible Flock
Preston Likely
MakeAMPLIFY
Jesse Kanda
Imitating the Dog
Quentin Budworth
Urban Projections
Heritage partners | Yorkshire Film Archives
Pathe
BFI
Huntley Film Archives
Hull History Centre
John Frost
Hull Maritime Museum
Hull History Museum
Delivery Partners | Hull City Council
Ground Control
VHEY
Hull Daily Mail
Daily Express
BBC Look North
Warren Centre
Open Doors
Hull Libraries Service
Hull Culture & Leisure

## MAIN PHASE
MONITORING & EVALUATION DELIVERY PLAN
NAME OF ORGANISATION | Hull UK City of Culture 2017 Limited
NAME OF PROJECT/EVENT | Land of Green Ginger
MONITORING & EVALUATION
|  |  | W/C 14 NOVEMBER | [6 empty] | W/C 21 NOVEMBER | [6 empty] | W/C 28 NOVEMBER | [6 empty] | W/C 5 DECEMBER | [6 empty] | W/C 12 DECEMBER | [6 empty] | W/C 19 DECEMBER | [6 empty] | W/C 26 DECEMBER | [6 empty] | W/C 2 JANUARY | [6 empty] | W/C 9 JANUARY | [6 empty] | W/C 16 JANUARY | [6 empty] | W/C 23 JANUARY | [6 empty] | W/C 30 JANUARY | [6 empty] | W/C 6 FEBRUARY | [6 empty] | W/C 13 FEBRUARY
ACTIVITY | RESPONSIBILITY | RESPONDENTS | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su
PROJECT MONITORING SHEET
Creative team to complete Equal Opps Form | NH / LH | n/a | bar: W/C 5 DECEMBER F
Commissioned artists to complete Equal Opps Form | NH / LH | n/a | bar: W/C 5 DECEMBER F
Populate sheet with existing data | NH / LH | n/a | bar: W/C 12 DECEMBER M to W/C 12 DECEMBER W
Enter data into sheet for the previous week | NH / LH | n/a | bar: W/C 19 DECEMBER M; W/C 26 DECEMBER M; W/C 2 JANUARY M; W/C 9 JANUARY M
Submit completed sheet to EU | NH / LH | n/a | bar: W/C 9 JANUARY F
AUDIENCE RESEARCH
Pilot project observational research | EU | n/a | bar: W/C 14 NOVEMBER T
Write up and code observational research | FB & MLS | n/a | bar: W/C 14 NOVEMBER F
| FB & MLS | n/a | bar: W/C 28 NOVEMBER T
| EU, FB | n/a | bar: W/C 5 DECEMBER M
| EU & PB | n/a | bar: W/C 5 DECEMBER F
| EU & PB | n/a | bar: W/C 12 DECEMBER F
| Information by Design | Sample of attenders | bar: W/C 12 DECEMBER M to W/C 23 JANUARY M
| Information by Design | n/a | bar: W/C 23 JANUARY W
| Information by Design | n/a | bar: W/C 30 JANUARY F
| Regeneris | n/a | bar: W/C 6 FEBRUARY M to W/C 13 FEBRUARY Su
EXPERENTIAL / EMOTIVE DATA CAPTURE
Pre-recruit 4 groups | Regeneris | n/a | bar: W/C 12 DECEMBER M to W/C 12 DECEMBER W
Partners (guided tour) | Regeneris | Partners | bar: W/C 12 DECEMBER M to W/C 12 DECEMBER W
Group 2 | Regeneris | Hull residents | bar: W/C 12 DECEMBER M to W/C 12 DECEMBER W
Group 3 | Regeneris | Hull residents | bar: W/C 12 DECEMBER M to W/C 12 DECEMBER W
Group 4 | Regeneris | East Riding residents | bar: W/C 12 DECEMBER M to W/C 12 DECEMBER W
Select data capture methodology for groups | Regeneris, EU, PB | n/a | bar: W/C 5 DECEMBER W to W/C 5 DECEMBER Su
Fieldwork | TBC | As above | bar: W/C 26 DECEMBER Su to W/C 9 JANUARY M
Analysis of data | TBC | n/a | bar: W/C 9 JANUARY T to W/C 16 JANUARY F
CREATIVE CORE TEAM SURVEY
Design pre-event survey | Regeneris, EU, PB | n/a | bar: W/C 28 NOVEMBER W to W/C 28 NOVEMBER F
Design post-event survey | Regeneris, EU, PB | n/a | bar: W/C 28 NOVEMBER W to W/C 28 NOVEMBER F
Deliver pre-event Survey | Regeneris | Creative Core Team (see 'Notes' below)
Deliver post- event Survey | Regeneris | Creative Core Team (see 'Notes' below)
Analysis of data | Regeneris | n/a
CREATIVE CORE TEAM DEPTH DISCUSSION GROUP
Design discussion group guide for pre-event | Regeneris, EU, PB | n/a | bar: W/C 28 NOVEMBER W to W/C 28 NOVEMBER F
Design discussion group guide for post-event | Regeneris, EU, PB | n/a | bar: W/C 28 NOVEMBER W to W/C 28 NOVEMBER F
Pre-event discussion group | Regeneris | Creative Core Team (see 'Notes' below)
Post-event discussion group | Regeneris | Creative Core Team (see 'Notes' below)
Analysis of data | Regeneris | n/a
ARTIST & HERITAGE PARTNER INTERVIEWS
Design discussion guide for pre-event | Regeneris, EU, PB | n/a | bar: W/C 28 NOVEMBER W to W/C 28 NOVEMBER F
Design discussion guide for post-event | Regeneris, EU, PB | n/a | bar: W/C 28 NOVEMBER W to W/C 28 NOVEMBER F
Pre-event depth interviews | Regeneris | Artists, Heritage Partners (see 'Notes' below)
Post-event depth interviews | Regeneris | Artists, Heritage Partners (see 'Notes' below)
Analysis of data | Regeneris | n/a
PEER SURVEY
Design pre-event survey | Regeneris, EU, PB | n/a | bar: W/C 28 NOVEMBER W to W/C 28 NOVEMBER F
Design post-event survey | Regeneris, EU, PB | n/a | bar: W/C 28 NOVEMBER W to W/C 28 NOVEMBER F
Pre-event Survey | Regeneris | Peer - TBC
Post-event Survey | Regeneris | Peer - TBC
Analysis of data | Regeneris | n/a
PEER DEPTH INTERVIEWS
Design discussion guide for pre-event | Regeneris, EU, PB | n/a | bar: W/C 28 NOVEMBER W to W/C 28 NOVEMBER F
Design discussion guide for post-event | Regeneris, EU, PB | n/a | bar: W/C 28 NOVEMBER W to W/C 28 NOVEMBER F
Pre-event depth interviews | Regeneris | Peer - TBC
Post-event depth interviews | Regeneris | Peer - TBC
Analysis of data | Regeneris | n/a
DELIVERY PARTNER SURVEY
Design post-event survey | Regeneris, EU, PB | n/a | bar: W/C 28 NOVEMBER W to W/C 28 NOVEMBER F
Post-event Survey | Regeneris | Delivery Partners (see 'Notes' below)
Analysis of data | Regeneris | n/a
MEDIA & PR
Media Monitoring | AJ & Gorkana | n/a | bar: W/C 21 NOVEMBER T to W/C 9 JANUARY Su
Media Analysis | AJ & Gorkana | n/a | bar: W/C 21 NOVEMBER T to W/C 16 JANUARY F
PR Report | BMc & PR Company | n/a | bar: W/C 23 JANUARY M to W/C 23 JANUARY W
DOCUMENTING
Design vox pops questions | Regeneris, EU, PB | n/a | bar: W/C 5 DECEMBER W to W/C 5 DECEMBER F
Design brief for film documentation | TBC | n/a
Filming | Contracted filmographer | All audiences, TBC
Editing | Contracted filmographer | n/a
Provide raw footage | Contracted filmographer | n/a
Provide edited cut | Contracted filmographer | n/a
PROJECT DEBRIEF
Design agenda | NH / LH | n/a
Debrief meeting | NH / LH
Analysis | Regeneris | n/a
NOTES
Creative Core Team | Niccy Halifax
Sean McAlister
Rupert Creed
Ala Lloyd
Durham Marenghi
Dan Jones
Artists | Zsolt Balogh
Chris Hees
Helga Gift
Sodium
Invisible Flock
Preston Likely
MakeAMPLIFY
Jesse Kanda
Imitating the Dog
Quentin Budworth
Urban Projections
Heritage partners | Yorkshire Film Archives
Pathe
BFI
Huntley Film Archives
Hull History Centre
John Frost
Hull Maritime Museum
Hull History Museum
Delivery Partners | Hull City Council
Ground Control
VHEY
Hull Daily Mail
Daily Express
BBC Look North
Warren Centre
Open Doors
Hull Libraries Service
Hull Culture & Leisure