## McGuires
Item | Supplier | Cost ex vat | option costs | Sub Totals Ex VAT | Description | Notes | Where we're at | More notes ??/?? | INVOICE RECEIVED | INVOICE PAID | Insurance values
LIGHTING
Interior lighting | AC | 228.18 |  |  | gel for emergency tubes |  | ordered 06/10 |  |  |  | 228.18
interior lighting | TGPS | 45 |  |  | festoon for walkwayinside skyscrapers |  | received quote 5/10 |  |  |  | 450
festoon lamps | Stage superstore | 21 |  |  | frosted lamps for festoon |  | ordered 15/10 |  |  |  | 21
Exterior lighting | HPSS | 898 |  |  | Festoon for walkway etc |  | ordered 06/10 |  |  |  | 3800
interior lighting | Screwfix | 21.46 |  |  |  |  | bought 18/10 |  |  | Adam CC
interior lighting | b&q | 35.07
LIGHTING SUB-TOTAL |  |  |  | 1248.71
AUDIO
Sound | 3d productions | 504.56 |  |  | 2 x E8, amp & desk | Adam to collect on Tuesday 10th or Weds 11th | ordered 5/10 |  |  |  | 5200
AUDIO SUB-TOTAL |  |  |  | 504.56
HERALDING
Heralding lighting | HPSS | 102.99 |  |  | tower ighting | 3 week hire |  |  |  |  | 102.99
Bits | Screwfix | 22.49 | [7 empty] | Adam CC | 22.49
HERALDING SUB-TOTAL |  |  |  | 125.48
STRUCTURES
Support structure | Strata | 7500 |  |  | as per Davey's drawings |  | ordered & built |  |  |  | 7500
Ramp | b&q | 127.03 |  |  | timber and stuff |  |  |  |  | paid on Adam CC | 127.03
various | pets at home | 6.98 | [7 empty] | TG CC | 6.98
Ramp | b&q | 18.55 |  |  | more timber |  |  |  |  | TG CC | 18.55
more timber | b&q | 25.37
holding tent | Nationwide | 745 |  |  | 6m x 12m with ballast |  | ordered 15/10 |  |  |  | 7500
delivery | Nationwide | 250 |  |  |  |  | ordered 15/10 |  |  |  | 0
furniture | Nationwide | 30 |  |  |  |  | added to order 17/10 |  |  |  | 175
tent dressing | ??? | 0
STRUCTURES SUB-TOTAL |  |  |  | 8702.93
POWER & DISTRO
electrics | TGPS | 300 |  |  | Distro as required | [5 empty] | 1800
Distro | IDE | 193 |  |  | 2 x MD12, 1 x 25m 32-3, 1 x 50m 32-3 | delivered 19th September - 6th November | requested quote & ordered 14/09 |  |  |  | 1550
more distro | b&q | 116.67 |  |  | 13A extensions
generator | John F hunts | 270 |  |  | 40 KVA |  | ordered 15/10 |  |  |  | 13000
tank | John F hunts | 50 |  |  | 2000l tank |  | ordered 15/10 |  |  |  | 2000
fuel | John F hunts | 500 | [8 empty] | 1500
delivery | John F hunts | 560 |  |  |  |  | ordered 15/10 |  |  |  | 0
POWER & DISTRO SUB-TOTAL |  |  |  | 1989.67
PLANT & BARRIERS
container | Add plant | 132 |  |  | 20' container for storage | 11 week hire @ £12 pw | ordered 20/08 |  |  |  | 2500
delivery | Add plant | 100 |  |  |  |  | ordered 20/08 |  |  |  | 0
articulating boom | AFI uplift | 250 |  |  | BA30NE |  | ordered 20/08 |  |  |  | 0
delivery | AFI uplift | 140 |  |  | £70 e/w |  | ordered 20/08 |  |  |  | 0
scaff | Actavo | n/a |  |  | 20 x 4' tubes, 20 x 12' tubes, 40 x swivels | delivered 19th, collected 6th | requested quote 05/10 |  |  |  | 0
PLANT SUB-TOTAL |  |  |  | 622
CREW
Event/FOH manager |  |  | 4200 |  | 2 people, in shifts, for 14 days @ £150 per day | [5 empty] | 0
crew |  | 400 |  |  | Ian & Laura to dress tent & exit | [5 empty] | 0
Crew |  | ??? | 720 |  | 2 crew for 3 days for get-out | £15 per hour |  |  |  |  | 0
CREW SUB-TOTAL |  |  |  | 400
MISCELLANEOUS
Asbestos testing | Euro Environmental |  | 216.5 |  |  | Hull 17 paid for | quote received |  |  |  | 0
Air quality testing | Euro Environmental |  | 1177 |  | to test for all airborn particles and moisture | Hull 17 paid for | quote received |  |  |  | 0
Build toilet | Add Plant | 242 |  |  | single unit for 11 weeks | £22 pw, inc weekly service | ordered 20/08 |  |  |  | 600
delivery | Add Plant | 30 |  |  | £15 e/w |  | ordered 20/08 |  |  |  | 0
event toilets | Add Plant | 360 |  |  | 3 toilets for 2 weeks | £45 pw | ordered 10/10 |  |  |  | 1800
servicing | Add Plant | 630 |  |  | 7 services at £90 per service |  | ordered 10/10 |  |  |  | 0
Bins | HULL CC | 434.6 |  |  | 2 x 1100l bins | delivered Mon 9th | ordered 10/10 |  |  |  | 250
Emptying | HULL CC | inc above |  |  | 3 empties |  | ordered 10/10 |  |  |  | 0
skip | ??? | 300 |  |  | for get-out
comms | 900 communications | 173.71 |  |  | 8 x DP3400's with surveillance earpieces |  | received quote 10/10 |  |  |  | 3040
delivery |  | 34.4 |  |  | Delivered to pacific exchange on 19th October |  | received quote 10/10 |  |  |  | 0
Dehumidifiers | HSS | 838.75 | [7 empty] | paid initial amount on Adam CC | 450
Bits | Maplins | 108.77 |  |  |  |  | bought 18/06 |  |  | paid on Adam CC | 108.77
MISCELLANEOUS SUB-TOTAL |  |  |  | 3152.23
STEWARDING
Stewarding/Security |  | 3685 |  |  | Stewarding/first aid as per spreadsheet |  | ordered 09/10 |  |  |  | 0
STEWARDING SUB-TOTAL |  |  |  | 3685
H&S
Fire alarm | Fire protection systems | 4475 |  |  | monitored fire alarm | need to work out keyholders | ordered |  |  |  | 2500
additional fire equipment | Fire protection systems | 1735 |  |  | beam detectors | [5 empty] | 1735
Alarm monitoring | Fire protection systems | 375 | [8 empty] | 0
key holding | SCAMP | 280 |  |  | this is an annual fee, for keyholding |  |  |  | 2017-10-13 |  | 0
Call outs | SCAMP | 187.2 |  |  | charged at £62.40 per call | Estimate, based on 3 call outs |  |  |  |  | 0
Extinguishers | Spitfire | 100 |  |  | 5 x water & 2 x Co2 |  | ordered 17/10
H&S SUB-TOTAL |  |  |  | 7052.2
TM
n/a
TM SUB-TOTAL |  |  |  | 0
FEES
Handling fee | TGPS | 1379.139 |  |  | 5% of all hires | [5 empty] | -----------------
FEES SUB-TOTAL |  |  |  | 1379.139
TOTALS Ex Contingency, Ex VAT |  | 28961.919
Contingency |  | 1038.081
TOTALS inc Contingency - EX VAT |  | 30000 | [8 empty] | 57985.99
TOTAL inc VAT |  | 36000