## Sheet1
PEOPLE KE
JL = Jack Lowe / EE = Eddie Elbourne / SM = Jade Hunter / HPSS1 = Sound / HPSS2 = LX / HPSS3 = Stage
CURIOUS DIRECTIVE: FROGMAN PRODUCTION SCHEDULE |  | Version 4_CD notes
Date & Time | Activity | Who | Notes
Tuesday 17th October
11:00-12:00 | Internet Survey | KCOM
Monday 30th October
PM 12:30-16:30 | Internet Installation | KCOM | Actual time TBC
13:30-15:00 | Arrival and Load-in | EE and JL/HPSS 1-3
14:30-16:00 | Pipe and Drape Install | HPSS3 & HPSS2 | Blackout windows
14:00-18:00 | Put together final 18 chairs, cabling and amps | EE & HPSS1 | At the side
16:00-17:00 | Rig LX | HPSS 2 | Check for power surge on the rings.
16:30 | Internet VR check | JL | Get in touch with KCOM if not working
18:00-19:00 | Sound cable run | HPSS1 / EE | Depending on EE progress.
15:30-19:00 | Control Position Set-up | JL
| AV set up | JL
| LX cable run / into desk | HPSS 2
| Continue Pipe and Drape | HPSS3 | Performance Area
Tuesday 31st October
10:00-13:00 | Roll out all rubber and sound connectors onto all 48 chairs | EE/HPSS 1-3
| Floor lay | JL and EE
13:00-14:00 | Break | All
14:00-17:00 | Plot LX | JL and EE
14:00-17:00 | Troubleshoot chairs | HPSS 1-3
Wednesday 1st November
10:00-12:00 | Final Sound checks | curious directive
12:00-13:00 | Cast Checks Tech | All | SM and Actor arrive around 12noon.
13:35 | Set up | curious directive | Duty tech required from 60 mins before show.
14:18 | Doors |  | Doors can open whenever, but house opens 12 minutes before show.
14:30 | Show 1 | curious directive
14:30 | End
18:35 | Duty tech |  | Duty tech required from 60 mins before show.
19:18 | Doors
19:30 | Show 2 | curious directive
20:30 | End
Weds 1st model repeated. SM and DT to arrive 60 mins before each show. Venue manager to co-ordinate with SM. SM, DT and VM are all in the show for the first 5 minutes.