Milestone 1 – On signature of the contract 2016

- Initial marketing copy and image developed.

- Project Plan delivered.

- Timeline document created.

- Headline venue held.

- Agreed budget.

- Friday 17th & Sunday 19th headline artists confirmed.

- Tickets on sale (Sept 22nd).

Milestone 2 –  by Friday 28th October

- Agreed budget update.

- Full line-up of artists contracted.

- Marketing and comms plan developed with Hull 2017 marketing team.

- Image and copy for confirmed Tier 1 artists.

- Volunteer numbers confirmed.

- Selected artists announced (on date to be confirmed).

- Decision on inclusion of Touch Tour.

- Tickets for Saturday 18 February on sale.

Milestone 3 – by Friday 9th December

- Agreed budget update.

- All artists contracted.

- Artist accommodation and travel booked.

- Initial tech and staffing scoped.

- Volunteer skills requirements confirmed.

- Remaining tickets for Mortimer Suite events on sale (if necessary).

Milestone 4 - by Friday 3rd March

- Evaluation.

- Successful delivery.