25/10/2017

Turner Prize Events Meeting

Katy Fuller, Chris Clay, Jenny Hutt, Lily Mellor, Mike Berriman, Rebecca Clark

Apologies: Ben McKnight

- PRESS

BM to confirm press info with JH – are all critics and correspondents sent invites and if so do these go from Bolton & Quinn or Hull 2017? 

MB suggested new café opposite Minster to use for press filing 
MB to test Wi-FI and press numbers / hire fee
JH to release hold on Minster offices as they only available from 21:00

- PRODUCTION

- Schedule to cover all venues – Maritime / Ferens / Minster

- CC / JH / KF meeting with Durham 26/10/2017

- CC confirmed HPSS are happy to go ahead with Durham

- JH/CC going to Minster on 10/11/2017 for a recce

- Jane confirmed the Christmas tree is going by the pulpit

- B stage needed for Steve Cobby - set up 19:00 – 23:00 – add into schedule

- CC suggested gauze

- Centre pieces to be decided, JZ flowers not yet confirmed

- JH - venue to be decided for 28 x crew over 2 days

- CATERING

- Costs for Ferens pre-drinks tbc. HCAL to provide the glasses. No canapes

- JH meeting with Saunts 26/10/2017

- Saunts will leave entire infrastructure for following events - £30 per head estimate -JH / LM / KF to re-cast budget

- AFTER PARTY

KF confirmed paid bar - Allocate £1000 to after party drinks to cover 80 people
Wristbands agreed for entry to all 3 venues -CC suggested turning it into a drink token by handing wristband in return for a drink 
RC to order wristband samples from ID&C

- AOB

- BBC Academy 10 x people. KF argued this is too many people to manage from our side. Make them available for the BBC?

- KF to e-mail BBC/Tate about meeting – 02/11/2017

- WH requested contract for Goldie

- RC confirmed music suggestions have been sent to BBC

- BBC 6 Music with Mary Ann Hobbs – date for recce tbc, to do a live on 02/12/2017 6am start LM to get confirmation from BBC if this will take place in the Ferens