## Detailed Critial Path
Event Name: Made in Hull
Client: Hull City of Culture
Event Date: 1st January - 15th January
Project Code:
Revision
Current week commencing
KEY
Milestones |  |  |  | No. of Months | 5 |  |  | 4 |  |  |  | 3 |  |  |  |  | 2 |  |  |  | 1 |  |  |  | 0
Completed |  |  |  | Month | August |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January
Needs Immediate Action |  |  |  | Weeks before Parade
|  |  |  | Days | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m
Dates
Key Meetings | Start Date | End Date | Notes | Name / Responsibility
Internal Project Team Meetings | 2017-08-01 | 2018-01-31 | every 2 weeks, moving to every week in october | Haitham R
Creative Project Team Meetings (face to face) | 2017-08-01 | 2018-02-01 | every 2 weeks | Niccy Hallifax
Artist agency Conference call (weekly) | 2017-08-01 | 2018-01-31 | On going | Niccy Hallifax
Artists Stakeholder Meetings | 2016-08-08 |  |  | Kirstine
Internal Debrief |  | 2018-01-20 | TBC in line with Board timelines | Haitham R
External Debrief |  | 2018-01-25 | TBC in line with Board timelines | Niccy Hallifax
Wash up report meeting |  | 2017-01-31 | TBC in line with Board timelines | All
Art Commisioning
Creative kick off meeting with key internals. | 2017-08-15 |  | Complete
Identify artists for intrest to tender
Create deck for briefing and brief
Artist tender for intrest deadline
contracted: Artists chosen.
Individual brief writing |  |  |  | NH/RC
Meeting Phase 1 to answer queries with each artist chosen |  |  | urban productions will be on the 5th sept.
Phase 2 and engagement with senior team
sign off of concept
design development
production development
tech development
sign off
Wash up report meeting
Creative
Creative Kick off Project meeting
Core team meeting
Continuous stakeholder client liaison
Present creative themes and core concepts to Board and stakeholders
Review of creative themes and core concepts with wider teams (fortnightly meeting)
Approval of scope on creative themes and core concepts
3D scope of works briefed and commenced. (design)
Sound design scope developed.
Present technical production for approval
H&S approve technical production and operational plans
Stakeholder meetings (inclusive of media partners)
Inter-agency liaison with depatrtment leads: Design, Interptritation, Digital, Marketing, PR
written word first draft (narartive)
Development Phase 1
Decvelopment Phase 2
wriitten word narrative sign off.
Post-event reconciliation with boards for stakeholders.
Finance Stages & Reconciliation
Contracts of artists and core team agreed & finalised | 2017-08-01 | 2017-09-01 | complete | Will / Jason
Budget approved | 2016-08-08 | 2017-09-01 | Complete | Tom /Niccy
Payment schedule agreed | 2016-09-01 |  |  | Nicc/ Tom
Artists Contract signed |  |  |  | Will / Jason
T&Cs and payment schedules agreed with suppliers and comunicated to Hull 2017 through a Roles and responsibilities document. |  | 2017-10-21 | ongoing | Jason Bruge team
Purchase orders sent to suppliers
Budget reconciled | 2018-01-12 | 2018-01-31
General Project
Approval of operational project scope |  |  |  | Chris Clay/Tom
Stakeholder management: Internal and external
Programming, interpritation and design Concept and strategy development
Operations management draft complted.
Onsite
Reccees for (external programming)
Load in dates
Tech and creative rehersal period
Live dates:
Site de-rig and official handover of space back to Holticulture / Operations.
Creative design and implimentation
Creative briefed (internal and external) with budget parameters
3D Design development key stages outside of artists commisions (outline) deadline
Creation of technical drawings
Approval/sign-off of final design & 'look & feel'
3D elements out for production
scheme implimentation
scheme sign off and install on site sign off.
Signage, Branding & Wayfinding design - within the footprint of the route.
Signage & branding requirements identified
Signage & branding spec developed
Signage & branding spec approved
Print companies identified
Design templates approved
Design/art working
Print company confirmed
Stage 1: sign off process for all branding and signage
All branding and signage sent to print
Print adjustments as required
Branding & signage delivered to site for install
Cross check signage is in correct location
Technical Design - infustructure
Technical initial briefing and development
Assigned Production team
Key technical suppliers identified
Supplier briefings & recces
Key technical suppliers contracted
Develop technical production
On-going meetings & discussions with technical suppliers
Queuing CAD and numbers plan designed and submitted
Site plans developed
Structural licensing and planning if required
Site plans issued to key stakeholders
Site plans revised and reissued as required
Final site plans submitted to key stakeholders and departments.
Onsite schedule developed
Onsite schedule issued to key stakeholders
Onsite schedule revised and re-issued as appropriate
Final onsite schedule issued to key stakeholders
Reconciliation report - technical
Technical Production services. - Ground Control
Radio Communications Plan produced
PA system - specification produced
Toilets - specification produced (if required)
Power - specification produced
Cable management
Trakway (if required)
Event Capture (Videographer & Photographer)
Engage and contract content capture team
Develop strategy & brief
Delivery of assets from capture team
Complete the post-event internal reporting documents, inclusive of upload of images etc.
Edit and upload to social media where applicable
Miscellaneous
Contingecy budgeting
IT requirements identified
IT requirements confirmed & ordered
Rehearsal schedules submitted and agreed
Onsite briefing plans submitted and agreed
Event operations management plan distributed
Media for Opening event - date TBC
Numbers identified and confirmed
Accreditation process confirmed
Technical requirements confirmed

## Operations Project Critical Pat
Event Name: Made in Hull
Client: Hull City of Culture
Event Date: 1st January - 15th January
Project Code:
Revision
Current week commencing
KEY
Milestones |  |  | No. of Months | 5 |  |  | 4 |  |  |  | 3 |  |  |  |  | 2 |  |  |  | 1 |  |  |  | 0
Completed |  |  | Month | August |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January
Needs Immediate Action |  |  | Weeks before Parade
|  |  | Days | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m
Dates
|  | Notes | Name / Responsibility
Key Meetings | Internal Project Team Meetings
Creative Project Team Meetings (face to face)
SAG Meetings
Production agency Conference call (weekly)
Artists Stakeholder Meetings
Internal Debrief
External Debrief
Wash up report meeting
Licensing, Approval & Permissions | Licensing, Approval & Permissions processes commences
Premises License submitted
Newspaper advertising of licence application
Premises notice notice of application (28 consecutive days starting from the day after the day the application is made)
Licensing, Approval & Permissions Secured
No Objection from stakeholders
Temporary Traffic Order
Acoustic consultant - pre event background assessment
Acoustic consultant - on the day monitoring and reporting
Resident Mitigation plan developed
Financials /Contracting - Client | Phase 1 budget prepared
Phase 1 Budget approved
Phase 2 budget prepared
Phase 2 budget approved
Phase 3 budget prepared
Phase 3 budget approved
Budget revisions & updates (weekly)
Payment Schedule/ Cancellation Terms
Project Revenue Target met
Reconciliation & Final Invoicing
Audit File
Drawings/ Plans/ Designs | Site layout / plans amends / updates
Plans issued
Traffic Management | Appoint traffic management company
Traffic Management Planning
Road signage plan produced
Traffic Management Stewarding plan produced
Contingency planning
Health & Safety | Event Safety Plan as part of ESMP
Contingency planning as part of ESMP
Risk assessments produced alongside the ESMP
SAG and Table top exercises
First Aid planning produced
Risk & issue management / risk register development
Crowd Management | Pedestrian Signage Plan produced
Crowd Management Planning as part of ESMP process
Crowd Management Stewarding Plan produced as part of ESMP process
Command and Control panel meetings
Emergency procedures developed
Table Top exercises
Stewarding & Security | Agreement of crowd and traffic management steward resourcing and allocation plans
Site Security planning
Site Security plan produced
Contingency planning
Table top exercises
Steward and security logistical plan agreed
Media Management | Discuss media requirements
Develop accreditation plan
Venue Management | Investigate ELT position
Technical Production | Production Schedule
PA System - Specification produced
Video / Projection Mapping - Specification produced
Site Management | Site Production Schedule
Fencing (including CCB Barrier)
Toilets - Specification produced
Power - Specification produced
Cable management
Trackway
Cabins & Steel Stores
Viewing platforms
Production Compound / Accreditation Compound - Specification
Signage Planning | CM Signage Plans compiled
CM Signage Plan authorised/signed off
CM Art work to graphics company
Health & Safety / CMP Signage produced
CM Signage installed
TM Signage plans compiled
TM Signage plans authorised/sign-off
TM Signage produced
TM Signage Installed
Financials/Contracting - Suppliers | Supplier Terms & Conditions
Supplier Payment Schedule
POs
Hull City of culture and Ground Control Operations | Insurance
Noise Management
ELT Specification
Submit Production Plans to Local Authorities
Radio Communications Plan produced
Onsite IT Requirements/ Scoping Doc
Onsite Financial Requirements
Onsite Equipment Requirements
Project Overview
Onsite Schedule & Key Docs
Job Close Processes
Crew and project team logistics | Accommodation
Travel
Refreshments
Accreditation - different levels and production agreed
Crew and performer Welfare
Crew Handbook
Legal Requirements | Identify legal requirements e.g. planning permission/ licenses
Obtain appropriate permissions/ licenses
Data sharing agreement
Sustainability | Identify project team champion
Stakeholder Register
Communication Plan with stakeholders
Sustainability Management Tracker
Event Impact Assessment

## Stakeholder Meeting Dates
Event Name: Made in Hull
Client: Hull City of Culture | [8 empty] | Current week commencing
Event Date: 1st January - 15th January |  |  |  | Current week commencing |  |  |  |  | `
Project Code:
Revision |  |  | No. of Months | 5 |  |  | 4 |  |  |  | 3 |  |  |  |  | 2 |  |  |  | 1 |  |  |  | 0
|  |  | Month | August |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January
Weeks before Happening
|  |  | Days | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m
Dates
Key Dates & Trigger Points |  | Notes | Name / Responsibility
Sean holiday and away times | 21st August to the 5th September
6th - 12th October
Chris Holiday | 25th Sept to the 3rd October
Ala holiday | 24th August to the 4th September
5th October 12th October (out of the country)
22nd October to the 30th October (can only work from London)
Niccy | 24th August
Bank Holidays | Christmas
Boxing Day
Bank Holidays
Other relevant dates | Local Authority elections
Possible Dates - Scenarios
Core Group Milestones | First meeting of core group to consider options dates, routes and format of live parade. Discuss possible dates.
Second core stakeholder group meeting (SAG)
Full authority and stakeholder meeting to review key planning documentation regarding format and placemnet
Full authority and stakeholder meeting to review dates, route and format.
Stakeholder (SAG) meeting to update on placement, Live event, finalise command and control structure, review resident mitigation plan etc.
Meetings of sub groups to discuss and agree specific aspects of the parade e.g. – emergency service liaison, publicity, traffic measures, command and control etc.
Final full authority and stakeholder meeting if required.

## Community Engagement Plan
Event Name: Made in Hull
Client: Hull City of Culture
Event Date: 1st January - 15th January
Project Code:
Revision
Current week commencing
|  |  | No. of Months | 5 |  |  | 4 |  |  |  | 3 |  |  |  |  | 2 |  |  |  | 1 |  |  |  | 0
|  |  | Month | August |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January
|  |  | Weeks before Parade | 14
|  |  | Days | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m
|  |  | Dates | 3rd
Key Dates & Trigger Points |  | Notes | Name / Responsibility
Bank Holidays | Christmas
Boxing Day
Bank Holidays
Other relevant dates | Local Authority elections
Possible Parade Dates - Scenarios
Community Engagement Comms Plan | Agree Locations can take place
Detailed assesement and understanding of impacts
Agree advice and information / develop and finalise factsheet
Submit TMO / Premises Licence
Inform PR & Media?
Community & stakeholder engagement - ongoing comms
Community & stakeholder engagement - letter & map highlighting route / closures / estimated timings
Hull website live with copy & map highlighting route / closures / estimated timings
BHF website live copy & map highlighting route / closures / estimated timings
Day Activity.
Online comms messaging
Hotline for residents to call?