## Sheet 1 - BROCCOLILY THEATRE -
BROCCOLILY THEATRE - PROJECT TIMELINE
Name of Individual / Organisation | Broccolily Theatre & Ganton School
Name of Project | Wired Differently
Please provide a breakdown of key activities /tasks for your project from start to finish. Please include your preparation and planning activity as well as start / end dates of your public activity (eg. public performance, exhibitions, festival).
START DATE | END DATE | ACTIVITY / TASK | STATUS
START DATE | END DATE | ACTIVITY/TASK | STATUS - COMPLETE / ON-TIME / BEHIND | NOTES
02/12/2017 | 2017-01-20 | Phase 1 - Research & Development Workshops with Participants. | COMPLETE
2017-01-20 | 2017-04-24 | Phase 2 - Writing & Design of show - Including Filming and Technical Plans for show. | ON-TIME
2017-04-24 | 2017-06-27 | Phase 3 - Rehearsals
28/06/2017 | 28/06/2017 | Public Performance - live streamed on the Internet & at Public Libraries. | ON-TIME
03/07/2017 | 14/07/2017 | Evaluation & report writing | ON-TIME
2017-07-03 | UNKNOWN | Screening of film at other venues | ON-TIME | Dates for screenings to be confirmed.
Activity Examples: Planning Meeting, Auditions, Contracting, Rehearsal, Costume Design, Performances