Internal R1BW meeting
28/02/2017

Attending:

Chris Clay
Jonathon Black

Melissa McVeigh

Helen Thackeray

Rebecca Clark

| POINT | ACTION |
| --- | --- |
| 1. Utilities |  |
| HT - Yorkshire Water are considering using the piping at the back of the house will speak to Burton Constable about this. BC to confirm with HT HT - confirmed they are able to barrel more water in if necessary CC - said there is a clause in the contract about utilities. Yorkshire Water can waive the cost as part of the Hull 2017 partnership HT – confirmed there is lighting at the front of the house and Rodrica Straker is keen to light the orangery via their internal lighting. BC will manage this. |  |
| 2. Catering |  |
| HT – Cerruti’s have gone directly to Nick Hildyard at BC about catering CC - confirmed BBC are trying to appoint local suppliers as much as they can and have requested a list of local caterers and wholesalers ACTION: HT to share the list of local caterers with Jack May, BBC | HT |
| 3. Procurement |  |
| 3.1 Medical MM - St. John’s Ambulance are confirmed for Medical 3.2 Cleansing CC - Victoria Hindle at ERC sent a cheap quote through and caused some confusion. She stated ERC could not meet staffing expectations using the council team. It transpired they can provide additional staff using external companies CC - confirmed Ryan’s been appointed as opposed to ERC Commercial Waste Management. They are able to conduct a post-event clean up 3.3 Welfare CC - yet to appoint H&S and Welfare companies CC - queried whether Welfare can go through St. John’s or whether there are other companies who could lead on this CC – confirmed BBC look after children and the Hull 2017 Welfare spec will primarily cover adults HT - confirmed Street Angels are recruited through Prestige Security and all their staff are trained as youth and community workers, covering sexual health, lost children, drug and alcohol use ACTION: Once appointed, Ryan’s to be invited for a meeting and site visit ACTION: MM to invite St John's for a meeting ACTION: Invite Linda from Street Angels to discuss Welfare requirements | CC MM CC |
| 4. Traffic Management |  |
| 4.1 Buses CC – confirmed HCC don't have a list of approved bus suppliers. Arriva are on the ERC framework. CC – confirmed the bus companies who are on the H17_013 Ground Transport Framework are Abellio and Acklams. By using local suppliers (Stagecoach and EYMS) they can only provide a percentage of the bus requirements, so there is a need to supplement their provision with national companies HT - speaking to Margaret Nieke about reinforcing the corners for wider bus turning circles HT – mentioned the quote for reinforcing the additional road out from Burton Constable was £4,500 and would be worth adding in although realises this is budget dependant 4.2 Traffic Management Plan CC – expecting a Draft Traffic Management plan from Nigel Wilson and will feedback at next meeting ACTION: CC to issue RFQ on 28/02/2017, closing on 07/03/2017 | CC |
| 5. Volunteer Requirement |  |
| CC to discuss volunteer requirements with HJ and feedback | CC |
| 6. Resident Liaison |  |
| HT – Unavailable to attend the next parish meeting in Skirlaugh on 07/03/2017 CC – to get into touch with Will at ERC and discuss if there are any other parishes we should be making contact with ACTION: HT to share additional Parishes information with CC ACTION: CC to attend parish meeting on 07/03/2017 | HT CC |
| 6. Catering |  |
| HT - to speak to the café at Burton Constable and confirmed £3,000 has been put aside for loss of earnings, but could potentially provide crew catering as an alternative |  |