## Sheet1
Item | Supplier | Cost ex vat | option costs | Sub Totals Ex VAT | Description | Notes | Where we're at | More notes 03/04 | Telephone | email | Order wording | Order cost exVAT | Insurance values
MACNAS
Prep/build space
Heating | TGPS | 100 |  |  | 2 x infra red heaters for office | bringing Monday 16th October
Heating | TGPS/HSS | 500 |  |  | other heaters as required
.
Furniture | All occasions | 374.95 |  |  | 50 x chairs & 8 x trestles |  | received quote 09/10
catering furniture | All occasions | inc above |  |  | 50 x chairs, 7 x restles & 6 x 6' rounds |  | received quote 09/10
distro | TGPS/IDE | 350 |  |  | 13A extensions etc | or maybe more | asked Gareth
electrician | Greg? | 700 |  |  | in case we need to put heavier distro in
catering | Gig-a-bite | 3974 |  |  | crew catering |  | waiting for firm quote
partitions for dressing room spaces |  | 0 |  |  | use existing partitions in Staples
Sub-Total |  |  |  | 5998.95
Performance
Get-in crew | TMC | 896.1 |  |  | 6 crew from 0900-1800 |  | requested quote 14/10
Get-out crew | TMC | 988.8 |  |  | 8 crew from 1800-0200 |  | requested quote 14/10
fencing crew | TMC | 390 |  |  | 2 crew Friday night to build savile street 1900-2200. 2 crew saturday to build & break fencing 1300-2000 |  | requested quote 14/10
show crew | TGE | 200 |  |  | 1 x tele drivers for day | need to be 17m ticketed
show crew | TMC | 385.22 |  |  | 2 x telehandler drivers 1000-2100 | 1 needs to be 17m ticketed | requested quote 14/10
pd's |  | 45
Site managers | TGE | 750 |  |  | 3 site managers | co-op, lowgate, C4DI
pd's | TGE | 75
travel | TGE | 250
TM | Centurion | 2920 |  |  | as required |  | ordered 06/10
C4DI Plant | Add plant | 640 |  |  | 2 x 17m telehandlers | with fork extensions | received quote 11/10
Lowgate plant | Add plant | 150 |  |  | 5 or 7m telehandler |  | received quote 11/10
delivery | Add plant | 450 |  |  | delivered Fri, collected Mon |  | received quote 11/10
barriers | Event solutions | 1546.75 |  |  | ped & Heras, as required |  | received quote 14/10
Comms | 900 communications | 411.25 |  |  | 35 x radios, 30 x noise cancelling headsets & 20 x surveillance mic kits | to supplement council radios | requested quote 13/10
delivery collection | 900 communications | 75 |  |  | delivered Thursday 9th | collected Monday 13th | requested quote 13/10
scissor lift | AFI | 340 |  |  | 14m scissor lift | For photographer | received quote 12/10
Street lighting | KWL | 1000 |  |  | to turn on/off street lighting as required | ESTIMATE. Gareth liaising with
Extinguishers |  | 50
Sub-Total |  |  |  | 11563.12
AND NOW
crew | TMC | 659.2 |  |  | 2 x crew for in & out |  | requested quote 14/10
Crane hire | Central cranes | 4140 |  |  | overnight on 3rd & 12th | Contract lift | received quote 14/10
scaff | B&A | 3140 |  |  | edge protection & crate base for Co-op & Hudgells |  | received quote 14/10
Security | Prestige | 425 |  |  | 2 x SIA for overnight in & out |  | ordered 10/10
plant | Add plant | 225 |  |  | 7m telehandler | to move crates | received quote 11/10
Fencing | Event solutions | 675 |  |  | barriers for in & out |  | received quote 14/10
Work light |  | 0 |  |  | Use Aidens battery floods
Traffic management | Centurion | 1150 |  |  |  |  | ordered 06/10
additional TM | Dynniq | 500 | 500 |  | possible cost to turn off crossing | Centurion have asked the council if the can do it | waiting to find out if there's a cost
comms | council | 0 |  |  | 6 x radios
Transport |  | 700 |  |  | 7.5t flat bed with driver | to move crates | need to find
Co-op Lighting | KWL | 700 |  |  | power on lamppost, inc 2 floods
Hudgells Lighting | ??? | 700 |  |  | power on building
general lighting | HPSS | 100 |  |  | 4 x floods | 2 for each box
Sub-Total |  |  |  | 12455
Handling fee | TGPS | 1533.8135 |  |  | 5% of all hires
Contingency |  | 1610.5042 |  |  | 5% of costs
MACNAS SUB-TOTAL |  |  |  | 33820.5877
TOTALS inc Contingency - EX VAT |  | 33820.5877 | [9 empty] | 0 | 0