## AndNow
Item | Supplier | Cost ex vat | option costs | Sub Totals Ex VAT | Description | Notes | Where we're at | More notes ??/?? | INVOICE RECEIVED | INVOICE PAID | Insurance values
LIGHTING
Entry/exit lighting | TGPS | 100 |  |  | festoon | [5 empty] | 2000
structure lighting | LAD events | 280 |  |  | 4 x LED fixtures to light structure |  |  |  | 2017-07-24
LIGHTING SUB-TOTAL |  |  |  | 380
AUDIO
Performance pa | 3d productions | 3128.24 |  |  | Ground stacked v system with in fills | inc crew, radio mics etc | ordered 29/06 |  | 2017-07-20 |  | 180000
labour | 3d productions | 910 |  |  |  |  | ordered 29/06 |  | 2017-07-20 |  | ----------
delivery | 3d productions | inc above |  |  |  |  | ordered 29/06 |  | 2017-07-20 |  | ----------
FOH | 3d productions | 150 |  |  |  |  | ordered 29/06 |  | 2017-07-20 |  | 2500
additional audio | 3d productions | 217.87 |  |  | extra speakers for platform |  |  |  | 2017-07-20
AUDIO SUB-TOTAL |  |  |  | 4406.11
STRUCTURES
Backstage tent | Nationwide | 465 |  |  | 6m x 9m |  | ordered 28/06 |  | 2017-07-20 |  | 5800
flooring | Nationwide | 162 |  |  | 6m x 9m |  | ordered 28/06 |  | 2017-07-20
Furniture | Nationwide | 66.5 |  |  | 20 x chairs, 10 x trestles |  | ordered 28/06 |  | 2017-07-20 |  | 640
delivery/collection | Nationwide | 250 |  |  | Delivered Thursday 7th, collected Monday 17th |  | ordered 28/06 |  | 2017-07-20 |  | ----------
brass band stage | 3d | 218.51 |  |  | 16' x 16' c/w treads | Us to provide 2 local crew to assist | ordered 29/06 |  | 2017-07-20 |  | inc above
STRUCTURES SUB-TOTAL |  |  |  | 1162.01
POWER & DISTRO
Backstage/show power | John F Hunts | 135 |  |  | 40KVA |  | Ordered 28/06 |  |  |  | 13500
Entry exit power | John F Hunts | 250 |  |  | 2 x 20KVA | For festoon | Ordered 28/06 |  |  |  | 19990
tank | John F Hunts | 25 |  |  | For 40KVA |  | Ordered 28/06 |  |  |  | 1500
Fuel | John F Hunts | 291.75 |  |  |  |  | received total 21/07 |  |  |  | 700
Delivery/collection | John F Hunts | 1120 |  |  | Delivered Thursday 6th, collected Monday 17th |  | Ordered 28/06 |  |  |  | ----------
Distro | TGPS | 100 |  |  | As required | [5 empty] | 1200
cable ramp | 3d productions | 256 |  |  | 30 panels, for FOH run |  | ordered 29/06 |  | 2017-07-20
extra cable | 3d productions | 4.8 | [6 empty] | 2017-07-20
Tower lights | John F Hunts | 240 |  |  | 2 x LED tower |  | Ordered 28/06 |  |  |  | 21000
POWER & DISTRO SUB-TOTAL |  |  |  | 2422.55
PLANT & BARRIERS
Ped barrier | Actavo | 206.25 |  |  | 75 panels of ped |  | ordered 29/06 |  |  |  | 2925
Heras | Actavo | 240 |  |  | 80 panels of Heras | with double clips | ordered 29/06 |  |  |  | 3476.8
damaged panels | Actavo | 140 |  |  | replacemt cost for 4 damaged panels
Scaff | Actavo | 27 |  |  | 50 x 5' scaff poles | Putlog | ordered 29/06 |  |  |  | 100
Scaff | Actavo | 76 |  |  | 50 x 14' poles | extensions | ordered 29/06 |  |  |  | 280
Scaff | Actavo | 6.8 |  |  | 100 x swivels |  | ordered 29/06 |  |  |  | 200
Delivery/collection | Actavo | 200 |  |  | Delivered Thursday 6th July, collected Monday 17th |  | ordered 29/06 |  |  |  | ----------
Telehandler | Add Plant | 275 |  |  | 9m telehandler |  | ordered 29/06 |  |  |  | 38000
Man basket | Add Plant | 50 |  |  |  |  | ordered 29/06 |  |  |  | 1500
Fuel | Add Plant | 50 |  |  |  |  | ordered 29/06 |  |  |  | ----------
Delivery/collection | Add Plant | 160 |  |  |  |  | ordered 29/06 |  |  |  | ----------
ground scanner | HSS | 78.34 |  |  | to scan ground for Putlog |  |  |  | 2017-07-10 | paid on TGE CC
Container | Add Plant | 48 |  |  | 20' container for storage of pyro | Maybe able to use existing one? | ordered 29/06 |  |  |  | 3000
delivery/collection | Add Plant | 100 |  |  | Delivered Saturday 8th July, collected Monday 17th |  | ordered 29/06 |  |  |  | ----------
PLANT SUB-TOTAL |  |  |  | 1657.39
CREW
Pre get-in crew | The Music Consortium | 247.2 |  |  | 2 men Thursday 7th 1000-1800 | Lay turf, fencing etc | ordered 29/06 |  | 2017-07-18 |  | ----------
Get-in crew | The Music Consortium | 618 |  |  | 2 men Fri 14th 1000-1800, Sat 15th 1100-0100 | To do putlog, scaff, Fencing etc | ordered 29/06 |  | 2017-07-18 |  | ----------
Get-out crew | The Music Consortium | 247.2 |  |  | 2 men Sun 1000-1800 |  | ordered 29/06 |  | 2017-07-18 |  | ----------
additional get-out crew | The Music Consortium | 77.25 |  |  | 1 extra man for 5 hours on Saturday night |  | ordered 13/07 |  | 2017-07-18
cleaning crew | Ian & laura | 200 |  |  | to finally clear site on 17th |  |  |  | 2017-07-18
crate crew | Ian | 70 |  |  | to move crate on 7th July
CREW SUB-TOTAL |  |  |  | 1459.65
MISCELLANEOUS
Turf | crown lawns | 542 |  |  | 200m2 of turf, to lay on top of existing turf | 2 layers10m x 10m @ £2.71 per sq.m. | received verbal quote 30/06 |  |  | 2017-07-05 | 542
Hessian | Hull 17 | 0 |  |  | 200m | use from periplum |  |  |  |  | 500
Rope | Hull 17 | 0 |  |  | For front line | use from periplum |  |  |  |  | 500
Road Pins | Hull 17 | 0 | [8 empty] | 150
Rope | Hull 17 | 0 | [8 empty] | 250
Urn | Hull 17 | 0 | [8 empty] | 100
Catering eqpt | Hull 17 | 0 |  |  | tea, coffee, cups etc | [5 empty] | 150
paint and stuff | B&Q | 44.57 | [6 empty] | 2017-07-08 | TG CC 08/07
spray paint | Hobby craft | 3.5 |  |  | for heralding |  |  |  | 2017-07-06 | cash
comms | Hull CC | 0 |  |  | Radios | using channels 9-12 back to back |  |  |  |  | 27502.96
Cleansing | Hull CC | 546.96 |  |  | Sweep on Sunday afternoon/Monday morning |  | ordered 29/06 |  | 2017-07-24 |  | ----------
Bins | Hull CC | 222 |  |  | 3 x 1100l bins |  | ordered 29/06 |  |  |  | 900
Skip | Walkers skip hire | 200 |  |  | 12 cubic yard | delivered Friday, call Monday for collection | ordered 12/07 | cash on delivery - £240 |  |  | 2000
Backstage toilets | Add Plant | 100 |  |  | 2 x single plastic units | delivered Thurs 7th, collected Sunday 16th | ordered 29/06 |  |  |  | 1200
Servicing | Add Plant | 150 |  |  | serviced Mon 10th, Weds 12th & Sat 15th |  | ordered 29/06 |  |  |  | ----------
Public toilets | Add Plant | 1240 |  |  | 20 singles plus 3 accessible units |  | ordered 29/06 |  |  |  | 15600
delivery/collection | Add Plant | 320 |  |  |  |  | ordered 29/06 |  |  |  | ----------
water bowser | GAP | 70 |  |  |  |  | received quote 23/06 |  |  |  | 2200
Delivery & collection | GAP | 70 |  |  | delivereurs 6th, collected Mon 17th |  | received quote 23/06 |  |  |  | ----------
MISCELLANEOUS SUB-TOTAL |  |  |  | 3509.03
STEWARDING
Build stewarding security | Prestige | 6050 |  |  | 9am Thursday 6th - 9pm Sunday 16th. 300 hrs @ £12.50 per hour |  | ordered 29/06 |  | 2017-07-18 |  | ----------
satellite security | Prestige | 150 |  |  | 1 SIA 1500-1900 Monday, Weds & Thurs |  | ordered 29/06 |  | 2017-07-18 |  | ----------
Event stewarding | Prestige | 1612 |  |  | as per spreadsheet |  | ordered 29/06 |  | 2017-07-18 |  | ----------
Lost kids | Prestige | 126 |  |  | 2 staff for 4 hours | £15.75 per hour | ordered 29/06 |  | 2017-07-18 |  | ----------
STEWARDING SUB-TOTAL |  |  |  | 7938
H&S
Medical | Heart | 992 |  |  | inc treatment centre |  | ordered 28/06 |  |  |  | ----------
Fire extinguishers | TGPS | 50 | [8 empty] | 350
H&S SUB-TOTAL |  |  |  | 1042
TM
No waiting restrictions | Centurion | 500 |  |  | Sat 15th 0700-0000 |  | ordered 29/06 |  |  |  | 700
Missing cones | Centurion |  | 250 |  | ESTIMATE, charged at £5 per cone | [5 empty] | ----------
TM SUB-TOTAL |  |  |  | 500
FEES
Handling fee | TGPS | 1223.837 |  |  | 5% of all hires | [5 empty] | -----------------
FEES SUB-TOTAL |  |  |  | 1223.837
TOTALS Ex Contingency, Ex VAT |  | 25700.577
Contingency |  | 1299.423
TOTALS inc Contingency - EX VAT |  | 27000 | [8 empty] | 350956.76
TOTAL inc VAT |  | 26400