Blade Removal Draft Schedule

19th March 2017

16:00		Secure QVS

Set up cranes

Attach A Frame

Attach tip lifting cradle

17:30		Lift Blade onto SPMTs

19:00		Move Blade to Saville St and park

Dismantle tip & root supports

20th March 2017

00:01		Blade departs Savile St

QVS clear

01:30		Blade leaves Hull network, arrives on A63

04:30		Blade leaves A63, arrives King George Dock

05:30		A63 handover to Highways England