Land of Green Ginger Weekly catch up

14 July, Eastmount, Present: Katy, Gareth, Lou, Chrissie, Maddie, Elizabeth, Adam

Joshua

- Main issue: lack of volunteers; now resolved via a combo of freelancers and extra volunteers

  - Freelancer cost: £135 per day

- North Point paying for lunchtime concerts

  - ‘Mucky Mary’ creates a crowd

- 1st nose party is this Sunday *Lou to pick up cake from Jackson’s

- Crown had a tour of the space, so all the donors are quite happy at the moment

- Case: need to understand what Joshua has left to pay Nick; whatever’s left he should use to pay him, along with the money he’s set aside for his VIP guest and we’ll cover that instead *Lou to find out from Joshua

- Remaining items to pay for: bus, food and drink, interpretation, celebrity *Chrissie to draft interpretation and *Lou to respond to History Centre

Thor

- Have developed install plan a bit more

- *Lou to check in with Elinor re: M&E plan, and ask Thor to write/draw up plan, including schedule/update report

- Thor planning to come up two weeks before install and be based at Staples

- *Lou to send through budget update (she chatted with Sid yesterday)

- We still need to discuss Heralding Part II

- *Lou to get basic dimensions fo crate needs from Sid

  - It might be easier to purchase a basic shed and then modify it to look like a crate

- Duration of event

  - Need to sit down and figure out what's best and then discuss with Thor/Sid the audience management: timed entry, etc.

Davy

- They sent through updated budget and report for next payment

- Yorkshire Water: we need to provide them with RAMs and fire safety plan

  - We need a drawn plan before doing anything else. Davy's currently working on that.

  - Also venue agreement needed with them. *Maddie to draft.

- Adam to build from 3 August to build frameworks, power, etc, but he needs plan ASAP

- *Adam to work out budget, but he reckons he'll need another £5k. *Katy to source

Macnas

- Lou's started to put together a list of who to approach, but we need more staff to make it happen

  - Gathering info and contacting people will take time

  - We'll need someone preferably within the organisation

- Will also need 'team leaders/stage managers' within each sub group

  - Could also be a volunteer lead who could do this.

- End point: Fruit Market (Susan Edwards)

  - Looking at Plan B: Nelson Street: lots of space and nicer ground

  - Just a holding area, so could be somewhere else entirely. Could low-load it all and transport it to the start.

- Rehearsal space: Walton St? Or Premier Inn car park?

MarComms

- *Maddie to send Chrissie all Story So Far emails for Chrissie to coordinate

- Media call out when second crate appears in Pickering Park?

- *Lou to send photos of nose party to Chrissie to put on social media