We Made Ourselves Over – Blast Theory -  Hull UK City of Culture 2017

Project Plan

Background Blast Theory

Blast Theory is renowned internationally as one of the most adventurous artists’ groups using interactive media, creating groundbreaking new forms of performance and interactive art that mixes audiences across the internet, live performance and digital broadcasting. Led by Matt Adams, Ju Row Farr and Nick Tandavanitj, the group’s work explores the social and political aspects of technology. Drawing on popular culture and games, the work often blurs the boundaries between the real and the fictional.

We Made Ourselves Over continues Blast Theory’s concern with the social impact and opportunities of rapidly changing technology on the city and its people. They believe that new technology provides critical challenges and opportunities for cities in the future. It also allows them to create groundbreaking new forms of performance and interactive art to build rich conversations about the landscape of that city.

As in their work  The Thing I’ll Be Doing For The Rest Of My Life – a commission in Japan in 2013 the project builds on an inclusive research and creative development process, comprising interviews and workshops with local people and organisations to excavate the diverse economic, social and political experiences of the city and its history. Their experience in research projects working with partners in higher education and at research labs across the European Union will allow them to co-ordinate a unique collaboration between local communities and an interdisciplinary team of architects, urbanists and economists.

Their previous project Rider Spoke interleaves new perspectives of the city with audiences’ own experiences. First premiered at the Barbican in London in 2007 and subsequently shown in 20 cities around the world, Rider Spoke invites audiences to cycle through the city at night making recordings and listening to other people’s. It uses technology to give new ways for audiences to have a meaningful voice within the work.

Introduction – We Made Ourselves Over

We Made Ourselves Over is a science fiction project that takes its audiences on a journey into an imagined future. Blast Theory will work in partnership with diverse communities from Aarhus and Hull to develop a speculative vision of the world in 2097; employing writing, photography, mobile gaming and film to construct a provocative and personal set of stories from each city.

We Made Ourselves Over springs from the respective histories and insights of communities in each city while drawing on the work of economists, futurologists, technologists, climate scientists and architects to frame their common challenges in the face of global migration, technical innovation and climate change.

We Made Ourselves Over reflects on the capacity of people to adapt within the inevitable cycles of decay and renewal of a city, postulating a lifetime of changes that will transform the city in the coming century. Delving through time zones past and future, Blast Theory will deliver and screen a series of extraordinary films, alongside a programme of public events in each city from September to December 2017 using phone boxes, an app for smartphones and intimate face to face encounters across the city.

Partnership with Aarhus

Blast Theory will be commissioned by Hull 2017 and Aarhus European Capital of Culture. We Made Ourselves over is an exciting and unique opportunity to explore the link between Hull and Aarhus.

We Made Ourselves Over will run consecutively in both cities for ten weeks from Sept 2017. Prior to the project starting an extensive research period will take place with workshops in both cities and there will be the opportunity for five young people from each city to travel to the other as part of a Young People’s Exchange.

In the films Blast Theory will blend landmarks and historical references from the Aarhus and Hull into a single landscape, creating a simultaneous experience of otherness and familiarity. The rooftop paths on the warehouses of the West Dock on the Humber will spill down among the communities of containers in Godsbanen. The view from the tidal barrier on the Hull will take in Aarhus’s now decayed Iceberg apartments on the harbour front in one direction and the estates of Gellerup in the other, now crowded with wealthy residents keen to shelter from the forbidding coastline.

The launch of each new film will be announced simultaneously in both Hull and Aarhus. In Aarhus, the air-raid siren will sound throughout the city. At precisely the same moment in Hull, every phone box in the city will ring.

The Story of the City

Through We Made Ourselves Over Blast Theory will invite people to contribute to a new vision of the city, to unleash radical, poetic and playful ideas about what is possible and what the future might be. They will invite people to think in new ways about the life they lead and where they want their communities to go. It will frame the present within a longer historical cycle of economic decay and renewal, reflecting on loss, our sense of history and purpose, and on our capacity of resilience in the face of the unknown.

The narrative and creative vision of We Made Ourselves Over is inspired by the psychological landscapes of J.G. Ballard; describing the future through the personal struggles of individuals who live there.

The Development Process

Blast Theory will define opportunities of exchange between experts, innovators, cultural practitioners and audiences across the two cities during each phase of the project. Throughout, Blast Theory will adopt a common digital strategy which shares the research, development and presentation of the project under a single identity, aiming to provoke conversations between the cities and beyond to the wider world.

The City and Capital of Culture teams will provide a key role in building relationships within each city, linking the project to independent researchers and development groups, establishing relationships with community and youth groups and assembling a production team of local film-makers, visual artists, performers and makers to involve in the delivery of the final work. The project will begin in June 2016 and be live to the public in a ten week programme from September to early December 2017 to coincide with the City and Capital of Culture programmes’ shared goals of looking towards the future.

Delivery

Blast Theory will be responsible for the delivery of this commission and Sam Hunt is the project lead from Hull 2017. Hull 2017 will work closely with Blast Theory to identity and introduce them to local connections from community groups, local experts, production companies, and our volunteers. Blast Theory will be responsible for recruiting any additional staff they need to deliver the project. Blast Theory will be recruiting a marketing officer, marketing assistant and Community Liaison Officer to work specifically on the project and it will be important that they work closely with the Hull 2017 Marketing, Communities and legacy team.

Audience Engagement

Participation and inclusion are at the heart of the audience development plan for We Made Ourselves Over. Relationships will be nurtured throughout the life of the project; contributing to the voice of the final work and creating advocates for the public programme of the event.

Blast Theory’s Business Director Kirsty Jennings will take overall responsibility for delivery of the audience development plan, in partnership with the Blast Theory artists. Artist Ju Row Farr will lead in building creative conversations with audiences across the project, working in coordination with a dedicated Community Liaison Officer based in Hull to establish and grow relationships with groups in the city.

PR will be led by an independent consultant with Blast Theory Trustee, Ben Vickers – an expert in marketing from Bloomberg providing oversight.

A Marketing Officer, supported by a Marketing Assistant both recruited by Blast Theory will undertake the day-to-day implementation of the project’s social media strategy to reach audiences nationally and internationally. This social media strategy will address an international audience, framing the ideas raised by the project within a context of global concerns, creating stories that reflect on our common fate and enabling conversations through the project blog and social media.

Phase 1: Research

In the first six months of the project, Blast Theory will work with experts and researchers from Aarhus and Hull to reimagine the city across four key areas:

• The environment and climate change

• Global and local economies

• New technologies, city infrastructure and civic space

• Community, identity, family life and culture

Blast Theory will interview ten experts to give their insights on the challenges faced by each city – what they have in common and the impact of global changes in the coming century. These interviews will be videoed and shared online, providing an exchange of ideas and acting as a starting point and a provocation for workshops with communities from each city.

In co-ordination with the City and Capital of Culture Teams, we will undertake parallel sets of thought provoking workshops in each city, to present and discuss alternative scenarios for the future of the city. Taking a playful and personal approach, each group will be invited to think about their own lives in this future city; re-inventing their own communities, carrying forward what is important, writing stories of daily life, drawing up new city plans and designing a new horizon line for their neighbourhood.

• Group 1: Schools Workshops – Blast Theory will work with the City and Capital of Culture Teams to draw twenty students from diverse locations in each city. Material produced during these workshops will be shared online between the schools and to the wider public through the project website.

• Group 2: Young People’s Exchange – Blast Theory will offer the opportunity for five young people from each city to travel to the other. During their visit the young people take part in a workshop with local young people. They will be invited to imagine their neighbourhoods side by side in the city of thefuture, to share insights about their own communities and discuss their common ambitions.

• Group 3: Over 60s Interviews – Blast Theory will work with over 60s groups to delve into the recent past of each city, reflecting on how daily life and experiences of the city have changed and how they see the changes of the coming century might be met.

The research phase will also set out to explore potential relationships with creative collaborators for the project, including production designers, 3D artists, writers, storyboard artists, film crew, facilities houses and performers.

Phase 2: Film and Interactive Development

The research and workshops will lead to a phase of intensive creative development; interpreting and collating material from this process. In collaboration with production designers, 3D artists, and a scriptwriter, Blast Theory will develop a set of interlinked stories and characters set in an

imaginary city of 2097; each film introducing a new character from the city and setting up a dilemma that they face. Blast Theory will bring an imaginary future city to life using motion graphics and special effects to reimagine the city as never before; developing storyboards for five films, scripts for a series of interactive phone calls and for intimate face-to-face encounters across the city.

Participants from the workshop phase and a wider public from both cities will be invited to suggest and photograph potential locations for the films.

This phase will also include technical development for a smartphone app, an interactive phone platform and two site visits to each city to scout locations, cast and rehearse with key cast members, plan for camera tracking and effects compositing and to shoot test material.

Phase 3: Filming and Final Production

Blast Theory will recruit and cast a production team for the film shoot. Key cast members and crew will travel between the cities to film in both locations, with Blast Theory inviting participants from communities on location to watch and potentially take part in the production.

Shot in 4K, an experienced effects team with a track record of work in television and feature films will use 3D compositing and camera tracking to embed environments and characters into the world of the film, joining neighbourhoods and landmarks from the present day in both cities into a single imaginary city of the future.

Phase 4: The Public Event

We Made Ourselves Over will launch as an immersive citywide event beginning in September 2017 in both cities and lasting for ten weeks.

The Films

Five films will be released over ten weeks - one each fortnight. The launch of each new film will be announced simultaneously in both Hull and Aarhus. In Aarhus, the air-raid siren will sound throughout the city. At precisely the same moment in Hull, every phone box in the city will ring.

In each city, a specially adapted truck will tour neighbourhoods to screen the films during the ten weeks. Acting as a projection platform, the truck will turn walls and billboards across the city into temporary screens. Neighbourhoods will be transformed as residents, visitors and passersby gather under the stars to watch as each new film premieres.

In Aarhus, Blast Theory will liaise with the Capital of Culture team to use electronic displays in train stations and on buses to catch commuters on their journeys to work, while a special screening of all the films will be made for delegates at the Creativity World Forum in November. In Hull, Blast Theory will co-ordinate screenings with public events such as Hull City Fair and during football matches at the KC stadium.

The films will be short, shareable and provocative; distributed online as well as within the city. Remapping familiar locations and landmarks from diverse neighbourhoods in both cities, each film will reveal a new aspect of the imaginary city and its story. Each film will be told as fact from the point of view of 2097 - sometimes voiced as personal reportage, at other times, in the guise of advertising or public information films. On its own, each film will encapsulate an idea of how people might live in the future, providing a visually rich re-imagining of the city for sharing and discussion across social media. But it will also be a call to action; setting up a character and a dilemma as a prompt to engage with the story world further via interactive phone calls and a smartphone app.

At the end of each fortnight, participants will be have the chance to be drawn further into the project – being carried away by one of a fleet of electric cars roaming the city; taking them on a remarkable and unforgettable journey of reflection into the future.

Interactive Phone Calls

As each new film is launched, so is an interactive phone call with the character from that film. Each film will be a call to action to enter the world of the film. Viewers in each city will be invited to call a phone number. At the end of the line is a character from 2097, pleading for your help. As you interact with them, you become a protagonist in their life. Help them with the dilemma they face – give them advice, record your thoughts and help them to reach a decision about the future. Audiences who’ve called the number will receive a call when each subsequent film is launched. Phone lines will be open 24 hours a day and seven days a week during the ten weeks of the event, allowing the public to explore the world of the project at anytime by calling in. In Hull, participants will also be able to call in from any one of the city’s white phone boxes.

The Smartphone App

Available globally, the smartphone app will present the films released each fortnight and allow participants to make an interactive video call into the future. One interactive video call is released to accompany each film. Framed FaceTime style, each video will feature a character from one of the films, allowing you to interact with them, giving an intimate first person window into their world and their view of the city and inviting you to help decide their future.

The app for smartphones will draw on Blast Theory’s recent award winning Karen app; building on the team’s experience in scripting compelling interactive video, and leveraging technology for delivering interactive full-screen video to mobile devices.

Project Timeline

Phase 1 - Research & Pre Production (June – Dec 2016)

Phase 2 - Film and Interactive Development (Jan – Mar 2017)

Phase 3 – Filming and final production (Apr – Aug 2017)

Phase 4 – Public Event (Sept - Dec 2017)

Phase 5 – Legacy (Dec 2017 onwards)