Turner Prize Events Meeting
29.09.2017

Katy Fuller, Ben McKnight, Jenny Hutt, Chris Clay, Rebecca Clark, Ben McKnight, Anneli Shearsmith, Jane Birch, Sue Nix, Alison Kee, Melanie Fanstone, Lorrie Fay, Eimear McNamara, Krishna Khakhria, Andrew Swann, John Wilmott, Ruth (Tate)

Apologies: Sara Black, Lily Mellor

SCHEDULE

- 04/12/2017 - Ferens Art Gallery scheduled to close at 16:30 as usual
John asked whether the rig can be put in place ahead of Monday 05/12
KF to request late opening on 04/12

- 05/12/2017 - Ferens to be closed early to rig and test - TBC 
Guests to privately view exhibition prior to presentation at Minster – timings TBC

KF to confirm whether Ferens exterior can be lit 05/12
KF to confirm whether Ferens closure is possible 05/12

- Minster

19:00 – Drinks
19:45 - 200 x guests seated for two course dinner
21:41 – Speeches (3 speakers max) 
           Time for reaction to winner being announced - TBC

21:56 – Programme finishes
22:00 – Winner joins Will Gompertz at Ferens Art Gallery for News at 10

Schedule TBC - to include choreographing guests

- Invite list to be finalised – list from Tate to JH no later than 20/10/2017

- Dinner scheduled at Minster on 10/11/2017 - BBC invited to view venue dressed for an event month before Turner Awards Dinner

COVERAGE

- BBC would like music by Hull artists, highlights of contemporary music scene. 
KF to speak to SH for suggestions and send to Alison

- Anneli Shearsmith confirmed the BBC truck will be parked to the rear of Ferens and cabling will come through the back

- BBC to embed Rosalind’s film - KF to speak to curators re: Rosalind’s film

- Curators to be available to talk about the artists, split the curators:
GV responsible for Andrea Buttner and Rosalind Nashashibi 
SC responsible for Lubaina Himid and Hurvin Anderson

- Confirm footage of Hull – Fruit Market, The Deep etc. KF to share suggestions