## production schedule
DAY/DATE | TIME | DETAIL | NOTES | WHO | COMPANY | CREW REQD | VEHICLES
Weds 5th July | am | collect trailer from Beverley | Take to staples and load pallets on | AL | TGE |  | Van
Thurs 6th July | 800 | Adam on site | collect keys, check ground, site handover. Deliver pallets and trailer | AL | TGE
| 900 | security on site |  |  | Prestige
| 900 | fencing delivered |  |  | Actavo
| 900 | Forks delivered | with man basket |  | Add plant
| 900 | toilets delivered | in production compound |  | Add plant
| am | Generators delivered |  |  | John F Hunts
| am | Bins delivered |  |  | Hull CC
| 1000 | crew on site | mark out road way build production compound and bonfire compound. Lay turf |  | TMC | 2
| 1000 | marquees built | in production compound |  | Nationwide
| am | And Now on site | mark out, start collecting wood |  | And Now
| 1200 | Scaff delivered | For Putlog |  | Actavo
| pm | Bowser delivered | need to fill |  | GAP
| pm | steel store delivered |  |  | Add plant
| 2100 | security Handover |  |  | Prestige
Fri 7th July | 900 | on site |  | And Now/AL
| 900 | security Handover |  |  | Prestige
| 900 | access to East Mount required |  | All | All
| 1000 | crew on site | finish off |  | TMC | 2
| am | begin bonfire build | continue with wood deliveries | And Now | And Now
| 2100 | security changeover |  |  | Prestige
Sat 8th July | 900 | on site |  | And Now/AL
| 900 | security Handover |  |  | Prestige
| 900 | access to East Mount required |  | All | All
| am | begin bonfire build | continue with wood deliveries | And Now | And Now
| 2100 | security changeover |  |  | Prestige
Sun 9th July | 900 | on site |  | And Now/AL
| 900 | security Handover |  |  | Prestige
| 900 | access to East Mount required |  | All | All
| am | continue bonfire build | continue with wood deliveries | And Now | And Now
| am | mark out Putlog positions | also stage and FOH | And Now/AL | TGE
| am | begin putlog |  | AL | TGE
| 2100 | security changeover |  |  | Prestige
Mon 10th July | 900 | on site |  | And Now/AL
| 900 | security Handover |  |  | Prestige
| 900 | access to East Mount required |  | All | All
| am | continue bonfire build | continue with wood deliveries | And Now | And Now
| am | backstage toilets serviced |  |  | Add plant
| 1500 | Set-up at Cam Grove | samovar & gazebo | And Now/AL | And Now
| 1500 | SIA at Cam Grove |  |  | Prestige
| 1900 | Finish at Cam Grove |  | And Now/AL | And Now
| 2100 | security changeover |  |  | Prestige
Tues 11th July | 900 | on site |  | And Now/AL
| 900 | security Handover |  |  | Prestige
| 900 | access to East Mount required |  | All | All
| am | continue bonfire build |  | And Now | And Now
| am | continue Putlog |  | AL | TGE
| am | collect radios | from Hull 17 | AL | TGE
| 2100 | security changeover |  |  | Prestige
Weds 12th July | 900 | on site |  | And Now/AL
| 900 | security Handover |  |  | Prestige
| 900 | access to East Mount required |  | All | All
| am | continue bonfire build |  | And Now | And Now
| am | backstage toilets serviced |  |  | Add plant
| 1500 | Set-up at Limerick Close | samovar & gazebo | And Now/AL | And Now
| 1500 | SIA at Limerick Close |  |  | Prestige
| 1900 | Finish at Limerick Close |  | And Now/AL | And Now
| 2100 | security changeover |  |  | Prestige
Thurs 13th July | 900 | on site |  | And Now/AL
| 900 | security Handover |  |  | Prestige
| 900 | access to East Mount required |  | All | All
| am | continue bonfire build |  | And Now | And Now
| am | begin site lighting install |  | AL | TGE
| 1500 | Set-up at Weaver Grove | samovar & gazebo | And Now/AL | And Now
| 1500 | SIA at Weaver grove |  |  | Prestige
| 1900 | Finish at weaver grove Close |  | And Now/AL | And Now
| 2100 | security changeover |  |  | Prestige
Fri 14th July | 900 | on site |  | And Now/AL
| 900 | security Handover |  |  | Prestige
| 900 | access to East Mount required |  | All | All
| am | finalise bonfire build |  | And Now | And Now
| 1000 | Production meeting | at East mount | AL, KF, GH, MM, EB, LY
| 1000 | crew on site | continue site lighting install and assist 3d |  | TMC | 2
| 1100 | 3d on site | install pa, stage and FOH | 3d | 3d productions | 2
| pm | soundchecks |  |  | 3d productions
| pm | rehearsals |  |  | And Now/community
| pm | rope off fallout area |  | AL | TMC | 2
| evening | Tech/Dress rehearsal | Check site lighting | All
| 2100 | security changeover |  |  | Prestige
Sat 15th July | 700 | no waiting cones put out |  |  | Centurion
| 900 | on site |  | And Now/AL
| 900 | security Handover |  |  | Prestige
| 900 | access to East Mount required |  | All | All
| 900 | begin pyro install | 4 SIA required |  | And Now
| 900 | audience toilets on site | Put in East Mount Car park |  | Add plant
| am | backstage toilets serviced |  |  | Add plant
| 1000 | crew on site | finalise site and dressing |  | TMC | 2
| pm | rehearsals
| 1900 | final on site checks
| 1900 | Medical on site | put unit in car park |  | Heart
| 2000 | Show stewarding begins |  |  | Prestige
| 2130 | Event starts |  | ALL | All | 2
| 2230 | Event finishes |  | ALL | All | 2
| 2230 | PA & structures out |  |  | 3d productions | 2
| 2300 | security changeover |  |  | Prestige
| 2359 | no waiting cones removed |  |  | Centurion
Sun 16th July | 900 | security Handover |  |  | Prestige
| am | audience area cleaned |  |  | Hull CC
| am | de-rig bonfire, tidy |  |  | And Now
| am | audience toilets removed
| 1000 | crew on site | de-rig site lighting |  | TMC | 2
| am | audience toilets removed
| 1200 | de-rig bonfire compound | Put turf in skip |  | TMC | 2
| pm | continue tidy
| 1600 | And Now off site
| 1630 | Marquee derigged |  |  | Nationwide
| 1730 | derig production compound |  |  | TMC | 2
| 1800 | Finish |  |  | TMC | 2
| 2100 | security changeover |  |  | Prestige
Mon 17th July | 900 | security Handover |  |  | Prestige
| am | final site cleanse |  |  | Hull CC
| 1000 | crew on site | final tidy, stack barriers etc |  | TMC | 2
| am | skip collected |  |  | Whites skip hire
| am | fencing collected | and scaffolding |  | Actavo
| am | gens collected |  |  | John F Hunts
| am | telehandler off site |  |  | Add plant
| am | toilets off site |  |  | Add plant
| am | container off site |  |  | Add plant
| am | bowser collected |  |  | GAP
| pm | final tidy & handover |  | AL
| pm | return radios |  | AL
| 1800 | security finish |  |  | Prestige
| 1800 | Adam off site

## production contacts
NAME | COMPANY | WHAT | MOBILE NUMBER
Adam Long | TGE | Prodction manager | 07754 728316
Katy Fuller | Hull 17 | Exec producer | 07771 764656
Gareth Hughes | Hull 17 | Event manager | 07733 112272
Maddie Maughan | Hull 17 | Producer | 07738 822568
Louise Yates | Hull 17 | Producer | 07753 171181
Elizabeth Bergeron | Hull 17 | Producer | 07702 922475
Mandy Dike | And Now | Artist | 07967 021042
Ben Rigby | And Now | Artist | 07855 437950
Sarah Harris | Hull 17 | Volunteer co-ordinator | 07445 987464
Steve McKee | Hull cc | Cleansing | 07789 372506
Brian | Nationwide | Marquee Hire | 07775 515398
Jean Byers | John F Hunt | Generators | 0191 4111200
Joy Whitley | Actavo | Barriers & fencing | 01652 601390
Paul | Heart Medical | Medical | 07764 926970
Justine peacocock | Prestige | Stewarding & child protection | 07886 838597
Jon Masters | Add Plant | toilets & plant | 07738 817940
Rona | The Music consortium | local crew | 01977 659874
Olivia | White skip hire | Skip & turf | 01482 227468