## Sheet1
Date likely to change | Complete
Incomplete |  | 2016-04-01 |  |  |  | 2016-05-01 |  |  |  | 2016-06-01 |  |  |  | 2016-07-01 |  |  |  | 2016-08-01 |  |  |  | 2016-09-01 |  |  |  | 2016-10-01 |  |  |  | 2016-11-01 |  |  |  | 2016-12-01 |  |  |  | 2017-01-01 |  |  |  | 2017-02-01 |  |  |  | 2017-03-01 |  |  |  | 2017-04-01 |  |  |  | 2017-05-01 |  |  |  | 2017-06-01 |  |  |  | 2017-07-01 |  |  |  | 2017-08-01 |  |  |  | 2017-09-01 |  |  |  | 2017-10-01 |  |  |  | 2017-11-01 |  |  |  | 2017-12-01 |  |  |  | 2018-01-01 |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01
Activity | Lead | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Establish timeline for delivery. | Martin A | bar: 2016-04-01 3
Meet with Luke to talk timeline, contract, proposal and budget. | Sam/Martin | bar: 2016-04-01 4
Meet with steering group comprised of Uni, Riba and British Council to discuss proposal. | Martin/Sam/Luke | bar: 2016-05-01 1
Commision initial articles with reference to the discussion about the north and confirm project outline. | Luke/Martin/Sam | bar: 2016-05-01 4
Receive a detailed project budget from Luke | Luke/Martin/Sam | bar: 2016-05-01 3
Confirm project budget with Luke | Luke/Martin/Sam | bar: 2016-05-01 4
Confirm content outline of festival with partners. | Sam/Luke/Martin | bar: 2016-05-01 4
R&D agreement agreement to release some initial funds if required. | Martin/Sam | bar: 2016-05-01 2
Contract with reference to timeline and budget | Martin/Sam | bar: 2016-05-01 2
First Payment of £25k | bar: 2016-06-01 1
Meeting with Digital and Marketing team at Hull2017 to discuss Substance's digital platform and how that can work with 2017's digital platform. | David/Martin/Sam/Luke/Phil | bar: 2016-05-01 1
Have lead image and copy ready. | bar: 2016-06-01 3
Begin build of Substance on the Discover section of the 2017 website with Hull2017 team. | bar: 2016-06-01 3
Second payment of £25k | bar: 2016-07-01 1
Begin build of website for Substance post 2017. | Luke | bar: 2017-12-01 1
Pencil peripheral venues for 8-10 December | Martin/Luke/Production | bar: 2016-06-01 3
Contract contirbutors online editorial, print editorial and other publications. | bar: 2016-09-01 1
Confirm a timeline of all contributions and activity pre festival with Hull2017 team | bar: 2016-09-01 1
Revisit budget off the back of contracting fr content. | bar: 2016-09-01 1
Third payment of £25k | bar: 2016-10-01 1
Release booklet with articles by artists working in the north. | bar: 2017-06-01 4
Contract all performers for the December weekend. | Luke | bar: 2017-04-01 2
Have all marketing material ready for first announcement | Luke/Martin/Sam | bar: 2016-06-01 4
Fourth payment of £25k | bar: 2017-03-01 4
Have all marketing material ready for full programme announcement | Luke | bar: 2017-04-01 1
Pre Activation Event: Hull | bar: 2016-10-01 1
Pre Activation Event: | bar: 2017-01-01 3
Pre Activation Event: Hull | bar: 2017-04-01 1
Pre Activation Event: | bar: 2017-07-01 1
Pre Activation Event: Hull | bar: 2017-09-01 1
Fifth Payment of £25k | bar: 2017-12-01 3
Pre Activation Event: | bar: 2017-11-01 1
Substance Festival | Luke/Sam | bar: 2017-12-01 2