| Name of Individual / Organisation | Artlink Centre for Community Arts |
| --- | --- |
| Name of Project | How to Listen |

Please provide a breakdown of key activities /tasks for your project from start to finish. Please include your preparation and planning activity as well as start / end dates of your public activity (eg. public performance, exhibitions, festival).

| START DATE | END DATE | ACTIVITY / TASK | STATUS | NOTES |
| --- | --- | --- | --- | --- |
|  |  |  | COMPLETE / ON-TIME / BEHIND |  |
| July 2016 | August 2016 | Confirmation of venues and artists. Following the outcome of the application the arts development worker will confirm dates with venues for the screening of the film. Project will be entered into the 2017 brochure |  |  |
| 1st March 2017 | 1st May 2017 | Workshops Workshops begin with established groups and permission forms will be collected. |  |  |
| 1st May 2017 | 1st June 2017 | Interviews Audio files submitted to Artlink and transcribed by volunteers. |  |  |
| 1st July 2017 | 1st September 2017 | Creation of new artwork Brief to be written and issued to artist for the creation of the animated film |  |  |
| 1st July 2017 | 31st October 2017 | Promotion We will start to promote the project on social media, websites and through leaflets. The project will also be in the Artlink 2017 brochure which will be distributed throughout the year. |  |  |
| 1st October 2017 | 31st October 2017 | Exhibition Exhibition of work in Artlink’s Pocket Gallery |  |  |
| 22nd October 2017 | 22nd October 2017 | Celebration event Event to celebrate the achievements of the project participants |  |  |
| 1st October 2017 | 31st October 2017 | Public screenings KC lightstream stadium and other venues |  |  |
| 1st November 2017 | 30th November 2017 | Evaluation Team members will evaluate the project |  |  |

Activity Examples: Planning Meeting, Auditions, Contracting, Rehearsal, Costume Design, Performances