LOGG WEEKLY ACTIVITY UPDATE

|  | PUBLIC FACING EVENTS/MOMENTS | INTERNAL | PRESS | DIGITAL | OTHER |
| --- | --- | --- | --- | --- | --- |
| Monday 5 June | A large stack of crates is delivered to Northpoint Atrium by GGF (including ginger smelling one) | Weekly catch up |  |  |  |
| Tuesday 6 June |  |  |  |  |  |
| Wednesday 7 June | Crate disappears |  |  | GGF open the crate, which is full of noses from last year |  |
| Thursday 8 June |  | Budget catch up Aswarm MarComms chat Macnas catch up |  |  |  |
| Friday 9 June | Crates start disappearing into shop |  | HDM print article about the noses being found / can now reveal a space at NP will be nose house for showing the gold nose temp until Aug. |  |  |
| Saturday 10 June |  |  |  |  |  |
| Sunday 11 June |  |  |  |  |  |

Updates

Lone Twin

- And Now: contract is nearly finalised

- Licence notice has been confirmed for Lone Twin activity week and finale

- GH writing EMP for Guild of Commoners

Davy

- Springhead Pumping Station now confirmed as venue for McGuire’s Cardboard City

- Garth West have agreed to supply all cardboard for Cardboard City, following a meeting with Davy and Elizabeth, and are very excited by the project

- McGuires filming in Hull now due to take place in August (instead of June). Participants are currently being identified.

Joshua

-Pamphlet getting finalized

-RAMS nearing completion

-Sponsorship confirmed with Jackson’s and North Point

-GH liaising with JS re: sound

-Schedule for 17th finalized

-M&E discussions around documentary occurring

Thor

-GH working on Yorkshire Water sponsorship

-EB scheduling recording sessions with JM, LY and Roisha

Overdue

-Periplum’s final budget breakdown and final payment

-Walk the Plank’s final budget breakdown and final payment

-Macnas contract draft

Key Dates:

17 June: Gold Nose of Green Ginger shop opens at North Point

3 – 6 July: Project VEAR voice collection

12 – 16 July: Project VEAR voice collection

9 – 15 July: Guild of Commoners activity live in Longhill

15 July: And Now bonfire, Longhill

19 August: Gold Nose of Green Ginger closing procession at North Point

6 – 9 September: Project VEAR voice collection

22 – 30 September: Project VEAR live at Pickering Park

20 October – 5 November: Cardboard City live at Springhead Pumping Station

11 November: Macnas parade in Old Town