## DRAFT SCHEDULE
| PHIL QUESTIONS: |  | WHEN/WHERE IS VIDEO STING HOSTED/RELEASED? |  | Helen to add in
|  |  | WHERE IS LEAFLET PRINT DELIVERED/DISTRIBUTED? WHAT IS THE PRINT RUN? |  | get-in times/company info
HULL TAKEOVER |  |  | WHAT IS THE PLAN FOR DIGITAL? |  | accessible shows (curious directive
DRAFT SCHEDULE |  |  | WHEN DO Fringe Ads GO LIVE, WHATS THE SIGN OFF PROCESS WITH ME? |  | fringe events worth going to/BC networking
Kofi, and press plans
awards/fringe deadlines
MONTH | DATE | TIME | WHAT | WHERE | WHO | Notes
JUNE | iminent |  | Press Release drafting/sent out |  | Helen/Ben/Alix/Cornershop
| 22nd |  | Phil Confirming Summerhall Hull Hangout |  | Phil
| 23rd |  | Confirm Schedule for Volunteers on Royal Mile |  | Phil/Helen/Harriet/Rachael
| 26th |  | Deadline for Marketing Form and Raw Footage. Send to designer. curious directive need Flyer banner graphic by this date. |  | Helen/Companies/Phil
| 27th |  | Companies begin emailing programmers. |  | Helen/Phil
|  | 4-5pm | Project Team Meeting | Danish 3 |  | Tom Stevens - Designer for Leader board ad.
| 28th | TBC | Confirm Volunteers plans and details for Royal Mile: meeting |  | Helen/Rachel/Phil | Print Run: 10k: 5k - shows; 5k - volunteers;
JULY | 3rd |  | Helen sending e-invite to industry/programmers. Deadline: E-Banner designed and sent to companies. |  | Helen
| 5th |  | Deadline: Flyer Mock Up to companies |  | Designer/Helen
| 7th |  | Deadine: Feedback to Graphic Designer on Flyer Mock Up
| 8th |  | Register with Arts Industry Accreditation, deadline 11th July. |  | Helen/Companies/Lindsey
| 10th | TBC | Jack from CD is in Hull (10th-12th). Photoshoot with 5 companies. Meeting with Rachel and Phil and companies. |  | Bethany/Helen
|  |  | Deadline: Leaflet Mock Up to 2017 |  | Designer/Phil/Helen
| 11th |  | Deadline for Arts Industry Accreditation
| 13th |  | Hull Hangout confirmed and finalised plans
Flyer Design reworked and sent to co's
| 14th |  | Flyer Amends to Designer |  | Designer/Companies/Helen
|  |  | Leaflet Feedback to Designer |  | Designer/Phil/Helen/Companies
| 15-17th |  | Flyer sign off from co's
| 20th |  | Deadline: Final Proof of combined Leaflet to companies and 2017 |  | Designer/Phil/Helen/Companies
|  |  | Deadline: Sting Edit |  | Filmmaker/Phil/Helen
DROP DEAD DAY FOR FLYER
| 24th |  | DROP DEAD DAY FOR LEAFLET
| 25th |  | Feature Article on 2017 Website |  | Phil/Helen/Digital
Begin beer mats design process?
| 26th |  | SILENT UPROAR/BELLOW FLYERS MUST BE DELIVERED TO EDFEST VENUES: The Pleasance
| 27th |  | Silent Uproar Preview at Truck | Hull Truck | Helen
| 28th |  | Deadline: Sting Final Sign Off. |  | Filmmaker/Phil/Helen
Deadline for beer mats final design.
|  |  | Meeting about Volunteering Plans TBC. Companies Collect Merchandise from 2017. | Hull | Rachael/Harriet/Phil/Helen
| 29th |  | PCP FLYERS MUST BE DELIVERED TO EDFEST VENUES: Paradise Green
| 31st | 10-12pm | Bellow and Silent Uproar Get-in | Pleasance B1 | Helen
AUGUST | 1st |  | Beer/Wine/Beer mats delivered to Summerhall.
|  | 7pm-11pm | Middle Child Get-in
| 2nd |  | Hull Hangout begins with companies
|  | 9am-1pm | Middle Child Tech
3rd
4th
| 5th | TBC | Meeting with all companies TBC. Bellow Press Night. | Summerhall
6th
| 7th | 4am-11pm | Volunteers on The Royal Mile | The Royal Mile | Rachael/Harriet/Phil/Helen/Companies | See schedule
|  | 7pm | Middle Child Press Night
8th
| 9th |  | Middle Child Captioned Performance
10th
11th
12th
13th
| 14th |  | Bellow Captioned Performance.
15th
| 16th |  | Middle Child Captioned Performance
17th
18th
19th
20th
| 21st | TBC | British Council Week Opening Party
22nd
| 23rd |  | Trade Fair 11-3pm with Hull Truck/2017 |  |  | Networking Breakfasts Throughout TBC
Middle Child Captioned Performance
| 24th |  | Silent Uproar Captioned Performance
25th
26th
| 27th | TBC | British Council Week Closing Party
28th
29th
30th
31st

## FLYER LEAFLET DEADLINES
|  | COMPANY FLYERS DEADLINES | COMBINED LEAFLET DEADLINES
JULY | 5 | Mock Up sent to co's
| 7 | Feedback to designer from co's
| 10 |  | Mock up sent to 2017
| 13 | Design reworked and sent to co's
| 14 | Amends to designer | Leaflet Feedback/Amends to Designer
| 15-17 | Sign off from co's
| 20 | Drop Dead Day - send to print | Deadline: Final Proof of combined Leaflet to companies and 2017
| 24 |  | Drop Dead Day - send to print
| 26 | Print DELIVERED to venue