## AndNow
Item | Supplier | Cost ex vat | option costs | Sub Totals Ex VAT | Description | Notes | Where we're at | More notes ??/?? | INVOICE RECEIVED | INVOICE PAID | Insurance values
LIGHTING
Entry/exit lighting | TGPS | 400 |  |  | festoon
backstage lighting | TGPS | 100 |  |  | some floods on stands
LIGHTING SUB-TOTAL |  |  |  | 500
AUDIO
Performance pa | 3d productions | 1562.02 |  |  | Ground stacked v system with in fills | inc crew, radio mics etc | received quote 23/06
delivery | 3d productions | inc above |  |  |  |  | received quote 23/06
FOH | 3d productions | ??? |  |  |  |  | received quote 23/06
AUDIO SUB-TOTAL |  |  |  | 1562.02
STRUCTURES
Backstage tent | Nationwide | 465 |  |  | 6m x 9m |  | requested new quote 22/06
Furniture | Nationwide | 66.5 |  |  | 20 x chairs, 10 x trestles |  | requested new quote 22/06
delivery/collection | Nationwide | 250 |  |  | Delivered Thursday 7th, collected Monday 17th |  | requested new quote 22/06
possible brass band stage | 3d | 572.3 |  |  | 24' x 20' c/w treads | Us to provide 2 local crew to assist | requested new quote 22/06
STRUCTURES SUB-TOTAL |  |  |  | 1353.8
POWER & DISTRO
Backstage/show power | John F Hunts | 135 |  |  | 40KVA |  | received quote 23/06
Entry exit power | John F Hunts | 250 |  |  | 2 x 20KVA | For festoon | received quote 23/06
tank | John F Hunts | 25 |  |  | For 40KVA |  | received quote 23/06
Fuel | John F Hunts | 700 |  |  |  |  | received quote 23/06
Delivery/collection | John F Hunts | 1120 |  |  | Delivered Thursday 6th, collected Monday 17th |  | received quote 23/06
Distro | TGPS | 100 |  |  | As required
Tower lights | John F Hunts | 240 |  |  | 2 x LED tower |  | received quote 23/06
POWER & DISTRO SUB-TOTAL |  |  |  | 2570
PLANT & BARRIERS
Ped barrier | Actavo | 412.5 |  |  | 150 panels of ped |  | requested new quote 22/06
Heras | Actavo | 180 |  |  | 60 panels of Heras | with double clips | requested new quote 22/06
Scaff | Actavo | 32.4 |  |  | 60 x 5' scaff poles | Putlog | requested new quote 22/06
Scaff | Actavo | 91.2 |  |  | 60 x 14' poles | extensions | requested new quote 22/06
Scaff | Actavo | 8.16 |  |  | 120 x swivels |  | requested new quote 22/06
Delivery/collection | Actavo | 200 |  |  | Delivered Thursday 6th July, collected Monday 17th |  | requested new quote 22/06
Telehandler | Add Plant | 275 |  |  | 9m telehandler |  | received quote 19/05
Man basket | Add Plant | 50 |  |  |  |  | requested quote 19/05
Fuel | Add Plant | 50 |  |  |  |  | received quote 19/05
Delivery/collection | Add Plant | 160 |  |  |  |  | received quote 19/05
Container | Add Plant | 48 | 48 |  | 20' container for storage of pyro | Maybe able to use existing one? | received quote 19/05
delivery/collection | Add Plant | 100 | 100 |  | Delivered Saturday 8th July, collected Monday 17th |  | received quote 19/05
PLANT SUB-TOTAL |  |  |  | 1607.26
CREW
Pre get-in crew | The Music Consortium | 247.2 |  |  | 2 men Thursday 7th 1000-1800 | Lay turf, fencing etc | requested updated quote 22/06
Get-in crew | The Music Consortium | 618 |  |  | 2 men Fri 14th 1000-1800, Sat 15th 1100-2300 | To do putlog, scaff, Fencing etc | requested updated quote 22/06
Get-out crew | The Music Consortium | 370.8 |  |  | 2 men Sun 1000-1800 & 2 men Mon1000-1400 |  | requested updated quote 22/06
CREW SUB-TOTAL |  |  |  | 1236
MISCELLANEOUS
Turf | Whites skip hire | 540 |  |  | 144m2 of turf, to lay on top of existing turf | 12m x 12m @ £3.75 per sq.m. | received quote 19/05
Hessian | Hull 17 | 0 |  |  | 200m | use from periplum
Rope | Hull 17 | 0 |  |  | For front line | use from periplum
Road Pins | Hull 17 | 0
Rope | Hull 17 | 0
Urn | Hull 17 | 0
Cooking eqpt |  | ?? |  |  | Check what they want
Catering eqpt | Hull 17 | 0 |  |  | tea, coffee, cups etc
Consumables |  | 100
comms | Hull CC | 0 |  |  | Radios | using channels 9-12 back to back
Cleansing |  | 250 |  |  | Sweep on Sunday afternoon/Monday morning |  | requested quote 13/06
Bins |  | 222 |  |  | 3 x 1100l bins |  | received quote23/06
Skip | Whites skip hire | 216.67 |  |  | 14 cubic yard |  | received quote 19/05
Backstage toilets | Add Plant | 100 |  |  | 2 x single plastic units | delivered Sun 9th, collected Sunday 16th | received quote 19/05
Servicing | Add Plant | 150 |  |  | serviced Tues 11th, Thurs 13th & Sat 15th |  | received quote 19/05
Public toilets | Add Plant | 1240 |  |  | 20 singles plus 3 accessible units |  | received quote 19/05
delivery/collection | Add Plant | 320 |  |  |  |  | received quote 19/05
water bowser | GAP | 70 |  |  |  |  | received quote 23/06
Delivery & collection | GAP | 70 |  |  | delivereurs 6th, collected Mon 17th |  | received quote 23/06
MISCELLANEOUS SUB-TOTAL |  |  |  | 3278.67
STEWARDING
Build stewarding security | Prestige | 5175 |  |  | 9am Thursday 6th - 9pm Sunday 16th. 300 hrs @ £12.50 per hour | 1 staff 0900-2100, 2 staff 2100-0900 | requested new quote 22/06
Event stewarding | Prestige | 1387 |  |  | as per spreadsheet |  | requested new quote 22/06
Lost kids | Prestige | 126 |  |  | 2 staff for 4 hours | £15.75 per hour | requested new quote 22/06
STEWARDING SUB-TOTAL |  |  |  | 6688
H&S
Medical | Heart | 992 |  |  | inc treatment centre |  | received initial quote 19/05
Fire extinguishers | TGPS | 50 | [8 empty] | 350
H&S SUB-TOTAL |  |  |  | 1042
TM
No waiting restrictions | Centurion | 500 |  |  | Sat 15th 0700-0000
Missing cones | Centurion | 250 |  |  | ESTIMATE, charged at £250
TM SUB-TOTAL |  |  |  | 750
FEES
Handling fee | TGPS | 1029.3875 |  |  | 5% of all hires | [5 empty] | -----------------
FEES SUB-TOTAL |  |  |  | 1029.3875
TOTALS Ex Contingency, Ex VAT |  | 21617.1375
Contingency |  | 5382.8625
TOTALS inc Contingency - EX VAT |  | 27000 | [8 empty] | 350
TOTAL inc VAT |  | 26400

## Lone Twin
Item | Supplier | Cost ex vat | option costs | Sub Totals Ex VAT | Description | Notes | Where we're at | More notes 08/04 | INVOICE RECEIVED | INVOICE PAID | Insurance values
LIGHTING
LIGHTING SUB-TOTAL |  |  |  | 0
AUDIO
AUDIO SUB-TOTAL |  |  |  | 0
STRUCTURES
STRUCTURES SUB-TOTAL |  |  |  | 0
POWER & DISTRO
POWER & DISTRO SUB-TOTAL |  |  |  | 0
PLANT & BARRIERS
PLANT SUB-TOTAL |  |  |  | 0
CREW
CREW SUB-TOTAL |  |  |  | 0
MISCELLANEOUS
MISCELLANEOUS SUB-TOTAL |  |  |  | 0
STEWARDING
STEWARDING SUB-TOTAL |  |  |  | 0
H&S
Fire extinguishers | TGPS | 50 | [8 empty] | 350
H&S SUB-TOTAL |  |  |  | 50
TM
TM SUB-TOTAL |  |  |  | 0
FEES
Handling fee | TGPS | 2.5 |  |  | 5% of all hires | [5 empty] | -----------------
FEES SUB-TOTAL |  |  |  | 2.5
TOTALS Ex Contingency, Ex VAT |  | 52.5
Contingency |  | 4947.5
TOTALS inc Contingency - EX VAT |  | 5000 | [8 empty] | 350
TOTAL inc VAT |  | 6000