IN WITH A BANG / MADE IN HULL COORDINATION MEETING

Thursday 24th November 2016, 14:00

Attending: Chris Clay, Melissa McVeigh, Justine Peacock, Niccy Hallifax, Zoe Snow, Kate Doyle

Apologies: Sam Hunt

| POINT | ACTION |
| --- | --- |
| 1. OVERVIEW OF MiH & IWAB |  |
| 1.1 MiH 8 different locations: Zebedee’s Yard / QVS / Whitefriargate / Silver Street / Scale lane Staith / Blackfriargate Underpass / Humber Street / The Deep NH confirmed 01/01/2017 times - 16:00 – 22:00 |  |
| 2. EVENT CONTROL 01/01/2017 |  |
| 2.1 Radio Channels |  |
| 1. Joint control 2. Joint Traffic Management 3. Joint Medical channel – (KD to speak to North East Medical) 4. MiH production channel 5. IWAB Production channel 6. MiH Show control channel 7. IWAB Gates & operations channel 8. Joint Emergency channel MM confirmed 8 radio channels, MM to speak to JB to boost number to 12 MM / NH – to confirm list of radio accessories from both teams ZS confirmed Prestige will be managing own stewarding channel JP confirmed Lost Children to go on Prestige security channel | KD MM MM / NH MM MM / NH |
| 2.2 Event Control Locations |  |
| - MiH based at Festival House MM – to confirm someone from HCC events team to be in Festival House - IWAB based a C4Di ZB – 8 x people 01/01 FGH & Sarah 02/01 FHG & Sarah to move back to Festival House CC - Silver Command tbc | MM CC |
| 2.3. IWAB security |  |
| Police cover Serial = sergeant + 6 officers 1 x serial - Zone A 1 x serial - Zone B 1 x serial - The Deep 1 x serial - A63 Total 24 officers |  |
| IWAB Accreditation Kate Doyle, Tommy, Niccy + 2 NH / KD to share names of contractors with MM Additional: AAA (event control at C4Di) Event Control Pass Show Control Pass CC to nominate someone from SLT on event control KD suggested event control briefing | NH / KD CC KD |
| 2.4 Partner Reception |  |
| NH - confirmed partner reception at Hull City Hall at 18:00 NH - confirmed Martin and Shaun will be doing 2 x tours from 16:00 MM - to share photos of Martin and Shaun with JP ahead of tours | MM |
| 3. CROSSOVER 1: Underpass - High Street (stewarding & road closures) |  |
| NH / KD to place wayfinding volunteers by Blackfriargate underpass NH to place 2 x wayfinding volunteers on Scale Lane Staith NH / KD to confirm road closures | NH /KD NH /KD NH / KD |
| 4. CROSSOVER 2: Footpath next to Stage@thedock (crowd management) |  |
| NH / KD to close footpath next to Stage@theDock - 19:15 – 20:45 | ND / KD |
| 5. TIMINGS |  |
| MiH load-in NH - 16:00 on 30/12/2016 IWAB load-in ZS - 14:00 – 20:00 on 30/12/2016 ZS - 08:00 - 20:00 - 31/12/2016 ZS - LED screen on Nelson Street – 31/012/2016 (post 00:00) CC - to speak to DW about projection of static logo on New Year’s Day ZS – confirmed low-level music during exit. Cleared by 21:30 |  |
| 6. VOLUNTEERS: Information & Briefing |  |
| CC suggested both sets of volunteers to have same briefing MM confirmed gate volunteers to arrive at 14:00 and be deployed at 17:00 Briefing notes to be shared across both events NH / KD – to give ZB script for Urban Projections area | NH / KD |
| 7. A63 |  |
| To be confirmed at next meeting |  |
| 8. Table Top preparation |  |
| MM confirmed table top is on 28/11 CC to speak to James (Silver command 01/01/2017) prior to table top meeting KD – confirm whether Jon will run the table top Tabletop Guest list: - Northeast medical - Prestige - Zoe Snow (Show event manager) - Kate Doyle (Event Manager) - Jon - Amy (H&S) - FGH - Niccy Hallifax - Sarah Scenarios: - On 31/12/2016 serious incident in London, increased threat level. Suspect package in toilets under QVS found at 16:30 - 19:00 large numbers of people without tickets (est. 10, 000) gathering in marina area, some are inebriated - 19:15 vessel reported to breach exclusion zone & report of lost child last seen near waterfront (dogleg) at 19:45 - 20:30 woman found unconscious in distressed clothing near Blackfriargate underpass. On regaining consciousness, reports being sexually assault BONUS - An unauthorized drone spotted flying over crowds in QVS at 17:00 KD – suggested cross referencing responses in SAG with responses in EMP. To discuss at next meeting. | CC KD |
| 9. AOB |  |
| FGH - Additional hours need to be confirmed for staff welfare. Cannot work more than 16 hours. Events Liaison Team meeting - 31/12/2016 – 13:00 - C4Di CC – share notes | ALL CC |