## PID
Project name | Hull Truck Theatre
Last updated | 2017-01-17 | [5 empty] | Objectives & metrics
[7 empty] | Metrics |  | Target |  | Forecast/actual
Related documents | [6 empty] | # audience |  | 65000
Project plan | Draft |  | Risk management plan |  |  | Pending |  | Hull residents |  | Y
Budget | Draft |  | Marketing & comms plan |  |  | Pending |  | regional |  | Y
[8 empty] | national |  | N
Dates | [7 empty] | international |  | N
Project start date | 2016-01-25 |  | Project live date |  | 2017-01-01 |  |  | children (<16) |  | N
End of Live date | 2017-12-31 |  | End of eval. date |  | 2018-03-31 |  |  | young people (16-25) |  | N
[8 empty] | families |  | N
Categories | [7 empty] | older people (60+) |  | N
Type | Funded (strategic partner) |  |  | Strand |  | Hull Truck |  | self-identify as disabled |  | N
Season | Thru 2017 |  |  | Digital requirements |  | High |  | BME |  | N
[8 empty] | NEET |  | N
Finance | [6 empty] | # temporary jobs created |  | 100
Total project budget |  | 1500000 |  |  |  |  | # freelance contracts created |  | 50
Hull 2017 contribution |  | 650000 |  |  |  |  | # participation opportunities |  | ?
Analysis/project code(s) | [6 empty] | of which for school age |  | ?
[7 empty] | # commissions |  | 7
[7 empty] | Objective |  | Met? | Notes
People
Project Lead | Paul Clay / Henrietta Duckworth |  |  | Volunteering lead |  | Shaun Crummey
Producer | Hull Truck |  |  | Education lead |  | Ian Read
Assistant Producer | Hull Truck |  |  | Marketing lead |  | Phil Batty
Production Manager | Hull Truck |  |  | Community Eng lead |  | James McGuire
|  |  |  | Evaluation lead |  | Elinor Unwin
Performance, Residency & Legacy
What is the model for delivering this project? eg we will employ a creative team, we will outsource to an agency, we are contributing funding but no other resource… | [6 empty] | Performance: Summary of events, including dates, times, venues, ticketing strategy (free/paid, (un)ticketed), age guidelines (free text OR UKFC categories) etc. NB Do not duplicate information stored in Artifax.
Hull Truck will be contracted under the Hull 2017 Delivery Partner Agreement and Hull Truck will be responsible for artistic direction, contracting, delivery and operations for productions, marketing and creative learning. Hull 2017 support over a 24 month period will enable Hull Truck as an organisation to produce and present a year of extraordinary diverse work including World and UK premiers to firmly establish Hull Truck as a leading national producing theatre. The programme will grow and exercise the theatre's artistic muscle in the industry; double output; co-produce at an unprecedented scale; develop operationally to deliver the new scale of programme; invest and develop the local professional team working alongside national theatre companies; expand talent development and creative learning programmes; create new youth theatre production; connect and integrate the theatre with theatre across the city; develop new and increase investment in marketing; develop new audiences locally, nationally and regionally. | [6 empty] | Ticketing strategy will work with Hull Truck's extant and operational policy, ensuring key ticketing initiatives for Hull 2017 will be incorporated and deliverable. See attached annual schedule for mainhouse performances. Studio & Education programme schedule TBC
How will delivery partners be identified and procured? Refer to the procurement flowchart and note below the agreed process (A–G) for each contract. | [6 empty] | Residency: How will you realise your residency work? What opportunities will be created within the project for our education programme? How will the project help to build new audiences through engagement? Note numbers, types and duration of participation opportunities.
Hull Truck Theatre is a strategic partner for Hull 2017. Hull Truck were party to the CoC Bid. Hull Truck Theatre is an NPO and the only producing theatre in the city. Procurement process for artists, technicians, suppliers etc to be controlled through Hull Truck standard procedures. | [6 empty] | Hull Truck Creative Learning department will create and deliver a range of programmes to complement the productions and initiatives to develop artists and theatremakers. The GROW programme runs throughout the year, with a focused festival in May/June. This festival brings the best of national theatre practitioners to the city to share practice, mentoring and practical workshops.
Who are the delivery partners? (Contact & organisation name, contract status for each) | [6 empty] | Legacy: What is built into the core project that will ensure legacy?
As Delivery Partner, Hull Truck will enter co-production agreements with a variety of third parties. For the co-productions in plan, these include the following: The Royal Shakespeare Company, Northern Broadsides; Sheffield Theatres; Improbable; Spymonkey; Eclipse Theatre; | [6 empty] | New ways of working and expansion in all departments of the Theatre for 2017 - producing, production, marketing, education and operations - will provide professional development, new robust structures, intellectual property and increased audience base for the theatre's future sustainability. New and increased number of partner industry organisations for future co-commissioning and co-production; Hull Truck post 2017 will be re-positioned as a significant national partner.
Volunteer management: What is your expectation of volunteer requirements? (Numbers, roles, responsibilities, duration / period required) | [6 empty] | Project description (200–400 words) for use in marketing materials, on webpages etc. Note that this may be edited.
Through the year. Wayfinding for new visitors to the city from Station to Hull Truck Front of House support to the Hull Truck inhouse team. Performance Opportunities for at least one production: Fantastic Voyage. This is scheduled to take place in Oct/Nov. | [6 empty] | Productions will be marketed individually by title - eg Hull Truck Theatre, Hull 2017 and the Royal Shakespeare Company present The Hypocrite by Richard Bean Campaigns will be production specific.
Version control
Date | Changes and/or approvals
2016-01-19 | Greenlit at Board
ACE
British Council
HLF
Treasury
University of Hull
Big Lottery
Health
Spirit of 2012
Trusts & Foundations
Key funders

## Option sets
Status | Type | Strand | Season | Digital | Y/N
Completed | Hull 2017 Production | 365 Grant Fund | Made in Hull | Very high | Y
Draft | Hull 2017 Commission | Blast Theory | Roots & Routes | High | N
Pending | Co-commission | Caravan of Love | Freedom | Medium
| Funded (strategic partner) | Circus | Tell the World | Low
| Funded (presenting) | Codhead | Curtain Raisers
| Grant-funded | Curtain Raiser 2016 | Thru 2017
| Non-funded (strategic partner) | Dance | Post-2017
| Non-funded (presenting) | Digital commission | n/a
| Non-artistic | Film
Freedom Festival
Fuerza Bruta
Hull 2017 @ New Theatre
Hull Truck
Humber St Arts Programme
Land of Green Ginger
Literature commission
Look Up
Museums / Libraries service
Music
Neighbourhood Network
New Years Eve
PRS New Music Biennial
Radio 1 Big Weekend
Singing City
Site-specific theatre
Slung Low
Street animation
Theatre Sector dev & commissions
Turner Prize