R1BW Internal Meeting Minutes
03/04/2017

Attending:  Chris Clay, Melissa McVeigh, Helen Thackeray, Jonathon Black, Rebecca Clark

| POINT | ACTION |
| --- | --- |
| - GENERAL UPDATES |  |
| MM - to run medical/waste contracts past Will Hutchinson HT - confirmed use of Civic One CCTV cameras ACTION: MM to confirm details of welfare plan after speaking to Linda | MM |
| 2. SITE |  |
| HT - discussion with Luke (resident of the menagerie) and agree to tickets and routes in and out of property HT – requested routes for helicopters from Gary Lathan due to livestock on the top field to assess the proximity from helicopter landing to Luke’s house HT - Groundworks – Natural England want to store the mud by bus entrance and put that same mud back in place after the event. Acceptable grass seed will be ordered by Natural England |  |
| 3. TRAFFIC MANGEMENT |  |
| CC - Leconfield confirmed, Hedon no longer needed. Park & Ride sites are as follows: Walton Street, Leconfield, Paragon Interchange and one other site (either Grove Hill or Craven Park dependent on postcode data) ACTION: HT to arrange drive around to coincide with meeting 04/04/2017 | HT |
| 4. RESIDENTS |  |
| HT - discovered another cottage opposite Burton Constable. Resident keeps 18 horses, but has alternative stabling HT - Meeting with Sproatley Parish Council confirmed for 28/04/2017 ACTIONS: HT – to arrange meeting with Skirlaugh Parish Council HT – to arrange meeting in the coach house at Burton Constable for residents who couldn’t attend the Parish Council meetings HT – to liaise with Will at East Riding Council for addresses of Parish Councils and obtain a list of local farmers | HT HT HT |