## CCP To do
Creative Communites Programme - SMHS To do list:
| Notes: | Completed?
Place HOLDS in diaries for 1st workshop (Mar/Comms) - 7/8th September. | HD, CD, SMHS, DW, PB, JM, BM, Laura Smith, LD, WH | Completed 17/06
Book space for workshop - Fruit, Octagon, Freedom Centre etc? ASAP! | 100 people to attend. Wifi needed - 7/8th Septmeber, 5-8pm. Albemarle booked for 8th September - 5pm till 9pm CD to speak to HD about refreshments and budgetary issues? | Completed 20/07
Speak to SR about CCP workshop voulnteers. | 6-8 Vols needed - CD to train vols. - Email sent to SR (17/06) | Completed 21/06 - Vols form filled in.
Curation email' to be signed of by BM - ASAP | HD to check 20/06 | Completed 21/06
Speak to DW about pulling report of CCP applicant contact details. (17/06) | Email sent (17/06) Spoken to 20/06 - DW needs to look at the whole process. Follow up email sent - 29/06 | Completed 11/07
Curation' email to be sent - Check with HD which one to send to (20-21/06) | BLF email needs to be sent ASAP. | Completed 11-12/07
Chase HD & JM - make sure they are completing 'curation chats' - Check actions on main spread sheet | HD & JM have sent emails. Phone calls to be had W/C 27/06. | Completed
Process plan - check for actions |  | Ongoing
Chase James C for Flow Diagram of above (w/c 20/06) | Chat to be had 22/06 - READ BEFORE THEN. | Completed 22/06
Schedule 1' - Draft - Ask DW to create new FR form. (w/c 20/06) | Email sent 20/06 Follow - up email sent 22/06 Form started - creating form, hopefully finished by 15/07 CD to meet with DW on 13/07 | CD to continue
Ask DW to add new basket to FR for BIG A4A - different comms email. (w/c 20/06) | Email sent 22/06 | Completed 27/06
Chase HD to discuss Joint PR with BM (BIG/H17) (w/c 20/06) | W/C 27/06 - CD to complete CD has spoken to BM - Facts are being sent over to him ASAP. | Completed 28/06
HD to get BM to sign off 'Yes/No' emails. (w/c 20/06 - ASAP) | W/C 27/06 - CD to complete CD has met with BM - Feeback has been given. CD to re-draft and send to BM/HD ASAP (28/06) BM has re-drafted - CD to check No Email has been signed off w/e 08/07 | Completed w/c 11/07
HD to speak with WH about 'non-funding' agreement - with BIG CCP projects. (w/c 20/06) | W/C 27/06 - CD to complete CD has spoken to WH. WH wants to do a non-funded agreement. Meeting on 29/06 | Completed 28/06
Speak to PB about Mar/Comms Support. | 3rd follow up email sent 07/07 Follow up email sent to RB on 13/07 - replied on the 14th. Follow up sent on 21/07
Get Policies from JF - put in CCP folder. | Email sent on 20/06 Enviromental policy added to folder - Policies 2, 3, 4 due to be completed by end of June. Follow up sent 27/06 Follow up email sent 06/07 Waiting on policies to be greenlit at SLT
Speak to DW/PB about the best way to give CCP applicants the policies - Dropbox etc? (w/c 20/06) | Email sent 22/06 DW said best way would be put them on the website. | Completed 11/07
Marketing Event Form - filled in & sent to Rachael Crow | BEFORE 11TH JULY - CHAT TO CD | FW'd to CD 04/07 - Completed
Put basic Project based info into ARTIFAX | Elizabeth B started - 20/06 | Completed
Create a CCP ARTIFAX TEMPLATE (w/c 20/06) | HD to check BIG Grid | Completed 21/06
Speak to JC about PID/Big Grid/Artifax in general |  | Ongoing
Pull all the Tours/Trails in new Doc | Saved in CCP folder > Scoring > Trail View | Completed 28/06
Check Big Yes/No is right on our list |  | Completed