## Sam Lee
PRS Residencies - sesssion schedule
SAM LEE
[5 empty] | Jack D | Sam Pirt | Richard O'Neil | Belinda & Heidi
Sam Lee visits | dates |  | no days
| 14 & 15 Nov 2016 | Initial visit, Traveller sites, planning meeting | 2
| Thurs 2 & Fri 3 Feb | Visit Trinity House, Visit R Smith, Meet Sam Pirt | 2 | [7 empty] | 108.34
| Tues 14 Feb | Jack Durtnall to meet schools |  |  | 1
| Fri 24 Feb | Jack Durtnall to attend CPD with James Redwood |  |  | 1
| Tues 7 Mar | Workshops start with Jack D Trinity Academy |  |  | 1
| Wed 8 Mar | am Trinity Academy, pm Buckingham Primary with Jack D |  |  | 1
| Tues 14 Mar | Trinity Academy, Sam Lee with Jack D and Richard O'Neil | 1 |  | 1 |  | 1
| Wed 15 Mar | am Trinity Academy, pm Buckingham Primary Sam Lee with Jack D and Richard O'Neil | 1 |  | 1 |  | 1
| Tues 4 Apr | Trinity Academy with Jack D, Sam Pirt |  |  | 1 | 1
| Wed 5 Apr | am Trinity Academy, pm Buckingham Primary with Jack D, Sam Pirt |  |  | 1 | 1
| Tues 25 April | Trinity Academy with Jack D, Sam Pirt |  |  | 1 | 1
| Wed 26 Apr | am Trinity Academy, pm Buckingham Primary with Jack D, Sam Pirt |  |  | 1 | 1
| Tues 9 May | Trinity Academy with Sam Lee, Jack D, Belinda & Heidi | 1 |  | 1 |  |  | 2
| Wed 10 May | am Trinity Academy, pm Buckingham Primary with Sam Lee, Jack D, Belinda & Heidi | 1 |  | 1 |  |  | 2
| Tues 23 May | Trinity Academy with Sam Lee, Jack D and Sam Pirt | 1 |  | 1 | 1
| Wed 24 May | am Trinity Academy, pm Buckingham Primary with Sam Lee, Jack D & Sam Pirt | 1 |  | 1 | 1
| Tues 13 Jun | Trinity Academy with Jack D |  |  | 1
| Wed 14 June | am Trinity Academy, pm Buckingham Primary with Jack D |  |  | 1
| Fri 23 Jun | Rehearsals - venue to be confirmed - with Sam Lee, Jack D & Sam Pirt | 1 |  | 1 | 1
| Sat 24 June | Showcase performance at Hull City Hall, with Sam Lee, Jack D & Sam Pirt | 1 |  | 1 | 1
| Sun 2 July | Festival performance, Princes Quay, with Sam Lee, Jack D, Richard, Belinda and Heidi | 1 |  | 1 | 1 | 1 | 1
|  | TOTAL | 13 |  | 19 | 9 | 3 | 5 |  | 0
| 2017-02-02 | W/C 6 FEB | 2017-02-14 | HALF TERM | 28 FEB & 1 MAR | W/C 6 MAR | 14 & 15 MAR | 21 & 22 MAR | W/C 27 MAR | 4 & 5 APR | EASTER | 25 & 26 APR | W/C 1 MAY | 9 & 10 MAY | W/C 15 MAY | 22 & 23 MAY | HALF TERM | W/C 5 JUN | 13 & 14 JUN | W/C 19 JUN | 23 & 24 June | 27 & 28 JUNE | 2017-07-02
JACK DURTNALL | [15 empty] | FINISH & SUBMIT FINAL PIECE
SAM LEE
GUEST |  |  |  |  | SAM PIRT |  |  |  |  | SAM PIRT |  | SAM PIRT | [8 empty] | SAM PIRT - Sat |  | SAM PIRT
Topic | [6 empty] | GUEST ARTIST - RICHARD O'NEIL | [6 empty] | GUEST ARTIST - BELINDA & HEIDI |  |  |  |  | rehearsal |  | Rehearsal Fri / Perf to other comm groups Sat |  | Performance
Jack total | 1 |  | 1 |  | 2 |  | 2 |  |  | 2 |  | 2 |  | 2 |  | 2 |  |  | 1 |  | 2 |  | 1 | 18
Sam lee Total | 1 | [5 empty] | 2 | [6 empty] | 2 |  | 2 |  |  |  |  | 2 |  | 1 | 10
Sam Pirt |  |  |  |  | 2 |  |  |  |  | 2 |  | 2 |  |  |  | 2 |  |  |  |  | 1 |  | 1 | 10
Richard | [6 empty] | 2 | [15 empty] | 1 | 3
Heidi & Belinda | [13 empty] | 4 | [8 empty] | 1 | 5
Note on B31: SL up early 2nd, leave night of 3rd -Polly Eldridge

## Jason Singh
PRS Residencies - sesssion schedule
JASON SINGH
|  |  | Jason | Jez Riley French
Jason Singh visits | dates |  | no days
| 2016-11-09 |  | 1
| 2016-12-15 | Masterclass | 1
| 2017-02-27 | query availability | 1
| 2017-02-28 | Warren meeting | 1
| 2017-03-13 |  | 1
| 2017-03-14 | Warren MC/RAP session with Paul Clark tbc | 1
| 2017-03-27 | Meet Seniors | 1
| 2017-03-28 |  | 1
| 2017-04-10 | Easter Holidays | 1
| 2017-04-11 | Sound recording session with Jez and The Warren | 1
| 2017-04-24 |  | 1
| 2017-04-25 | Warren | 1
| 2017-05-08 |  | 1
| 2017-05-09 | Warren | 1
| 2017-05-22 |  | 1
| 2017-05-23 | All audio to be ready for programming by Kinicho | 1
| 2017-06-05 | Rehearsal with all artists for composed piece | 1
| 2017-06-06 | Warren/ Rehearsal with all artists for composed piece | 1
2017-06-24
|  | TOTAL | 18
Jez Riley French | dates |  | no days | day rate £180.00
half day rate £120.00
Dates Jez is already busy from Feb - July 2017.9 day section from 30th April - May 9th might change & if it does it will likely be still in May or June.
Feb:
15th in Leeds
17-19th - Kirchin festival
22nd in Manchester
March:
24th - 27th - away
28th - 4th April - around but have a few things to do locally. These can be moved if needed.
April:
certain days in April will be taken up with the Humber Bridge / Opera North project - as far as i'm aware my involvement will be perhaps 4 days during the install & the performance / public launch section.
28th - 30th - nordic festival / hull
May:
30th april - 9th May - in Estonia
11th May - performance
22nd-24th - folkestone
26th - 28th
June:
9th - 12th - northumbria
16th-20th
29th - 3rd July - involved in the Hull Uni sound & ecology symposium - this is same weekend as the PRS event so it'd be good to know when Jason't piece will be opening etc & of course any involvement you'd like from me (it'll be a weekend of running around to all the things going on that sound (!) very interesting)

## Eliza Carthy
PRS Residencies - sesssion schedule
ELIZA CARTHY
[5 empty] | Gary | Sam
ELIZA CARTHY | dates |  | no days
| 2016-09-14 |  | 1 | Visit - planning and introductions
Wed | 2017-02-08 |  | 1 | Walton St Market am walkabout, Indoor Market, |  |  | Meeting Mikey 11am |  | 2:30
Mon | 2017-02-13 | 9-11am | 1 | Wyke College, music and creative writing students together in one session – contact Ben Newton and Jamie Farrow (one of them will be waiting in reception at Wyke College for you just before 9am)
|  | 1:00-3:15pm |  | Spring Cottage Primary School (45 mins with Yr1 class followed by 45 mins with Yr5)
1.05-2.05 then 2.15-3.15
Spring Cottage Primary School, 13 Dressay Grove, Hull HU8 9JH
Contact: The Head, Andy Rhodes
|  | 5:30-6:30pm |  | Kingston Boxing club - informal chat with members of the club (They are uncomfortable about a workshop)
Hessle High Road, HU4 6 Hull (on north side of road before junction with Pickering Rd).
Contact Sean Smith who organises the club – he’s a great guy to talk to himself (ex fish filliter, his dad was a trawlerman, and he used to be a Union Activist) (tel 07504040058)
Thur | 2017-02-16 | 10:30am-12 noon | 1 | Boulevard Village Hall (community coffee morning group am)
Boulevard, Hull, HU3 2UE it’s next to the church (and there is a small car park beside the hall)
Your host is Eddy Bewsher (07748573124) another character
|  | 1:30pm |  | Visit Day Centre - Fernleigh Day Centre for the Elderly – waiting final confirmation this is OK
Contact Barbara Wright, Day Care Manager, Hull City Council
Fernleigh Day Centre, Waterloo Street, Hull, HU2 9LG
|  | 3:30pm |  | Workshop with volunteers and workers, Giroscope Housing Co-op
Giroscope Limited, 69 Coltman Street, Hull, HU3 2SJ
Liaison in advance is Sally, she’s not there on the day, but will brief volunteers to expect you, Eddy Bewsher will probably be there in this afternoon session as well. They have a room that fits 15 people, so it will be a cozy group.
Tel 01482 576374
Fri | 2017-02-17 | up until 2:15 | 1 | Morning at Trinity Market
|  | 3-4:30pm |  | ABP dock workers - at ABP Port House, Northern Gateway, Hull – HU9 5PQ (HU9 5NS for sat nav). Contact Louise Thackwray (Tel: 01472 246228¦ Mob: 07725 639462)
Fri | 2017-03-03 | 1-2:30pm and 3-4:30pm | 1 | Two afternoon workshops with Hull 2017 volunteers (30 in each session) – at the following times 1pm until 2:30pm and 3pm until 4:30pm (venue tbc) |  |  |  | hull2017 volunteers
|  | 6-7pm |  | Hindu Cultural Association - dancers (mixed ages),
Contact Uma Rajesh tel 07900 408655
Hindu Cultural Association, 7 Park St., Hull
| 2017-03-13 |  | 1 | working with Gary and Sam on music creation |  |  |  | at Eliza's Studio, Robin Hood's Bay
| 2017-03-14 |  | 1 | working with Gary and Sam on music creation, joined by Sarah Dew (PhD composition student) |  |  |  | at Eliza's Studio, Robin Hood's Bay
| 2017-03-15 |  | 1 | working with Gary and Sam on music creation |  |  |  | at Eliza's Studio, Robin Hood's Bay
|  | TOTAL | 9

## Errollyn Wallen
PRS Residencies - session schedule and planning
ERROLLYN WALLEN
Errollyn Wallen | dates | Detail | no days | EWB | Hotels | Sarah | Michael Harper | Mambo? | Gary H | Nola marshall | Orch X | Students
Thurs | 2017-01-26 | Visit Open Doors, meet key contacts working in the community, event showcasing musical achievements of local groups working with Open Doors, meet staff of Pearson and Thoresby Primary Schools at Thoresby Primary school, possibly meet local supporting artists - tbc | 1 | x6 hrs meeting & planning | accom booked |  |  | 3 hrs meeting
Fri | 2017-01-27 | planning and meet supporting artists/ student morning | 1
Thurs | 2017-03-09 | Thoresby am , Open Doors visit, Errollyn, Em, Pete and Frankie | 1 | 1 | accom booked |  |  | 1
Fri | 2017-03-10 | Pearson Primary am Errollyn and Em, planning with artists pm; Errollyn will perform at WOW Festival launch in the evening | 1 | 1 | accom booked
Sat | 2017-03-11 | Masterclass at Albemarle, Errollyn with Sarah Suckling part of WOW Festival | 1 |  | accom booked | 1
Sun | 2017-03-12 | Errollyn to contribute to panel discussion as part of WOW
Thurs | 2017-03-23 | Thoresby Primary am Errollyn with Em and Gary, with Open Doors pm Errollyn with Gary | 1 | 0.5 |  |  |  |  | 1
Fri | 2017-03-24 | Pearson Primary am - Gary alone | [6 empty] | 0.5
Thurs | 2017-04-06 | Pearson Primary am Open Doors pm Errollyn with Pete and Frankie | 1 |  |  |  |  | 1
| 2017-04-20 | Open Doors 10am-3pm - Gary Hammond alone | [6 empty] | 0.5
Tues | 2017-04-25 | Pearson at Thoresby am all day - Em and Mambo Jambo - twilight with parents |  | 1 |  |  |  | 1
Tues | 2017-05-02 | Thoresby at Pearson all day - Mambo Jambo - twilight with parents | [5 empty] | 1
thurs | 2017-05-11 | workshops Errollyn and Mambo Jambo | 1 | CANCEL??? |  |  |  | 1
Thurs | 2017-05-25 | Open Doors, plus in school workshop - Kaleidoscope week 2 at Thoresby with Errollyn, Em, Sarah, Mambo Jambo,and Gary | 1 | 1 | accom booked | 1 |  | 1 | 1
Fri | 2017-05-26 | workshops in schools - finale of Kaleidoscope week at Thoresby with Errollyn, Em, Sarah, Mambo Jambo and Gary | 1 | 1 |  | 1 |  | 1 | 1
Thurs | 2017-06-15 | workshops open doors schools together 9-5 with Errollyn, Em, Sarah, Mambo Jambo and Gary | 1 | 1 | accom booked | 1 |  | 1 | 1 |  | x
Thurs | 2017-06-22 | workshop coming together rehearsal 9-5, supporting musicians without Errollyn |  | 1 |  | 1 |  | 1 | 1 |  | x
| 2017-06-24 | Residency showcase day at Hull City Hall with Errollyn, Em, Sarah, Mambo Jambo and Gary | 1 | 1 | accom to book | 1 |  | 1 | 1 |  | x
| 2017-06-29 | Rehearsal for supergroup moment 3.30 onwards with Errollyn, Em, Sarah, Mambo Jambo and Gary | 1 | 0.5 |  | 0.5 |  | 0.5 | 0.5 |  | x
| 2017-07-01 | Mighty River performance - 2pm
| 2017-07-02 | Performance at Festival weekend - residencies, with Errollyn, Em, Sarah, Mambo Jambo and Gary | 1 | 0.5 |  | 0.5 |  | 0.5 | 0.5 |  | x
|  | TOTAL of days | 14 | 9.5 |  | 7 | 0 | 11 | 8 |  | 5
|  |  |  | EWB | Hotels | Sarah | Michael Harper | Mambo? | Gary H |  | Orch X | Students
Draft Budget
EW travel & expenses |  |  | Fee |  | Travel | Accom | Expenses
|  |  | 6000 |  | 1120 | 589.19 | 280
Supporting artists |  |  |  |  | Travel | Accom | Expenses
Em Whitfield Brooks | 1/2 day planning meeting re workshop activity in school and community on 26 Jan |  | 50 |  | 50
| 8 full days in schools & open doors re vocal confidence & performance |  | 2400 |  | 350
including working with parents in twilight sessions
| 3 half day rehearsals |  | 600 |  | 150
Mambo Jambo | 12 full days with open doors and schools (£280 for full day, £200 half day) |  | 3360
| 2 half day rehearsals |  | 360
Gary Hammond | 6 full day sessions with EW - workshop support in Open Doors and with Schools - percussionist, plus 4 half days |  | 1800
Sandy Clarke and Stanislava |  | Student support up to 4 days - DBS checks |  |  |  |  | 88
Members of Orchestra X | 5 days with EW - 2 members at day rate of £300 plus travel, accom on 29 jun & 1 Jul |  | 3000 |  | 680 | 260
Sarah Suckling (Cellist) | 1 day on 10 March - Albemarle Saturday |  | 300 |  | 120 | 65
| 6 project days |  | 1800 |  | 640 | 260
Grant to Open Doors for facilitation
| based on 10 days | [5 empty] | 2357.5
|  |  | Fees |  | Travel | Accom | Expenses
|  | TOTAL visiting supporting artists | 19670 | 0 | 3110 | 1174.19 | 2725.5
|  | total for whole residency | 26679.69
|  | BUDGET for whole residency | 26120
|  | difference | 559.69
Open Doors schedule
thurs | 2017-03-09 | afternoon at Open Doors, with Errollyn Wallen, Em Whitfield Brooks, and Mambo Jambo
thurs | 2017-03-16
thurs | 2017-03-23 | afternoon at Open Doors, with Errollyn Wallen, Em Whitfield Brooks, and Gary Hammond (percussionist)
thurs | 2017-03-30
thurs | 2017-04-06 | afternoon at Open Doors with Errollyn Wallen and Mambo Jambo
thurs | 2017-04-13
thurs | 2017-04-20 | Open Doors 10am-3pm - Gary Hammond
thurs | 2017-04-27
thurs | 2017-05-04
thurs | 2017-05-11 | Errollyn and Mambo Jambo | CANCEL
thurs | 2017-05-18
thurs | 2017-05-25 | Open Doors in the afternoon, plus in school workshop - Kaleidoscope week 2 at Thoresby
| 2017-05-26 | workshops in schools - finale of Kaleidoscope week at Thoresby, Open doors clients invited to join in
thurs | 2017-06-01
thurs | 2017-06-08
| 2017-06-15 | workshops open doors schools together 9-5 - all artists at school
| 2017-06-22 | workshop coming together rehearsal 9-5 - all Residency participants during the day - all artists
| 2017-06-24 | Residency showcase day at Hull City Hall - everyone
| 2017-06-29 | Rehearsal for supergroup moment 3.30 onwards - involvement tbc
| 2017-07-02 | Afternoon 'supergroup' performance at Festival weekend
total 14 Open Doors music sessions at Open Doors from 9 Mar to 8 Jun
Per session costs for Open Doors
|  | Room hire | 20
|  | Interpretation 6 per session at £15 | 90
|  | Assistant Workshop Leader expenses x 3 | 75
|  | Participant expenses (taxi/bus fares) | 20
|  | Administration fee for Open Doors @ 15% | 30.75
|  | TOTAL per session | 235.75
|  | TOTAL for 14 sessions | 3300.5
|  | TOTAL for 10 sessions | 2357.5

## Brian Irvine
PRS Residencies - sesssion schedule
BRIAN IRVINE
BRIAN IRVINE | dates |  | no days
| 2016-11-30 |  | 1 | Emmaus - possibly separate from Crossings because of issues around sobriety
Thurs | 2017-03-02 |  | 1
Buckingham Day Centre pm
3:30/4pm 6pm Crossings at Emmaus
Fri | 2017-03-03 | 10:30-12noon - Big Elastic Band - P&F Homes | 1
Mersey PS pm
Thurs | 2017-04-06 |  | 1
Buckingham Day Centre pm
3:30/4pm 6pm Crossings at Emmaus
Fri | 2017-04-07 | 10:30-12noon - Big Elastic Band - P&F Homes | 1
Mersey PS pm
Thurs | 2017-05-04 |  | 1
Buckingham Day Centre pm
3:30/4pm 6pm Crossings at Emmaus
Fri | 2017-05-05 | 10:30-12noon - Big Elastic Band - P&F Homes | 1
Mersey PS pm
Thurs | 2017-05-25 |  | 1
Buckingham Day Centre pm
3:30/4pm 6pm Crossings at Emmaus
Fri | 2017-05-26 | 10:30-12noon - Big Elastic Band - P&F Homes | 1
Mersey PS pm
Sats | 2017-05-27 | Albemarle Saturday masterclass | 1
Thurs | 2017-06-01 |  | 1
Buckingham Day Centre pm
3:30/4pm 6pm Crossings at Emmaus
Fri | 2017-06-02 | 10:30-12noon - Big Elastic Band - P&F Homes | 1
Thurs | 2017-06-22 | Groups coming together | 1
Buckingham Day Centre pm
3:30/4pm 6pm Crossings at Emmaus
Fri | 2017-06-23 | Groups coming together | 1
Sat | 2017-06-24 | Sharing event all day at Hull City Hall | 1
Thurs | 2017-06-28 | rehearsal | 1
Fri | 2017-06-29 | rehearsal | 1
Sun | 2017-07-02 | performance at NMB Festival | 1
|  | TOTAL | 18
02/3 March 2017
6/7 Apr 2017
4/5 May 2017
18/19 May 2017
27 May tbc
1/2 June 2017
15/16 June 2017
22/23 June 2017
28/29 June 2017
pop in at Broadway Pavillion, off the broadway drive, HU9 3PA, HU9 3PB (at Back of Broadway Manor, off Broadway Village)
Mersey dates |  |  | 2 March, 6 April, 4 May, 25 May, 1 June, 22 June

## James Redwood CPD
James Redwood CPD sessions
CPD sessions for students and local musicians
Date | Venue | Details
Friday 4 November | University of Hull | am local leaders, pm joined by students
Friday 24th Feb | University of Hull
Friday 21st April | University of Hull

## Other relevant dates
Albemarle Saturdays
2016-03-11 | pos Errollyn Wallen (tbc)
2016-04-08
13 or 20 May
2016-06-17
2016-07-08
2016-08-05
2016-09-09
2016-10-07
2016-11-04
2016-12-15 | Jason Singh Masterclass

## Sheet1
Gary Hammond - for Errollyn's residency
| Thurs | 2017-03-23 | Thoresby Primary am Open Doors pm | 1
| Fri | 2017-03-24 | Pearson Primary am - Gary alone morning only | 0.5
|  | 2017-04-20 | Open Doors 10am-3pm | 1
| Mon | 2017-05-15 | Workshops in first week of Kaleidoscope for Thoresby and Pearson
| Tues | 2017-05-16 | Workshops in first week of Kaleidoscope for Thoresby and Pearson
| Wed | 2017-05-17 | Workshops in first week of Kaleidoscope for Thoresby and Pearson
| Thurs | 2017-05-18 | Workshops in first week of Kaleidoscope for Thoresby and Pearson
| Fri | 2017-05-19 | Workshops in first week of Kaleidoscope for Thoresby and Pearson
| Thurs | 2017-05-25 | Open Doors, plus in school workshop - Kaleidoscope week 2 at Thoresby | 1
| Fri | 2017-05-26 | workshops in schools - finale of Kaleidoscope week at Thoresby | 1
| Thurs | 2017-06-15 | workshops open doors schools together 9-5 | 1
| Thurs | 2017-06-22 | workshop coming together rehearsal 9-5 | 1
|  | 2017-06-24 | Residency showcase day at Hull City Hall | 1
|  | 2017-06-29 | Rehearsal for supergroup moment 3.30 onwards | 0.5
|  | 2017-07-02 | Performance at Festival weekend | 1
|  |  | TOTAL of days | 9
Gary H
DBS ruling re frequency: once a week or more or four or more times in any 30 day period