Larkin Exhibition
Fri 10 June 2016

Present: SW, JB, PP, IR, HD, JT
Apologies: GC, SH

Notes												Actions
Guest Curator		Invitations to be sent to Alan Bennett and David Walliams		GC
			- taking 2 options from GC shortlist 	

 			Discussion confirmed that other names on list were ideal for 
			being part of an accompanying animation programme.

Dates 			Aim for exhibition at Uni still for June/July/Aug/Sept with a celebrity 	General
 			curator.  Acknowledgement, that this is a long exhibition without a 
 			‘blockbuster’ ticket.
 			Final dates awaiting confirmation from Uni re National Portrait Gallery
 			exhibition, which it is hoped will firm for March/April/May – or possibly
 			April/May/June.

ACE Process		PLS to open account and set up profile.  					PP
 			PLS to send background info on recent artistic projects undertaken 
 			eg Larkin 25, the statue, Poet’s corner to James T.

			Link to ACE website and guidelines to be shared				JT

 			Aim for group to share information to build application for 		ALL
  			submission by end June; mid July at latest.

Project Dev		Summary outline from GC and original exhibition design details		SW
			to be shared;  use as basis for project summary for ACE bid

BBC			Request to access BBC archives by Simon Wilson 			HD
 			Following up through Spoken Word Festival contact.

Marketing & Aud Dev	Discussion confirmed aim for exhibition to widen audiences:
 			- to reach across the city and share the asset of the collection with the 
 			people of Hull and region
  			- to draw national and international visitors

 			Discussion ensued re requesting Project Room (local programmers)
 			to ‘hack’ a new Larkin game!  Provoked by Larkin.

 			Identified need to establish target age for the exhibition 		IR/SW

Learning &  		Exploration of Larkin’s inclusion, or not, on school syllabus 		IR
Participation		inc 6th Form & Hull College
 			Exploration of Larkin modules and undergrad / postgrad teaching 	IR
 			at Uni.  
 			Connect Ian Read with Elisabeth Salter, Head of English, at the Uni	HD

Budget			Share project outline & budget by email with Henrietta			SW
 			Budget to show project expenditure and with whom expenditure
 			will reside, to clarify roles & responsibilities re contracts and financial
 			mgt for project.

MoU	Develop MoU to describe relationship between History Centre		HD
PLS and Hull 2017.